SOUTH DUBLIN COUNTY COUNCIL

COMHAIRLE CHONTAE ÁTHA CLIATH THEAS

# MEETING OF TALLAGHT AREA COMMITTEE (1)

Monday 4th December 2006

Item H-I 5

Report on Implementation of Traveller Accommodation Programme 2005 - 2008

The assessment of Traveller accommodation needs conducted in association with the process leading to the adoption of the Traveller Accommodation Programme 2005 - 2008 indicated that there is a need to provide 215 units of Traveller-specific accommodation throughout the County during the course of the programme.  This accommodation is to cater for both immediate requirements and future family formations.

To date, 31 units of Traveller-specific accommodation have been delivered throughout the county under the 2005 – 2008 programmes and it is anticipated that 28 units of permanent accommodation will be completed in 2006.

The Council adopted the Traveller Accommodation Programme 2005 – 2008 unanimously on 9th May 2005.

The incomplete elements of the previous accommodation programme form the first phase of the current accommodation programme.

The following is the current position on developments at various stages of delivery in this Area Committee’s jurisdiction.

| Traveller Accommodation Programme 2005 – 2008 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Scheme |  | Type and No. of Units | Part X/8 Advertised |  | Architect |  | Comments |  |
| Belgard Park |  | R.C.P. – 10 Bays |  |  |  |  | Residents moved into RCP on 5th May 2005. |  |
| Daletree Place |  | 10 Group Houses |  |  |  |  | Residents moved into houses in August 2005. |  |
| St. Aidan’s Close Brookfield |  | 5 Group Houses | 22/04/03 |  |  |  | Families moved in to houses on 3rd May 2006. |  |
| Hazel Hill, Killinardin |  | Group Houses – 5 R.C.P. – 5 Bays | Completed |  | M.V. Cullinan |  | Accommodation completed: ESB in process of connecting power supply. Units will then are ready for occupation. |  |
| Fortunestown |  | 10 Group Houses – |  |  | SBA |  | Scheduled to be completed in Dec. 2006. |  |
| Rathcoole | 10 group houses |  |  |  |  | Arch Services Dept |  | Brief for revised Part 8 process for group housing being prepared. |
| Stocking Lane | 10-bay RCP |  |  | December 2004 |  | GAP Architects |  | Went to tender on 15th November 2006. |

Belgard Road Re-development - Scheduled to start construction in 2008.  Further progress on this scheme dependent on ITT Master Plan.

Brittas – at site identification stage.