COMHAIRLE CHONTAE ATHA CLIATH THEAS

SOUTH DUBLIN COUNTY COUNCIL

# MEETING OF TERENURE-RATHFARNHAM  AREA COMMITTEE (2)

TUESDAY 12th DECEMBER 2006

HEADED ITEM NO: 2

## Report on Housing Construction Programme:

The up-to-date position of the construction programme for the Terenure/Rathfarnham area is set out in the detail below: -

Completions 2004:-

Terenure/Rathfarnham Area

| Scheme Name | No. Of Units | Completion |
| --- | --- | --- |
| Whitechurch Phase 3 | 7 | September, 2004 |
| Whitechurch Phase 3 | 2 | December, 2004 |
| ### Sub Total | 9 |  |

Completions in 2005:-

Terenure/Rathfarnham

| Scheme | No. Of Units | Completion |
| --- | --- | --- |
| Whitechurch Phase 3 | 4 | April, 2005 |
| Whitechurch Phase 3 | 4 | May, 2005 |
| ### Whitechurch Phase 3 | 2 | July 2005 |
| ### Sub Total | 10 |  |

ON SITE:-

Terenure/Rathfarnham

| Scheme Name | No of Units |
| --- | --- |
| ## Whitechurch Phase 4 (SH242) | 29 & Community facility Anticipated completion date December 2007 |
| ## Sub Total | 29 & Community facility |

Part 8 Approved by Council:-

Terenure/Rathfarnham

| ### Scheme | No of Units |
| --- | --- |
| ## Whitechurch Phase 5 | 7 |
|  | Negotiated Tender Report submitted to The Department of the Enviroment Heritage and Local Government on 30th September. It is anticipated that the contract will be in place before the end of 2006. |
| ## Sub Total | 7 |

At Concept/Design Stage:-

Terenure/Rathfarnham

| Scheme | No. of Units |
| --- | --- |
| Kingston / Glendoher Palmer Park / Pearse Brothers Park | Preliminary design concept for infill housing noted at October ACM. Two Deputation meetings held with residents. Consultation with residents to determine accommodation requirements is in progress to inform design brief. Recommendations from members also to be incorporated into brief. |

Other potential sites are also being examined.