COMHAIRLE CHONTAE ÁTHA CLIATH THEAS

SOUTH DUBLIN COUNTY COUNCIL

# MEETING OF TALLAGHT AREA COMMITTEE (1)

Monday, 15th January 2007

Headed Item No. 9

## Report on Housing Construction Programme:

The up-to-date position of the construction programme for the County area is set out in the detail below: -

Completions in 2004:-

| Total | No. of Units | 81 |
| --- | --- | --- |

Completions in 2005:-

| Scheme Name | No. of Units | Completion Dates |
| --- | --- | --- |
| Russell Square | 110 | 2005 |
| Bawnlea | 7 | March 2005 |
| Jobstown Village Core | 10 | March 2005 |
| Cushlawn, Phase II | 31 | 2005 |
| Daletree, Ballycragh | 8 | September 2005 |
| Fettercairn Village | 22 | 2005 |
| Sub Total | 188 |  |

Completions in 2006:-

| Total | No. of Units | Completion Dates |
| --- | --- | --- |
| Fettercairn Village | 9 | February 2006 |
| Fettercairn Village | 8 | May 2006 |
| Deerpark (Joint Venture) | 11 | May 2006 |
| Deerpark (Joint Venture) | 14 | August 2006 |
| Deerpark (Joint Venture) | 16 | September 2006 |
| Deerpark (Joint Venture) | 14 | October 2006 |
| Fettercairn PH2 & Community Facility | 2 | October 2006 |
| Deerpark (Joint Venture) | 29 | November 2006 |
| Fortunestown B, Phase 2 | 38 | November 2006 |
| Deerpark ( Joint Venture | 35 | In phases from May 2006 |
| Fortunestown B Phase 4 | 120 | December 2006 |
| Daletree (Part V/Joint Venture) | 24 | December 2006 |
| Sub Total | 320 |  |

Completions in 2007:-

| Scheme Name | No. of Units | Completion Dates |
| --- | --- | --- |
| Fortunestown B Phase 2 | 28 | January 2007 |

### On Site:-

| Scheme Name | No. of Units | Completion Dates |
| --- | --- | --- |
| Fortunestown B, Phase 1 | 110 | In phases from early 2007 |
| Avonbeg, Phase 3 | 47 | February 2007 |
| Hunterswood (Heathersett) (Part V) | 37 | First quarter 2007 |
| Brookfield Village+ Community Facility | 16 | First quarter 2007 |
| Daletree | 3 | Second Quarter 2007 |
| Deerpark (Part V) | 36 | First quarter 2007 |
| Castlepark | 9 | June 2007 |
| Cushlawn Phase 3 | 22 | December 2007 |
| Greenhills Road (Part V) | 9 | December 2007 |
| Kilcarrig Phase 3 | 80 | 4th Quarter 2008 |
| Sub.Total | 369 |  |

Tenders Recommended

| Scheme Name | No. of units | No of Units |
| --- | --- | --- |
| Kiltalown Green | 28 | Contracts to be signed December 2006 .Commencing on site Mid Feb 2007 |
| Sub Total | 108 |  |

Tender Advertised

| Scheme Name | No. of units | No of Units |
| --- | --- | --- |
| Avonbeg Phase 4 | 7 | Closing Date for receipt of tenders 18/01/2007 |
| Sub Total | 7 |  |

Tender Production

| Scheme Name | No. of Housing Units |  |
| --- | --- | --- |
| Rossfield (old shop site) | 9 | Cost Plan Report approved by DoEHLG on 25/9/06. Target Tender date 1st Quarter 2007 |
| Fettercairn Phase 2 | 33 | Target tender date March 2007 |
| Sub Total | 42 |  |

Part 8 Approved by Council:-

| Scheme Name | No. of Housing Units |  |
| --- | --- | --- |
| ### Fortunestown B, Phases 3 & 5 | 160 | Draft procurement plan for affordable scheme being prepared. Target tender date 1st quarter 2007 |
| ### Knockmore House (incl. 15 units for Bernardos) | ### 96 | ### Cost plan submitted to DoEHLG 23rd November 2006 (including 6 no. units at Donomore Avenue) |
| ### Castletymon | 32 | Cost plan to be finalised for 32 units for submission to DOE in Jan 2007 |
| ### Total | 288 |  |

At Concept/Design Stage:-

| ### Scheme Name | ### Approx. No. Of Units |  |
| --- | --- | --- |
| ### Kilclare, Phase2 | ### 30 | Concepts presented to Area Committee Meeting held on 16/06/2003 |
| ### Kilclare Phase3 | ### 15 |  |
| Whitestown Stream | 147 | Private/affordable/social/ voluntary units |
| Suncroft | 10 | Possible affordable option. Concept Presented to ACM on 14/12/2006 |
| Whitebrook Park | 25 | Concept presented to Area Committee Meeting held on 20/09/2004. Land transfer to be finalised by development department |
| ### Stocking Lane | 150 | Concept presented to Area Committee Meeting in June 2006 |
| ### Swiftbrook | 11 | Concept presented to Tallaght Area Committee Meeting 08/12/04 |
| ### Deerpark Infill | 9 | Concept presented to Tallaght Area Committee Meeting 20/11/06 |
| ### Sub Total | 397 |  |

Other potential sites are also being examined.