COMHAIRLE CHONTAE ATHA CLIATH THEAS

SOUTH DUBLIN COUNTY COUNCIL

# MEETING OF TERENURE-RATHFARNHAM  AREA COMMITTEE (2)

TUESDAY 13th FEBRUARY 2007

HEADED ITEM No: 4

## Report on Housing Construction Programme:

The up-to-date position of the construction programme for is set out in the detail below: -

COMPLETIONS 2004

Terenure/Rathfarnham Area

| Scheme Name | No. Of Units |  |
| --- | --- | --- |
| Whitechurch Phase 3 | 9 |  |
| ### Sub Total | 9 |  |

Tallaght

| Scheme Name | No. Of Units |  |
| --- | --- | --- |
| Cushlawn Phase 1 | 28 |  |
| Tymon Park | 2 |  |
| Bolbrook | 11 |  |
| Kilcarrig 2 | 8 |  |
| Russell Square | 5 |  |
| ### Marlfield | 26 |  |
| ### Sub Total | 80 |  |

Lucan/Clondalkin

| Scheme Name | No. Of Units |  |
| --- | --- | --- |
| Old Church Avenue | 4 |  |
| Balgaddy A | 84 |  |
| Balgaddy B | 44 | +24 Voluntary Units |
| ### Sub Total | 132 |  |

| SUMMARY COMPLETIONS 2004 |  |  |
| --- | --- | --- |
| SDCC Completions | 221 |  |
| Voluntary Completions | 24 |  |
| Purchases | 20 |  |
| ### Total | 265 |  |

COMPLETIONS 2005

Terenure/Rathfarnham

| Scheme | No. Of Units |  |
| --- | --- | --- |
| Whitechurch Phase 3 | 10 |  |
| ### Sub Total | 10 |  |

Tallaght

| Scheme Name | No. of Units |  |
| --- | --- | --- |
| Marlfield | 1 |  |
| Russell Square | 110 |  |
| Bawnlea | 7 |  |
| Jobstown Village Core | 11 |  |
| Cushlawn, Phase II | 31 |  |
| Daletree, Ballycragh | 8 |  |
| Fettercairn Village | 22 |  |
| Sub Total | 190 |  |

Lucan/Clondalkin

| Scheme Name | No of Units |  |
| --- | --- | --- |
| Liscarne | 38 |  |
| Harelawn | 10 |  |
| Moorfield | 14 |  |
| Total | 62 |  |

| SUMMARY COMPLETIONS 2005 |  |  |
| --- | --- | --- |
| SDCC Completions | 262 |  |
| Purchases | 9 |  |
| ### Total | 271 |  |

COMPLETIONS 2006

Lucan/Clondalkin

| Scheme Name | No of Units |  |
| --- | --- | --- |
| Moorfield | 9 |  |
| Ballyowen Hall (Part V) | 12 |  |
| Shancastle | 26 |  |
| Moorfield | 21 |  |
| Mayfield ( SH 244) | 36 |  |
| St Finians | 4 |  |
| Sub Total | 108 |  |

### Tallaght

| Total | No. of Units |  |
| --- | --- | --- |
| Fettercairn Village | 19 |  |
| Deerpark (Joint Venture) | 119 |  |
| Fortunestown B, Phase 2 | 38 |  |
| Fortunestown B Phase 4 | 120 |  |
| Daletree (Part V/Joint Venture) | 24 |  |
| Sub Total | 320 |  |

| SUMMARY COMPLETIONS 2006 |  |  |
| --- | --- | --- |
| SDCC Completions | 428 |  |
| Purchases | 20 |  |
| ### Total | 448 |  |

COMPLETIONS 2007

### Tallaght

| Scheme Name | No. of Units | Completion Dates |
| --- | --- | --- |
| Fortunestown B Phase 2 | 28 | January 2007 |

ON SITE:-

Terenure/Rathfarnham

| Scheme Name | No. of Units | Completion Dates |
| --- | --- | --- |
| ## Whitechurch Phase 4 (SH242) | 29 | + Community facility. December 2007 |
| ## Sub Total | 29 | 29 & Community facility |

### Tallaght

| Scheme Name | No. of Units | Completion Dates |
| --- | --- | --- |
| Fortunestown B, Phase 1 | 110 | In phases from early 2007 |
| Avonbeg, Phase 3 | 47 | February 2007 |
| Hunterswood (Heathersett) (Part V) | 37 | First quarter 2007 |
| Brookfield Village | 16 | + Community Facility. March 2007 |
| Daletree | 3 | Second Quarter 2007 |
| Deerpark (Part V) | 36 | First quarter 2007 |
| Castlepark | 9 | June 2007 |
| Cushlawn Phase 3 | 22 | December 2007 |
| Greenhills Road (Part V) | 9 | December 2007 |
| Kilcarrig Phase 3 | 80 | 4th Quarter 2008 |
| Sub.Total | 369 |  |

Lucan/Clondalkin

| Scheme Name | No. Of Units | Completion |
| --- | --- | --- |
| Balgaddy “C” (SH 161) | 85 | + (65 Voluntary Units) March 2007 |
| Balgaddy “D” (SH 209) | 65 | September 2007 |
| Balgaddy “E” (SH 210) | 100 | Delayed due to Public Lighting issues |
| Kilcronan (SH 182) | 21 | (+ 32 Voluntary units) December 2007 |
| Lindisfarne (SH 297) | 5 | December 2007 |
| “Cherryville”, New Rd. Clondalkin (SH286) | 9 | Feb 2007 |
| Fonthill (Cowan’s) (Part V) | 7 | December 2007 |
| Sub-total | 292 |  |

| SUMMARY SCHEMES ON SITE | No. Of Units |  |
| --- | --- | --- |
| SDCC | 690 |  |
| VOLUNTARY | 97 |  |
| ### Total No. of units on site | 787 |  |

TENDERS APPROVED

### Tallaght

| Scheme Name | No. of units | No of Units |
| --- | --- | --- |
| Kiltalown Green | 28 | Contracts signed December 2006 Due to commence on site Mid Feb 2007 |
| Sub Total | 28 |  |

Terenure/Rathfarnham

| ### Scheme | No of Units |  |
| --- | --- | --- |
| ## Whitechurch Phase 5 | 7 | Negotiated Tender Report approved by The Department of the Environment Heritage and Local Government. Work due to commence in February 2007 |
| ## Sub Total | 7 |  |

TENDER ASSESSMENT

### Tallaght

| Scheme Name | No. of units | No of Units |
| --- | --- | --- |
| Avonbeg Phase 4 | 7 | Tenders being assessed |
| Sub Total | 7 |  |

TENDERS ADVERTISED

No Schemes

TENDER PRODUCTION

Lucan/Clondalkin

| Scheme Name | No. of units |  |
| --- | --- | --- |
| Rowlagh (SH165) | 5 | Part V option being considered – tenders being prepared |
| Harelawn | 20 | Cost plan approved the 18th of September, Tender target date 2nd Quarter 2007 |
| Sub Total | 25 |  |

Tallaght

| Scheme Name | No. of Units |  |
| --- | --- | --- |
| Rossfield (old shop site) | 9 | Target Tender date 2nd Quarter 2007 |
| Fettercairn Phase 2 | 33 | Target Tender date 2nd Quarter 2007 |
| Sub Total | 42 |  |

PART 8 APPROVED BY COUNCIL

Lucan/Clondalkin

| Scheme | No of Units |  |
| --- | --- | --- |
| Lealand (SH 279) | 7 | Cost plan submitted to DoEHLG for approval on 26/10/06 |
| Airlie Heights | 5 | Cost plan submitted to DoEHLG for approval on 25/1/07. Target tender date May/June 2007 |
| Old Church , Clondalkin | 4 | Cost plan being prepared |
| Sub Total | 16 |  |

Tallaght

| Scheme Name | No. of Units |  |
| --- | --- | --- |
| ### Fortunestown B, Phases 3 & 5 | 160 | Draft procurement plan for affordable scheme being prepared. Target tender date 1st quarter 2007 |
| ### Knockmore House (incl. 15 units for Bernardos) | ### 96 | ### Cost plan submitted to DoEHLG 23rd November 2006 (including 6 no. units at Donomore Avenue) |
| ### Castletymon | 32 | Cost plan to be finalised for 32 units. |
| ### Total | 288 |  |

PART 8 ADEVERTISED

Lucan/Clondalkin

| Scheme Name | No. of Units |  |
| --- | --- | --- |
| Newcastle Lyons | 34 | +10 traveller units + Community Facility. Closing date for receipt of submissions 29/01/2007. Report to be submitted to February ACM and March Council Meeting |

CONCEPT / DESIGN STAGE

Terenure/Rathfarnham

| Scheme Name | No. of Units |  |
| --- | --- | --- |
| Kingston / Glendoher Palmer Park / Pearse Brothers Park | 10 | Target date for commencement of Part 8 process first quarter 2007 |

Lucan/Clondalkin

| Scheme | Approx. No. Of Units |  |
| --- | --- | --- |
| Balgaddy West | 200 | Proposed exchange of lands with Shelbourne Developments |
| Nangor | 160 |  |
| Balgaddy B1 + Community Centre | 14 |  |
| ### Tony Kearns Motors Site, Palmerstown | 5 | Concept to be prepared |
| ### Balgaddy F | 114 | Approved plan under review |
| ### Sub Total | 493 |  |

Tallaght

| ### Scheme Name | ### Approx. No. Of Units |  |
| --- | --- | --- |
| Suncroft | 10 | Possible affordable option. Concept Presented to ACM on 14/12/2006 |
| ### Stocking Lane | 150 | Concept presented to Area Committee Meeting in June 2006 |
| ### Swiftbrook | 11 | Concept presented to Tallaght Area Committee Meeting 08/12/04 |
| ### Deerpark Infill | 9 | Concept presented to Tallaght Area Committee Meeting 20/11/06 |
| ### Sub Total | 180 |  |

Other potential sites are also being examined.