COMHAIRLE CONTAE ÁTHA CLIATH THEAS
SOUTH DUBLIN COUNTY COUNCIL

MEETING OF TALLAGHT AREA COMMITTEE 2

Monday, October 01, 2007

QUESTION NO. 14

QUESTION: Councillor M. Corr

"To ask the Manager when it is anticipated that the first draft of the West Oldcourt Local Area Plan will be ready and will he make a statement on the matter?"

REPLY:

At the moment a number of issues remain to be resolved regarding the proposed Draft Local Area Plan, namely:

- Resolving access and circulation given the existing pattern of traffic in the area. This was a key issue in the pre-draft public consultation

- The treatment of the existing 220Kv power line that traverses the land, and accommodating two existing raw water trunk mains that also traverse the Draft Local Area Plan lands

Satisfactory resolution of these issues will result in a significantly improved environment for the Draft Local Area Plan lands and surrounding area.

In terms of the timetable, this depends on the date of the public notice announcing the preparation of the Draft Local Area Plan, which in turn is linked to the dates of the Tallaght Area Committee meetings in October or November 2007.  There will be a briefing for local Councillors on the Draft Local Area Plan in advance of the Area meeting

At present it is more likely that the public notice will be given in November with the resultant timetable as follows:

- Presentation of Draft Local Area Plan to Tallaght Area Committee: Depending on the resolution of the above two issues, this could take place at  the Tallaght Area Committee on 26/11/07.

- Public Notice/Display (six weeks + 1 additional week for Christmas week), 27/11/07 to 15/01/08. An advertisement is placed in the press (on 27/11/07) announcing the preparation of the Draft Local Area Plan. Notice and a copy of the draft plan is also sent to the Planning Appeals Board and to prescribed bodies. Draft Plan goes on display for a minimum period of 6 weeks during which submissions/ observations are invited from the public and all interested parties.

- Manager’s report. A Managers report on submissions/ observations is prepared and submitted to the Councillors for their consideration not later than 12 weeks after notice of the preparation of the Draft Local Area Plan is published in the press. (i.e. not later than 18/02/08).

- Managers report submitted to Councillors for consideration. Councillors have 6 weeks to consider report and adopt/amend the plan. (until 01/04/08). TAC meeting on 24/3/2008

- Amendment of Draft Local Area Plan. If the Councillors decide to amend the Draft Local Area Plan otherwise than is recommended in the Managers report, the Planning Authority must publish notice of the proposed variation or modification not later than 3 weeks after the passing of a resolution to materially alter the plan.(until 22/04/08)

5(i). Display of Proposed Variation. Proposed variation of Draft Local Area Plan must go on public display for not less than 4 weeks.  Written submissions/observations received in respect of material alterations to the Draft Local Area Plan are put on public display.

5(ii). Manager’s report on submissions/observations on Proposed Variation. Manager’s report to be prepared on submissions/observations received in respect of material alterations to the Draft Local Area Plan not later than 8 weeks after notice of the proposed variation or modification is published.

5(iii). Councillors consider the proposed variation/modification and report of the Manager. Councillors make or amend the Draft Local Area Plan with variations(s) proposed by the Planning Authority or, if different, as recommended in the Manager’s report not later than 6 weeks after receiving the report.