South Dublin County Council

Disability Act Implementation Plan 2008-2010

‘ENABLING ACCESS – ENSURING EQUALITY OF OPPORTUNITY’

“Disability in relation to a person, means a substantial restriction in the capability of the person to carry on a profession, business or occupation in the State or to participate in social or cultural life in the State by reason of an enduring physical, sensory, mental health or intellectual impairment (Disability Act 2005)”.

South Dublin County Council recognises that language is a very powerful and evocative tool.  Therefore, the language and terminology used in this document has been carefully chosen to reflect the values of equality and empowerment underpinning this Disability Act Implementation Plan. The term ‘disabled people’ has been used throughout the Policy as per the UPIAS classification of disability and impairment which has been developed by disabled people themselves (UPIAS 1976). Where disabled people are referred to in this plan this should be understood to include all disabled people, including those with learning difficulties, mental health difficulties and sensory impairments. The UPIAS classifications are consistent with the social model of disability and make an important distinction between the terms impairment and disability as follows:

- Impairment - Lacking part or all of a limb or having a deflective limb, organ or mechanism of the body (including psychological mechanisms).

- Disability – The restrictions caused by the organisation of society which does not take into account individuals with physical or psychological impairments (UPAIS, 1976).

This document is available in a number of different formats on request

Note – To go to the Section listed below, hold the cursor over the title, press Ctrl and left-click

Foreword – Mayor	3

Introduction from the County Manager	3

1. INTRODUCTION	3

1.1.  Introduction	3

1.2. Vision, Strategy and Aim	3

1.3. Disabled People in South Dublin County	3

2.  POLICY FRAMEWORK – NATIONAL LEVEL	3

2.1.The Disability Act (2005)	3

2.2.DEHLG Sectoral Plan	3

2.3. NDA Guidelines	3

3. POLICY FRAMEWORK AND BACKGROUND – COUNCIL LEVEL	3

3.1 The Council as Employer	3

3.2 The Council as Service Provider	3

3.3. Equality Promotion Achievements	3

3.4. Future Equality Commitments	3

3.5. Section Summary	3

4.THE BUILT ENVIRONMENT	3

4.1. Introduction	3

4.2  South Dublin’s County Development Plan, 2004-2010	3

4.3. Development Management Guidelines	3

4.4. Architectural Services Department Commitment to Universal Design	3

4.5. Building Control	3

4.6.  Planning Information	3

4.7.  Section Summary	3

5	DEVELOPMENT OF THE DISABILITY ACT IMPLEMENTATION PLAN	3

5.1. Approach	3

5.2. Access Auditing	3

5.3. Consultation Process	3

5.4. Development of Action Matrices:	3

6.  SUMMARY OF PART ONE	3

PART TWO – ACTION MATRICES	3

1.INTRODUCTION	3

1.1. Approach, Timing and Prioritising of Actions	3

1.2. Budget and Timescales	3

1.3. Monitoring Implementation	3

2.	CORPORATE COMMITMENTS	3

2.1. Customer Service	3

2.1.1.Access to information / facilities	3

2.1.2. Register of Electors and Local Election Voting Facilities	3

2.2. Human Resource Management	3

2.3. Web Accessibility	3

3.	HOUSING SERVICES	3

3.1. Disabled Persons Grants	3

3.2 Essential Repair Grant	3

3.3. Homeless and Voluntary Housing Programme	3

3.4. General Improvement Projects	3

3.5. Traveller Accommodation	3

3.6. General Information regarding Housing Welfare issues	3

3.7. Proposed Actions to implement the Disability Act (2005)	3

3.8. Monitoring of Progress on Actions in Housing Matrix	3

3.9. Housing Department Action Matrix	3

4. ROADS AND THE PUBLIC REALM	3

4.1. Introduction	3

4.2. Roads Action Matrix	3

5. PARKS AND LANDSCAPE SERVICES	3

5.1. Introduction	3

5.2.About the Parks Action Matrices	3

5.3. Parks – Esker District	3

5.4. Parks Tymon District	3

5.5 Parks Corkagh District	3

6. CEMETERIES	3

6.1. Introduction	3

6.2. Saggart Cemetery	3

6.3.  Bohernabreena Cemetery	3

6.4.  Esker Cemetery	3

6.5. Newcastle Cemetery	3

7.  LIBRARY SERVICES	3

7.1.Introduction	3

7.2 Physical Access	3

7.3. Library Services	3

7.4 Access Matrix	3

8.   COMMUNITY SERVICES	3

8.1. Introduction	3

8.2. Action Matrix 2008/2009	3

9.	REPORT SUMMARY	3

- Foreword by the Mayor of South Dublin County

As Mayor of South Dublin County, I very much welcome this Disability Act Implementation Plan 2008-2010 which outlines South Dublin County Council’s commitments over this period to improving access and service provision to disabled people in our county. This includes better access to information and services, Council buildings and the public realm.

The Implementation Plan is an ambitious one and will be partly resourced by funding from the National Disability Strategy and complemented by ongoing resources from South Dublin County Council from both capital and revenue sources.

Significant progress has already been achieved over the past years in a wide variety of areas including staff training, provision of assistive technologies, provision of automatic access doors to public offices, redesign of public counters, adaptive works to council houses, footpath and traffic signal improvements, accessible signage for people with visual impairments, works to cemeteries, parks and community centres etc.

The list is impressive and a testament to the commitment of this organisation to improving the quality of life of disabled people. This has been acknowledged by the achievement of several O2 Ability Awards in recent years. This work continues and will gain further momentum through the actions contained in this Plan.

The overriding aim is to make South Dublin County a more accessible place that better meets the needs of disabled people in terms of the services provided by the local authority, and the built environment that we all interact with and live in.

I wish to thank the staff who contributed to the development of the Plan and to the members of the public and groups within our county who participated in the public consultation process which helped to ensure that the Plan reflects the needs of disabled people in South Dublin County.

Councillor Marie Corr

Mayor, South Dublin County.

- Introduction from the County Manager

It is my pleasure to introduce the South Dublin County Council Disability Act Implementation Plan which sets out how South Dublin County Council shall implement the provisions of the Disability Act (2005) by creating an enabling environment underpinned by the principle of universal access, to ensure that disabled people can participate fully in our society.

According to the census 2006, 9.3% of the population of Ireland are disabled people. 8.6% of the population of South Dublin County are disabled people, and approximately 75% of disabled people in the County are aged 45 years or more.

These figures have implications for all aspects of the services and functions for which the Council is responsible, including providing Social Housing and managing estates, the ongoing development and maintenance of a quality roads infrastructure, developing accessible public parks and environmental services and all other aspects of planning and managing a vibrant, living and sustainable County.

It is the policy of the Council to promote the inclusion of disabled people in the County through the implementation of the Barcelona Declaration (1995) and a considerable programme of access works has already been completed, both to ensure compliance with the Barcelona Declaration and also more recently through the implementation of the National Disability Strategy. In addition the Council is dedicated to being an equal opportunities employer and promotes equality in all aspects of its activities, and is proud to have received many awards relating to our equality achievements.

This plan is a very living, active document and many of the actions listed were completed, or commenced during the draft period.  We look forward to continued work, in co-operation with our customers and the many agencies working in the County, to achieve our vision of achieving equality of opportunity and equality of outcome for disabled people in South Dublin County and removing the barriers that create disability.

Joe Horan

County Manager

- 1. INTRODUCTION

  - Introduction

Welcome to the South Dublin County Council Disability Act Implementation Plan 2008 – 2010.

South Dublin is a County extensive in area and rich in diversity.  With a population of approximately 250,000 and increasing, the Council prides itself on striving to improve the quality of life for all those who live, work, do business or have reason to visit or travel through the county.

The Disability Act (2005) is a positive action measure that gives a statutory (legal) basis for making public services accessible.  It places specific obligations on local government to ensure universal access to public spaces, buildings and services (including information provision) owned and operated by local authorities nationally.  It also requires that local authorities ensure the integration of previously separately delivered services to disabled people into mainstream services where this is practical and appropriate.

This document is the Council’s plan to implement the provisions of the Disability Act that apply to Local Authorities, in South Dublin County.

- 1.2. Vision, Strategy and Aim

Vision:

Provide disabled people with equality of opportunity to access and participate in the social, economic, environmental and cultural life of South Dublin County.

Strategy:

To develop a Plan that is proactive, and improves equality of opportunity and equality of outcome for disabled people who access the services and facilities of South Dublin County Council.

Specific Aims:

- To uphold any and all existing disability related commitments and legislative/policy responsibilities and articulate the principle of equality of opportunity for disabled people within the processes and services of South Dublin County Council.

- 1.3. Disabled People in South Dublin County

According to Census 2006, 4329,848 (9.3%) of the population of Ireland is disabled.

The population of South Dublin County is 246,935, and of this total 21,209 (8.6%) are disabled people.  The age profile of disabled people in the county is as follows:

| Age Groups | Total persons | Total disabled persons | Percentage of disabled persons |
| --- | --- | --- | --- |
| 0-14 years | 53,580 | 2,158 | 4 |
| 15-24 years | 40,387 | 1,938 | 4.8 |
| 25-44 years | 86,559 | 5,121 | 5.9 |
| 45-64 years | 53,435 | 7,103 | 13.3 |
| 65-74 years | 11,401 | 2,398 | 21 |
| 75 years and over | 6,460 | 2,691 | 41.7 |

Larger numbers of disabled people are in the older age groups, approximately 76% of disabled people in the County are aged 45 years or more.  These figures have implications for the Council, including in its role as a housing authority when designing, constructing and managing social and affordable housing schemes.

For example, the South Dublin County Development Plan 2004 – 2010 aims to bring about a high quality built environment through good design.  The Plan commits to ensuring that relevant development proposals incorporate access and facilities for disabled people.  Some examples include level access to buildings, lifetime adaptable housing, appropriate parking spaces and dished kerbs.

The types of impairment experienced by the 21,209 people are given in the following table – definitions are those used in Census 2006.

| Type of impairment | No. of impairments (% of population of South Dublin County) |
| --- | --- |
| Blindness, deafness or a severe vision or hearing impairment | 3755 (4.89 %) |
| A condition that substantially limits one or more basic physical activities | 8225 (4.64 %) |
| Difficulty in learning, remembering or concentrating | 6206 (5.49 %) |
| Difficulty in dressing, bathing or getting around inside the home | 3972 (4.5 %) |
| Difficulty in going outside the home alone | 5280 (4.51 %) |
| Difficulty in working or attending school/college | 7141 (50.7 %) |
| Learning or intellectual disability | 4307 (6.08%) |
| Psychological or emotional condition | 3675 ( 5.66%) |
| Difficulty in participating in other activities | 6674 (4.91%) |
| Other, including chronic illness | 7693 (5.72%) |
| Total Impairments | 56,928 .(5.08%) |

It should be noted that this table sums to 56,928 because some of the 21,209 disabled people have more than one of the impairments listed above.

1.4. Section Summary

Section one has set out the vision, mission and aim of this Disability Act Implementation Plan. This introduction section has also provided an overview of the percentage of the population in the County who are registered as disabled people, and gives a breakdown of the types of impairments that must be considered to ensure that the diverse access needs of the customers of the Council are recognized and that services are provided accordingly

To provide background, the next two sections introduce the national and council level strategies, actions and approaches that have enabled advancements in relation to inclusion of disabled people in recent years.

2.  POLICY FRAMEWORK – NATIONAL LEVEL

The Government launched the National Disability Strategy on 21st September 2004 to underpin the participation of disabled people in Irish society.  The strategy builds on existing policy and legislation, including the policy of mainstreaming public services for disabled people.

The Key elements of the strategy are:

- The Disability Act 2005.

- The Citizen’s Information Act 2007, which equips the Citizens’ Information Board (formerly Comhairle) to provide a personal advocacy service for disabled people.

- Sectoral Plans prepared by six Government Departments, including the Department of the Environment, Heritage and Local Government (DEHLG).

- A multi-annual investment programme worth €900 million targeted at high-priority disability support services to run until 2009.

- 2.1.The Disability Act (2005)

The Disability Act, in addition to overall actions to be taken by public bodies, includes in Part 3, Section 36(l) obligations that are specific to the DEHLG.  The DEHLG is asked to prepare a sectoral plan which addresses the actions set out below:

- Measures to be taken to ensure compliance with Part M of the Building Regulations 1997 (S.I. 497 of 1997).

- Measures to be taken to facilitate access by persons with disabilities to public roads and other public places and to other services provided by the Minister, local authorities and other public bodies in relation to which he or she performs functions and the time proposed within which such measures are to be taken.

- Arrangements proposed to be put in place by the Minister and the Minister for Transport to facilitate access to the vehicles providing the passenger transport services by such persons from a public road.

- Housing and accommodation for persons with disabilities.

- Proposed arrangements for co-operation by housing authorities with the Executive in relation to the development and co-ordination of the services provided by housing authorities for persons with disabilities

- And any other matters which the Minister considers appropriate.

Public places include:

- Street furniture, pavements, pedestrian zones,

- Signage,

- Public parks and open spaces owned or maintained by a local authority

- Harbours, bus and light rail stops for which a local authority is responsible.

Disability Act 2005

Circumstances that may qualify for time bound exceptions are listed in section 25, 26, & 27 of the Act, and include buildings being used temporarily for a limited period, and buildings where cost would not be justified based on the use to which the building is put, or would cause unreasonable delay in making the goods or services available to other persons.

- 2.2.DEHLG Sectoral Plan

The Sectoral Plan of the Department of the Environment, Heritage and Local Government (DEHLG) 2006 sets out national objectives and guidelines for access to local authority services and the built facilities as quoted below:

- To promote universal access to public spaces, buildings and services owned and operated by local authorities and those owned and operated by the Department and bodies under the aegis of the Department.

- To promote universal access to new developments and heritage sites.

- To ensure access to information on local authority services for persons with disabilities and similar access to information on services provided by the Department and bodies under its aegis.

- To update standards set out in Part M (Access for Disabled people) of the national Building Regulations; and provide for more effective enforcement of these standards.

- To promote and ensure participation by persons with disabilities in decision-making.

- To ensure a high level of awareness among all staff in regard to the requirements of persons with disabilities.

- To encourage and facilitate access to appropriate housing and accommodation for persons with disabilities.

8) To improve access of persons with disabilities to streets, pavements, footpaths, and street crossings, and access from public roads to passenger transport vehicles, through promoting an accessible barrier free pedestrian environment.

9) To ensure co-operation and co-ordination in relation to cross cutting issues under the National Disability Strategy between the Department, bodies under the aegis and local authorities, with other Government Departments and public bodies.

10) To promote co-ordination between service providers at local level through the County and City Development Boards.

- 2.3. NDA Guidelines

In addition to legislative obligations, the National Disability Authority provides guidelines for organisations to improve access in three critical areas common to all organisations:

- Access to Quality Customer Services;

- Access to the Built Environment;

- Access to services delivered via Information and Communication Technology.

South Dublin County Council has considered the legislative requirements within the Act and the DEHLG Sectoral Plan commitments and also the NDA guidelines during the development of this action plan. The Council has a significant track record in relation to inclusive planning, both at corporate level and County planning levels. An overview of the existing policies and planned ongoing development of strategies to ensure inclusive mainstreamed services is presented in the next section.

# 3. POLICY FRAMEWORK AND BACKGROUND – COUNCIL LEVEL

## 3.1 The Council as Employer

Part 5 of the Disability Act 2005 places a number of obligations on Public Body employers to take all reasonable measures to promote and support the employment of disabled people and to ensure that the organisation reaches any compliance targets set by Government. The Act also requires public bodies to report on an annual basis in relation to the achievement of compliance targets and initiatives taken to promote employment. Local authorities who have not attained a minimum of 3% for the employment of disabled people are required to immediately put in place measures to ensure this target is reached. South Dublin County Council has consistently exceeded this compliance target (3.51% as at 31/12/2007)

South Dublin County Council is dedicated to being an equal opportunities employer and promotes equality in all aspects of its activities.  The Council strives to ensure that equality is a core policy driver of the organisation and has been active in introducing equality and family friendly schemes. South Dublin County Council is particularly committed to a policy of equal opportunity regarding access to employment. Our Equality Policy will ensure that no individual receives less favourable treatment on the nine grounds of gender, marital status, family status, sexual orientation, religion, disability, age, race and membership of the Travelling Community as defined in the Employment Equality Act 1998.

South Dublin County Council is committed to the implementation of a positive action programme to complement equality legislation and to realise the equality policy.  The policy is widely promoted through all available avenues e.g. staff handbook, HR website, and information sessions.  The issue of equality is addressed at induction stage.

South Dublin County Council is committed to meeting the access requirements of disabled staff through the use of assistive technology, sign language interpreters, induction loop systems, the use of Braille machines and also by paying vigilant attention to ensuring access for all staff to all areas of Council buildings.

The Council‘s Human Resources Department continues to promote awareness of equality issues by facilitating information sessions on Equality and Diversity, ensuring that information on the issue is provided to new staff as part of their induction and ensuring that a module on Equality and Diversity has also been included in its supervisory management training courses.

An extensive schedule of Disability Equality Training has been developed for Council staff as part of the 2007 core training programme. This is a collaborative initiative between the Training & Development Unit and the Disability Liaison / Access Office, funded through the National Disability Strategy and is an important part of ensuring that the Council’s commitment to implementing the Disability Act 2005 is understood and realised throughout the organisation. The Council is committed to continuing this training over the period of this plan and periodically on an ongoing basis.

Staff Recruitment:  South Dublin County Council is fully committed to encouraging and supporting disabled people to seek employment and to progress within the organisation.  Disabled people have an equal opportuinity to be selected, trained and promoted within the Council.

If an existing employee becomes disabled, the County Council is fully committed to making every reasonable effort to enable the employee to remain at work within the County Council.

It is South Dublin County Council’s policy to support a positive attitude in the workplace towards disability and to provide disability equality training.

HR Policy and Commitments:  It is the current and future policy of the H.R. Department to:

- Ensure that equality is a core policy driver of the organisation

- Meet / exceed the 3% employment target for disabled people (3.27.51% at 31/12/2007)

- Promote awareness of equality at inductions, with interview boards, through website, and by scheduling equality awareness sessions and formal training.

- Monitor the application of Equality and related policies in conjunction with the Equality Officer and Equality Action Team

- Ensure equal access to employment, promotion, training and other HR services

- Work with relevant agencies, in conjunction with the Disability Liaison/Access Officer, to promote and encourage employment opportunities for disabled people.

- Meet the specific access requirements of each disabled staff member.

- 3.2 The Council as Service Provider

In 2002, South Dublin County Council established a Social Inclusion Unit, housed within the Community Services Department, dedicated to the goal of eliminating disadvantage and improving the quality of life for all residents in the County particularly for disadvantaged communities, disabled people and other relevant target groups. The unit aims to advance its objectives through collaborative work with the statutory and voluntary agencies, community groups and the South Dublin County Development Board. Within the Council there is a cross departmental working group for Social Inclusion Issues and all departments are represented on this group.

There is a Social Inclusion Policy section in the staff handbook that includes a section on inclusive event management and inclusive information provision.

South Dublin County Council is committed to ensuring equality of opportunity and outcome for all disabled people accessing Council buildings and services.  In 2006 the Council appointed a full time, dedicated Disability Liaison / Access Officer to:

- ensure the implementation of the Disability Act 2005 across the organisation

- co-ordinate actions under the National Disability Strategy

- Assist and advise disabled staff and job applicants/work experience participants

The Barcelona Declaration was signed by all EU member states in 1995.  It is a gateway that facilitates local authorities in tackling one of the pillars of the Equality Agenda – Disability. South Dublin County Council adopted the Declaration in 2002 and has been actively implementing the Declaration since through various actions.

Council staff provide key support to and engage fully on the County Development Board’s Social Inclusion Measures Group (SIM) and the Social Inclusion Network.

The South Dublin County Social Inclusion Network was established in June 2003.  It provides a forum for social inclusion officers and equality officers from member agencies of the County Development Board to collaborate, network and provide peer support on social inclusion, anti-poverty and equality issues.

The Networks role is to:

- Ensure an understanding of the concept and practice of social inclusion by member agencies of the South Dublin County Development Board.

- Actively participate in the implementation of actions contained in the cross-cutting themes of the South Dublin County Development Board 10 Year Strategy: ‘A Place for People’.

The SIM/RAPID (Revitalising Areas through Planning Investment and Development) Monitoring Group is a sub structure of the County Development Board.  The SIM has several specific purposes as follows:

- To Co-Ordinate delivery of social inclusion measures at local level

- To feed into the social inclusion aspects of the County Development Board Strategy

- To Monitor the RAPID. Programme

- Endorsement of Local and Community development agency work plans

- To promote targeted approaches to address poverty and social inclusion.

- To enable cohesive service delivery.

The Social Inclusion Network (SIN) reports to the SIM Group at its quarterly meetings, updating the SIM group on the work of the Social Inclusion Network.

Customer Services

The provision of quality Customer Service and Care is a priority for the Council and we have adopted a detailed Customer Service Action Plan.  We recognise that our customers are central to our existence as an organisation and that an ethos of customer care will drive all our actions.  The Customer Service Action Plan incorporates a Charter of Rights and Entitlements for both customers and staff as well as detailing the levels of service we are committed to providing. The Council provides a vast range of services which are listed and available under the A-Z of Services and Frequently Asked Questions on the Council’s website.

South Dublin County Council is fully committed to both the principles of social inclusion, and meeting our responsibilities under the Barcelona Declaration. Our priority is to make it easy, convenient and pleasant for customers to do business and interact with us.  This means making it easy to find us, to find information, to contact the right person, get the appropriate service and receive sufficient feedback and support.  In order to achieve these standards we ensure that customers can access our services in a manner that suits their needs, accommodating any specific requirements including language, or accessibility needs.  Customer service desks have induction loop systems, counters at suitable height for wheelchair users, prominent clear signage and staff trained to be aware of, and skilled to accommodate, the varying needs of disabled customers.

In addition Council Services can be accessed online 24 hours a day, every day of the week at www.southdublin.ie. The website has been designed to be simple to use and we are constantly improving the quality of information and seeking to enhance the level of business transactions that customers can carry out online.  Services that customers access online include:

- Purchase of bin tags online

- Look up information on services provided

- View live feed from traffic cameras

- Access live journey times on main traffic routes

- Look up Council job vacancies

- Download application forms

- Review planning permission application files and decisions

- Make an enquiry / seek Customer care / report a fault

- View agenda and minutes of Council meetings

- Get contact details for Councilors and Departments of the Council

- Review roles / responsibilities of Council Departments

- Access details of local businesses, community and sporting / recreational facilities

- View Council Public Notices, Tenders and Press Releases

- Review policy documents

All of the above are simple to access and easy for to use. The facility to do business at any time day or night, to suit the customer is a major benefit, and often of particular benefit to disabled customers.

Information requests can also be forwarded to Customer Services by SMS Text Message to the following number: 086/1731707, or by emailing info@sdublincoco.ie.

All public information documents, including this document, are available in alternative formats including Braille, and on disk.

## 3.3. Equality Promotion Achievements

Since the establishment of South Dublin County Council in 1995, the Council has demonstrated a commitment to inclusion and this has been underpinned with specific actionable commitments in the County Strategy, the Corporate Plan, the Customer Care Plan and the Customer Charter.  Success in relation to following through on commitments is evidenced by several awards and positive external evaluations and assessments of the Council in relation to achievements as follows:

South Dublin County Council has been awarded the overall prize at the Irish eGovernment

Awards 2007 for its Connect Project.

Our innovative Connect project is an ambitious project which will open up the potential of technology to local communities, integrating eInclusion with the eGovernment and eCitizen agendas to ensure a fully inclusive and meaningful interaction on quality of life issues for all. There are four strands to the Connect Project:

  - Connect Me, access to local information using an online interactive mapping system,

  - Connect Web, supporting all community groups to create their own internet content that will facilitate improved information management and develop new methods of collective engagement;

  - Connect School in St Aidan’s Community School, Brookfield, developing student centred technology through an innovative learning culture in order to improve school attendance, participation in class and educational outcomes for the students;

  - Connect Centres, creating a network of Community technology Centres where local people can access and learn about technology in their own communities transforming the digital divide into digital inclusion.

To maximize the potential of the Connect project to improve access for disabled customers, the Council intends to progress the following actions:

- Providing details of the physical accessibility of each business and service (as suggested by a customer during a recent customer focused review of Connect).

- Ongoing work with a Disability group that is creating a website through Connect Web to exploring the potential of Connect to support the communication technology needs of a possible disability network for the county.

- Progressing Connect School to a standard where all technologies and systems developed within the school are fully accessible as well as developing the use of assistive technologies to ensure students of all abilities are full project participants.

- Maximising the potential of Connect Centres project to make technology accessible to people in their local community where they can use and learn about new digital technologies in a supportive, inclusive and comfortable environment.

Best Companies Staff Survey

- 92 % agree – ‘People here are treated fairly regardless of Disability’

Excellence Through People ETP Award 2005/6/7

- Achieving the ETP standard ‘demonstrate a commitment to non-discrimination, accommodating diversity and promoting equality’.

O2 Ability Awards 2005 /2006

- Award winner Recruitment & Selection 2005

- Category Winners 2006

O2 Ability Awards 2007

- Nominated Best Overall in Public Sector

- Category Winners for Leadership, Recruitment & Selection, Environmental Accessibility, Customer Service, Learning Development & Progression

The Council recognises the contribution that disabled people make to business and is committed to their employment. Our aim is to achieve and sustain best practice in this area.

- 3.4. Future Equality Commitments

The Council has addressed specific inclusion requirements to ensure access for disabled people to Council facilities and services, including the installation of a Minicom and Braille machine in County Hall, and a Braille machine in the Clondalkin Civic Offices. Countywide improvements are evident with the near completion of works programmes to ensure path dishing and accessible parking provision, the Architectural Services Department has committed to the principles of lifetime design and the Council has an excellent track record in relation to administering the Disabled Persons Grant for house adaptations.  The Council commits to continued and sustained progress to ensure that services and facilities are universally accessible. Specific commitments going forward include the following:

- Inclusive information provision: In our Corporate Plan 2004 – 2009, the Council is committed to working towards a policy of inclusive information provision, including the use of plain language, across all Council functions and in all key Council documentation and forms e.g. they will be made available in alternative formats, such as large print, as required.  The Council has also made progress through measures such as the accessible Customer Care Centre, Assistive Technology in libraries and the Web Content Accessibility Initiative.  Minicom is available at County Hall and Braille machines are in use in both County Hall and the Clondalkin Civic Offices.

- Customer Consultation: To continue to consult with disabled customers. This action will be implemented through the Council Customer Care programme, which includes consultation and feedback through consumer panels.  In addition, arising from the Disability Act Consultation Process, a number of disabled people have agreed to come together with key staff for ongoing access related consultative focus group discussions, which will be conducted in co-operation with the County Development Board.

- Accessibility Proof at Procurement Stage:  The Corporate Procurement Plan is currently under review in order to incorporate accessibility objectives into procurement process so that ‘design for all users’ is a valid criteria to be taken into account unless it would not be practicable or justifiable on cost grounds or would result in an unreasonable delay.

- An Accessible Complaints System: Maintain an accessible complaints system for all customers, and ensure that responsibility is allocated for dealing with enquiries relating to the implementation of the Disability Act.

- Provide Access Guides to Facilities and Services: Ensure Access Guides are developed for all Council Facilities.  This process has commenced and guides are in place for County Hall and the Clondalkin Civic Centre.

- An Accessible Website:  Monitor the accessibility of the Council website and implement an ongoing programme of development and staff training to ensure that all future information prepared for the website is disability proofed. To progress this commitment, The Information Technology Department have committed to reviewing all aspects of the Council website during 2008, in order to meet level AA compliance, and to provide facilities for the conversion of PDF documents to HTML format. The IT Department shall continue to audit the Council’s website and links for adherence to accessibility standards.

- Accessible Voting Facilities:  The Council are undertaking a review of all access issues relating to voting facilities in the county and actions to remove or address all voting access barriers are scheduled for completion in 2009.

- Monitor and Evaluate Progress: Monitoring and evaluation of the implementation of this plan will be carried out by the Disability Act Implementation Team (DAIT) and a report on progress will be made to the elected Council,  Management Team and the public by inclusion in the Council’s Annual Report

3.5. Section Summary

This section has set out the policy and corporate framework that underpins the commitments in this plan. Equality principles underpin the corporate approach both as an employer and as a public service provider, and this is evidenced by a significant track record in achieving excellence through staff.   The Council is firmly committed to providing disabled people with the equality of opportunity to access and participate in the social, economic, environmental and cultural life of South Dublin County.

## 4.THE BUILT ENVIRONMENT

- 4.1. Introduction

An accessible built and external environment is a core element of an equal society, ensuring that all members of our community can exercise their equal right to autonomy, inclusion and participation.

The Building Control Act of 1990 provides the framework on which the modern Irish building control system is based.  This act regulated standards in building construction and design.

Part M of the Building Control Regulations 2000, ‘Access for Disabled People’, sets out the appropriate codes and standards to be observed in the design and construction of buildings, see below.

South Dublin County Council is required by law to ensure that the services we provide to the general public are accessible to disabled people as far as practicable and appropriate.  The services concerned are those in Section 2 of the Disability Act.  Disabled people, by law, should now be able to avail of a service provided by a public body at the same point of access or location, at the same time as everyone else, as far as is practical and appropriate.

The Council recognises that the ‘Design for All’ approach is an important tool for ensuring accessibility for people with physical impairments and older people with mobility impairments, and that the resultant inclusion of previously marginalised members of our community, and the improvements generally to our environment by thinking about accessibility during design has benefits for everyone.

The Disability Act requires the local authority to take reasonable steps to ensure an accessible approach to its built environment, including, where provided, car parking facilities.  The fundamental accessibility criteria include providing means for achieving equal spatial orientation to all users by the means of adequate spatial layout of the outdoor space and the spaces inside buildings, including the use of accessible signage, adequate way-finding and information systems

South Dublin County Council has a designated Disability Liaison/Access Officer who is responsible for providing, coordination or arranging assistance to disabled persons when they are accessing services provided by the Council.

This section introduces the Council’s specific commitments to equality of access in the built environment, and the factors and approaches taken by the Council to promote social inclusion through accessible community and recreational facilities, and by providing guidance and control systems for building and planning in the County.

- 4.2  South Dublin’s County Development Plan, 2004-2010

One of the principal aims of South Dublin’s County Development Plan, 2004-2010, is to promote social inclusion by means of ensuring the retention and provision of accessible community and recreational facilities including local/neighbourhood/town centres, parks and open spaces’ and by ensuring that these facilities are adequate to meet the needs of the community they serve.

It is the policy of the Council to promote the inclusion of disabled people in South Dublin County through the implementation of the Barcelona Declaration (1995) and to continue the provision and development of facilities which maximise the independent mobility of all disabled people.  South Dublin County Council signed the Declaration in June 2002 (Policy SCR 3).

It is the policy of the Council to cater for all age-groups and abilities in the population of the County through the facilitation of both active and passive recreational activities and also to support and facilitate the development of indoor and outdoor recreational facilities to cater for all age groups on suitable sites, and to ensure that these facilities are accessible to disabled people (Policies SCR 19 and 20).

The Development Plan states that access requirements for disabled people must be incorporated into the design of shops and all other buildings, public spaces, facilities and services likely to be used by the general public.  Such requirements include ensuring level/ramped access to buildings, the dishing of footpaths, the provision of accessible parking for disabled drivers/passengers and toilet facilities, provision of appropriate hard surfaces, audible signals and tactile paving at pedestrian crossings etc.

It is indicated in the Development Plan that the criteria necessary in designing for disabled people is set out in Part M (Access for Disabled people) of the Building Regulations 2000, and the guidelines “Buildings for Everyone”, published by the National Disability Authority, August 2002.

## 4.3. Development Management Guidelines

In the application of the Department of the Environment, Heritage and Local Government’s “Development Management Guidelines”, South Dublin County Council advises prospective applicants of the necessity of ensuring that the design implications of accessibility for all are addressed in the approach routes to buildings including the location of car-parking, the provision of accessible car-parking and other related issues.  While those aspects dealt with under the Part M of the Building Control Act are not permitted to be included in the planning permission conditions, applicants can be reminded in the permission documentation of their responsibility in relation to the regulations.

- 4.4. Architectural Services Department Commitment to Universal Design

As a matter of course all buildings designed under the auspices of the Architectural Services Department comply with PART M of the building regulations.

The Architectural Services Department works closely with the Planning, Parks and Roads Departments on Development, Area Plans, Urban Design and site specific developments where the principles of easy accessibility for all are clearly set out as an overall aspiration of a successful public realm. These principles inform all elements of the design from general mobility in a neighbourhood right down to specific needs within a dwelling.

The Department has long been an advocate of the principles of ‘Lifetime Homes’ and ‘Universal Access’. These principles are incorporated informally into the guidelines for our design teams (both in-house and external consultants).

We are currently updating our outline requirements for housing design for social and affordable housing provision in the county. As part of this update it is intended to detail the ‘Universal Access’ and ‘Lifetime Homes’ principles in our new document as design requirements rather than aspirations. This will impact positively, not only on housing provided directly by the Council, but will also be required of Developers providing housing to the Council under PART V of the Planning & Development Act.

‘Universal Access’ principles have already been embraced in the design of the group-houses and day-houses constructed for the Traveller Accommodation programme. These dwellings are designed to include full accessibility.

Within the Housing Programme the needs of persons with specific impairments is addressed on an individual basis. The project architect works in association with the Occupational Therapist and prospective tenant to identify the dwelling in the proposed development most suitable for adaptation to the specific requirement.

The Architectural Services Department also runs a Small Works Programme which responds to requests for alterations/extensions to existing dwellings for persons with a specific impairment/access need. In this programme the project architect works closely with the Occupational Therapist and the resident to provide the most appropriate upgrade/extension to the dwelling.

The quality of Universal Accessibility provision is an important element of our residential, community, civic building and public realm design.

- 4.5. Building Control

The Building Control regulations set out basic requirements and refer to appropriate codes and standards to be observed in the design and construction of buildings including Part M ‘Access for Disabled people’.  Technical Guidance Document M sets out guidance on the minimum level of provision to meet the following:

- Disabled people can safely and independently approach and gain access to the building or dwelling.

- Elements of the building do not constitute an undue hazard for disabled people, including those who have a visual impairment.

The underlying philosophy is that people involved in the design and construction of buildings should have regard to the provision of universal access for all, including disabled people.

The primary responsibility for compliance with the Building Regulations rests with designers, builders and building owners.  However the Building Control Section of the Council has powers to inspect design documents and buildings as well as powers of enforcement and prosecution where breaches of the regulations occur.

  - Planning Information

For ease of access to planning information, full details of all Planning Applications can be viewed on line, including weekly updates regarding applications received and decisions made and searchable maps containing aerial photos of the County.  The website also enables access to an online database which contains details of applications since 1991 and full scanned planning files for applications since January 2000.  This is a useful facility for those considering adaptations to their own house. By making this information accessible on our website, the need to travel to Council offices to access it is removed, which is beneficial to citizens with mobility difficulties.

  - Section Summary

The Council aims to facilitate and promote the highest quality planning and sustainable development of this unique County, with maximum participation of the citizens in its physical, economic, social and cultural development.  The Council does this through the application of inclusive policies in the County Development Plan, the enforcement of the Building Regulations where required and the provision of relevant information on-line.

- DEVELOPMENT OF THE DISABILITY ACT IMPLEMENTATION PLAN

- 5.1. Approach

The approach to development of this plan commenced with the establishment of a Disability Act Implementation Team, to oversee the consultation and methodology engaged to develop the plan and to monitor its implementation.  The team is comprised of representatives from all departments and, along with Senior Management, the team has engaged in training sessions on Disability Equality and on the National Disability Strategy.

- 5.2. Access Auditing

The Council engaged Capita Symonds to carry out a series of accessibility audits on Public Parks and Cemeteries, Configure Ltd to conduct access audits of Town Centres and Community Facilities and TMS Consultancy to conduct access audits of Neighbourhood Centres, during 2007. These audits identified barriers that disabled people may encounter when engaging with the community and public services and facilities.  The audits have contributed to the development of the access plans prepared by each of the Council departments, culminating in one overall Disability Act Implementation programme aimed towards identifying, removing and preventing barriers to participation by disabled people. More specific detail of each of the individual audits is available from the Council’s Disability Liaison/Access Officer in the Corporate Services Department.

- 5.3. Consultation Process

A comprehensive consultation process was conducted by the Council during 2007, giving all stakeholders an opportunity to contribute to the development of this plan. The consultation process was launched with an advertisement in the Echo Newspaper, published on 19th June 2007.

Consultation meetings were then held with:

- South Dublin County Councillors on 21st June 2007

- Disabled People, Representatives from Disability Organisations and Advocates on 27th June 2007.

- South Dublin County Comhairle na nÓg on 26th July 2007

Oral, written and audio submissions were invited from members of the public during the same period, with a deadline set for 5th July 2007.  To encourage submissions, a questionnaire was posted on the South Dublin County Council website and also posted to Disability Organisations through the membership list of Disability Federation Ireland.  Participants from the Barcelona Declaration Consultation conducted by the Council in 2005 were also notified of the process and methods for making submissions.  Young People were consulted by means of a questionnaire circulated at a Training day for Comhairle na nÓg on 26th July 2007.  Staff members of the Council were also consulted by Questionnaire in August 2007.

Feedback from the consultation process was collated into one report, which was then circulated to all departments within the Council to ensure that issues and suggestions arising from consultation informed the development of this plan.  In addition the report will continue to be available for ongoing reference and crosschecking with regard to the improvements during the implementation phase. The Council commits to ongoing incremental consultations to ensure access issues are addressed promptly.

- 5.4. Development of Action Matrices:

The Disability Act Implementation Team, under the direction of Selina Bonnie, Disability Liaison/Access Officer, proactively initiated and co-ordinated departmental input to the action matrices set out in Part 2 of this Plan, ensuring that all relevant commitments contained in the overall strategic management and policy documents are adhered to and built into or interpreted and applied to the action plans.

In addition, the external auditors were instructed to prioritise works into three categories (four in the case of Parks) and departments have respected this advice and have scheduled works accordingly. Further information about these categories and also relating to other considerations that influence Departmental approaches to prioritisation is set out in Part Two.

- 6.  SUMMARY OF PART ONE

Part One has introduced the Vision, Strategy and Aims of this plan, and has provided information on disabled people in South Dublin County and the National Disability Strategy.  Part One, Section two and three, set out the policy framework at National Level and also at Council Level which underpins this plan and also set out the specific corporate commitments to ensuring equality of opportunity to access and participate in the social, economic, environmental and cultural life of South Dublin County.

Part One, Section Four, set out the Council’s responsibilities and legal obligations; along with specific commitments to ensure that the approach to the built environment is underpinned with the ‘Design for All’ concept.

Part Two of this plan presents the schedule of actions to be implemented by specific departments, and arrangements for monitoring the implementation of the plan.

- PART TWO – ACTION MATRICES

# 1.INTRODUCTION

Part two presents information relating to how specific Departments within South Dublin County Council will implement the Disability Act.

South Dublin County Council has responsibility for providing many Services and Functions.  We deliver services and responses that are easy to see, some less easy to notice, and some that have an impact over a longer time span than others.  Our outputs are more often recognised in physical “things” such as new roads, refuse collection and disposal, housing developments and libraries and the diverse passive and active use of our parks. All in all the Council provides a vast number of different services.  The principal ones are

| Housing Services | All aspects of Social and Affordable Housing as well as estate management for our Housing Estates |
| --- | --- |
| Planning Services | Planning and Managing the orderly development of a vibrant, living and sustainable County. |
| Architectural Services | Building sustainable neighbourhoods and public buildings with a sense of place and accessibility for all. |
| Roads and the Public Realm | Providing and maintaining our roads infrastructure including footpaths bridges and public lighting. Achieving more efficient use of the existing road network. |
| Environmental Services | Providing and maintaining our water, drainage, solid waste management systems and burial grounds. |
| Parks and Landscape Services | Design, operation and maintenance of a range of amenities including Regional parks, neighbourhood parks, playgrounds, Grange Castle golf course, and numerous other sporting facilities for public enjoyment. |
| Community Services | Working in partnership with community, voluntary and statutory organisations to enhance the quality of life for all residents and to create stronger recognition of the role of the community sector within the Council, state organisations and the community at large. Civic Theatre, Libraries and community centres. |
| Economic Development | Acting as the catalyst for industrial and Economic development through the provision of an International Business Park, low costs enterprise units for start up business and managing the Council’s property portfolio. |
| Information Technology | Development and maintenance of the Council’s website as a quality information platform. |
| Corporate Services | Acting in a support role for the elected members, maintaining the Register of Electors and organisation of Local Elections, operating a quality customer service function, managing the Council’s public offices particularly in relation to accessibility and dealing with dissemination of information to the public and media. |
| Human Resources | Is responsible for the management of our organisations most valuable resource – its staff, adopting best practice in all areas including staff recruitment, retention, training and development, management of employee relations, staff welfare and the administration of staff benefits and entitlements. |

- 1.1. Approach, Timing and Prioritising of Actions

The approach by the Council to implementing the Disability Act is threefold.  Firstly there are initial ‘upgrade’ actions that require investment to bring public services and facilities to an acceptable level of accessibility. Secondly there are actions that have been identified that can have a real impact in terms of improving access, requiring commitment, but not necessarily financial investment, such as fostering an openness to ongoing learning and information updates in relation to access, or barriers to access, in order to achieve the highest access standards possible; this includes participating in inter-departmental and inter-agency forums, within the Council, nationally and internationally in order to identify ‘best practice’ approaches and strategies that the Council can adapt going forward. Thirdly the Council has committed to ensuring that access for disabled people is considered to be an integral part of mainstream work programmes going forward, and this should ensure that the need for ‘corrective’ measures to improve access in the future is minimised.  Therefore the matrices of actions set out here in Section Two, whilst forming a major part of the approach to implementing the plan, are also complemented by actions that do not have budgetary implications.

The action matrices set out below were informed by the countywide access audits, the public and staff consultation process, and existing programmes underway to improve access. The Access Auditors, engaged by the Council in 2007 were instructed to prioritise work into three categories as follows: ‘Priority 1’ refers to actions that must be implemented straight away to either bring up to compliance or address a safety issue.  ‘Priority 2’ are actions that should be addressed to meet best practice within two years, ‘Priority 3’  are actions that should be taken as part of scheduled future main works, repairs, maintenance or renovations and in the case of Capita Symonds (Parks Department) audits ‘Priority 4’ ongoing maintenance and management.  In the matrices presented below, those that are prioritised from the audit reports include the prioritising category as 1, 2, 3 (& 4, in the case of Parks).  Some matrices were generated by departmental work plans and informed by the public consultation process.  Prioritisation codes therefore are not necessary or applicable to all actions set out on the matrices.

The departments will endeavour to address as many of the items listed from budget over the next three years, as is possible.  The advice from the Access Auditors and also other considerations, such as the need to co-ordinate work with other departments and agencies, and to respond to the specific access needs of individuals who contact the Council, will continue to inform the order in which work is carried out by all departments.

Contact Details for all departments are available through the South Dublin County Council website, www.southdublin.ie  and questions to departments in relation to these plans and also in relation to works already completed are very welcome and shall be responded to promptly.

- 1.2. Budget and Timescales

Most actions set out in matrices below are scheduled for 2008-2010. Where budget and timescales are included, they are indicative and may vary depending on resources available and changing priorities during the life of this plan.  Budgetary estimates in some instances are taken from the Access Audit Reports and for this reason variances with actual costs may be considerable, based on the fact that estimates by the auditors could not give due consideration to issues such as economy of scale, availability of contractors, delays in the tender process, works costings arising from the tender process, availability of funds and co-ordination of the programme of works with other departments and agencies.

The Access audits carried out to inform this plan, provided the first comprehensive listings of actions required to make our county accessible.  In some cases this process has produced a range of works that are unlikely to be completed during the life of this plan, within available resources and budget. Therefore items that cannot be addressed during 2008-2010 due to budgetary constraints, or other practical considerations such as co-ordination with external agencies for major work programmes, will be carried forward and prioritised in the next planning period.

- 1.3. Monitoring Implementation

This implementation of this plan will be through the corporate Performance Management Development System (PMDS) and monitored by the Disability Act Implementation Team which has a member representing each department.  An annual report on progress will be made to the elected Council, the Management Team and the public by inclusion in the Council’s Annual Report.

- CORPORATE COMMITMENTS

- 2.1. Customer Service

In accordance with South Dublin County Council Customer Service Action Plan, we will ensure, as far as practicable, that information and communications which are provided to the public whether orally, in written form or in publications, are provided in an accessible format and in clear language that can be easily understood, by persons with hearing, visual or intellectual disabilities or impairments. In doing so, the Council will, where appropriate, ensure the availability of appropriate expertise and skills to advise it in relation to making its services and information accessible. Such expertise will be developed within the organisation, or, where appropriate, sourced externally.

The Council is committed to internally and externally audit its compliance with these exacting standards and has commenced this process. In 2007, a “Mystery Shopping” exercise carried out with the assistance of an outside consultant with expertise in this area, measured the Council’s performance against our published policy criteria. In respect of access to Council buildings and information provided by Customer Service and Library staff, the Council scored an average of 79% in relation to access by persons with physical, hearing and visual impairments.

Where disabled persons experience barriers to access, a well-publicised, accessible, transparent and simple-to-use system of dealing with complaints about the quality of service will be provided.

- 2.1.1.Access to information / facilities

Disabled persons must also be facilitated and enabled to physically access to the same extent, as far as is practicable, all public facilities and buildings. In 2006 and 2007, considerable improvements have been made in this area through the provision of automatic doors, wheelchair accessible counters and Braille signage in Council buildings. This work is continuing. Through our annual involvement in the O2 Ability Awards, stringent scrutiny of Council facilities is carried out which is invaluable in measuring progress on compliance. In all new facilities, accessibility standards are stringently observed.

- 2.1.2. Register of Electors and Local Election Voting Facilities

Electoral law provides that local authorities, in making polling schemes, shall endeavour to appoint polling places where at least one polling station is accessible to wheelchair users.

While the selection of buildings to be used as polling stations is a matter for the returning officer, the Act requires that, where practicable, such buildings are accessible to wheelchair users. The returning officer must in addition, where practicable, give public notice of all polling stations that are inaccessible to wheelchair users not later than eight days before polling day. If an elector has difficulty gaining access to their polling station, the person may apply in writing for authorisation to vote at another polling station in the same constituency that is accessible to wheelchair-users.

Once in the polling station, disabled persons or persons with a literacy difficulty may avail of companion voting or may seek the assistance of the presiding officer. Alternatively, if a person has a physical impairment or illness which prevents them from going to the polling station, they can vote by post if they apply to be included in the postal voters list which is drawn up each year as part of the register of electors.

In the compilation and review of the Register of Electors, the Council will ensure that forms and online facilities comply with relevant accessibility standards.

| Actions | Responsible Department | Timescale |
| --- | --- | --- |
| Customer Service |  |  |
| Designation of an authorised Inquiry Officer / Access Officer to respond to accessibility issues | Corporate Services | 2008 |
| Implement actions of our Customer Service Action Plan in all public offices and customer contact | All Departments | 2008 |
| Access complaints / feedback system will be established, promoted and developed | Corporate Services | 2008 & Ongoing |
| Establish a Disability Advisory Focus Group to assist in implementing and monitoring the Disability Action Plan | Corporate Services | 2008 |
| Access to information/ facilities |  |  |
| Seek to achieve national best practice standards in accessibility through the ‘02 Ability Awards’ scheme | Corporate Services | Ongoing |
| Ensure that the interiors of local authority buildings incorporate the needs of disabled users and staff. | Corporate Services & Library Service | Ongoing |
| Ensure all public buildings have adequate accessible directional and information signage | Corporate Services | Ongoing |
| Ensure accessibility requirements are catered for at public events, seminars & public consultations | All Departments | Ongoing |
| Provide sign language interpreter facilities at public conferences, if requested. | All Departments | Ongoing |
| Written information provided will be in a clear format using ‘plain language’ principles. | All Departments | Ongoing |
| Provide wheelchairs and fixed seating in principal public offices to assist visitors with mobility impairments | Corporate Services & Library Service | 2008 & Ongoing |
| Introduce fixed counter induction loop systems and Braille printers in principal public offices and libraries to assist people with hearing and visual impairments | Corporate Services & Library Service | 2008 |
| Provide means for achieving safe evacuation conditions from public buildings for those with mobility or hearing impairments | Corporate Services | Ongoing |
| Procurement |  |  |
| Corporate Procurement Plan to incorporate accessibility objectives into procurement process so that ‘design for all users’ is a valid criteria to be taken into account unless it would not be practicable or justifiable on cost grounds or would result in an unreasonable delay | Corporate Services | 2008 |
| Calls for tender using electronic means will be in compliance with Web Accessibility Initiative guidelines | Corporate Services & Information Technology Services | 2008 & Ongoing |
| Ensure relevant goods and services procured for use in local authority buildings are accessible to all unless it would not be practicable or justifiable on cost grounds or would result in an unreasonable delay | All Departments | Ongoing |
| Voting |  |  |
| Ensure, where practicable, buildings to be used as polling stations for Local Elections are accessible to wheelchair users or that alternative arrangements are published and facilitated. | Corporate Services | 2009 and ongoing |
| In Local Election polling stations, facilitate persons with a physical impairment or literacy to avail of companion voting or assistance of the presiding officer | Corporate Services | 2009 and ongoing |

- 2.2. Human Resource Management

Our Human Resource Management policies, in particular The Equal Opportunity Policy and Employment of Disable Persons Policy, procedures and practices will support and facilitate the employment of disabled persons.

| Actions | Responsible Department | Timescale |
| --- | --- | --- |
| Positive Action Measures |  |  |
| Meet / exceed 3% employment target for disabled people. | Human Resources | Ongoing |
| Pro-actively linking with other agencies such as FÁS and supported employment agencies (SEPs) to find work placements for disabled people. | Human Resources/Disability Liaison Access Office | Ongoing |
| All application forms for posts are designed to enable applicants specify any access and/or support requirements for interview. | Human Resources | In place |
| Provision of assistive technologies etc. at recruitment and selection | Human Resources | In place |
| Hosting of mock interviews for Employability and sourcing job placements for a number of its clients. | Human Resources | Ongoing |
| Seek to achieve national best practice standards in recruitment practices for disabled people through the ‘02 Ability Awards’ scheme | Human Resources | Annual Entry |
| Training |  |  |
| Ensure high level awareness among staff on disability/diversity/equality awareness | Human Resources | Ongoing |

- 2.3. Web Accessibility

Design of our websites must take into account the fact that the ability to see, hear, make inputs, read text or process information varies from user to user, across time and across situations of use.

We are committed to achieving conformance level AA with the Web Accessibility Initiative’s (WAI) Web Content Accessibility Guidelines (WCAG).

| Actions | Responsible Department | Timescale |
| --- | --- | --- |
| Ensure that all websites under the control of South Dublin County Council comply with relevant web accessibility guidelines | IT | 2008 |
| Facilities will be provided for the conversion of PDF documents to HTML formats | IT | 2008 |
| A web accessibility statement will be in place to indicate commitment to reaching and maintaining conformance to level AA with WAI WCAG 1.0 | IT | 2008 |

- HOUSING SERVICES

In managing its housing stock of over 8,500 houses, the Council provides its services within the framework of a Statement of Policy on Housing Management and Maintenance and a Strategic Plan. These documents set out comprehensive policies for meeting needs by maximising the use of all available resources and working in partnership with residents and a wide range of statutory, private sector, voluntary and community based agencies.

In the Action Plan for Social and Affordable Housing 2004-2008 entitled “A Place to Live”, The Council committed to increasing the sustainable nature of the housing stock by several means, one of which is to ensure the flexibility and adoptability of housing layouts to create a ‘lifetime dwelling’.  The plan commits to developing:

“A County which actively promotes a range of accommodation options, based on identified need, by encouraging agencies and occupiers to develop adequate and well-maintained homes”.

One of the key strategic objectives set out in the plan is to provide accommodation for target groups with specific access needs, for example, homeless, older and disabled people and also young lone parents.

Many applicants require tailored accommodation set in a family sized environment to ensure that the specific needs of an individual can be incorporated in an integrated way within the overall housing need of the family group. The Council has been particularly active in this area during the last four-year programme and each scheme, including an increasing number of infill housing schemes that has been designed or completed over this period has contained some housing designed for individuals who have specific access needs.

Listed below are details of Disabled Person’s Grant and Essential Repairs Grant Schemes which are administered by the Council’s Housing Maintenance Section. The Housing Department, in response to feedback from public consultations sessions, has revised the layout and wording of application forms, ensuring that they are plain language proofed.  Forms for the Disabled Persons Grant, Essential Repair Works and Tenancy Agreements have all been proofed and updated.

South Dublin County Council is actively participating in the development of a national housing strategy and actively engaging in inter-agency forums and research to identify good practice in other regions in order to bring back learning to the County.

- 3.1. Disabled Persons Grants

Privately owned dwellings:

The Council operates a Disabled Person’s Grant Scheme under which a grant may be paid in cases where, in the opinion of the Council, the provision of an additional room, chalet or the carrying out of other structural works are reasonably necessary for the purpose of rendering a house more suitable for the accommodation of a member of the household who is either a disabled person with a physical impairment or a person with a learning or mental health difficulty.

The grant is available in respect of dwellings in the functional area of South Dublin County Council and may represent an amount not exceeding 90% of the approved cost excluding V.A.T., subject to a maximum grant of €20,320. The house for which the grant is paid must be the normal place of residence of the disabled person.

The Council reserves the right to refuse a grant in any particular case. The grant is not available for the following works:-

(a)       Replacement of windows.

(b)       Repairs of any kind.

(c)       Provision of non-residential accommodation (e.g. garage, utility/storage room, garden wall etc.)

(d)       Works which are of general benefit to the household rather than specific benefit to the disabled

person.

Application forms are available from the Housing Department or on the Council’s website.

Local Authority Dwellings:

The scheme is also available to Local Authority Tenants. The full cost of approved works is covered for disabled tenants. The Council will arrange for the costing and carrying out of the works

The following table shows the number of disabled persons grants issued since 2004:

Table 1

| 2004 | 2005 | 2006 | 2007 | Total |
| --- | --- | --- | --- | --- |
| 190 | 197 | 229 | 424 | 1040 |

It should be noted that the above table contains figures for 2007 for both Private Disabled Persons Grants and Tenant Disabled Persons Grants

The following table shows the estimated number of disabled person’s grants that will be issued 2008 to 2010:

Table 2

| 2008 | 2009 | 2010 | Total |
| --- | --- | --- | --- |
| 357 | 447 | 559 | 1,649 |

The grants are funded as follows:

Grants for privately owned dwellings – 2/3 (D.O.E.H.L.G), 1/3 (Council).

Grants for L.A. dwellings		        - 90% (D.O.E.H.L.G), 10% (Council)

The average length of time to process applications is 6 months.

New Disability Grants

Experience implementing the Disabled Persons Grant and the introduction of new Grants in November 2007 has enabled improvements to the service and these shall be applied as soon as possible to ensure that the application process is simplified and that unnecessary delays are avoided.  Under the new schemes the Council can now provide a list of contractors to an applicant.  The Council can also advertise for expressions of interest from contractors without any requirement to ‘vet’ responses or risk of liability for the Council.  The requirements in relation to the minimum number of estimates an applicant must submit prior to grant approval has also been eased.

- 3.2 Essential Repair Grant

Privately owned dwellings

The Essential repairs grant scheme assists applicants over the age of 65 to carry out essential repairs to their properties.  The Council prioritise each application and the appropriate level of grant assistance is decided based on assets, means and income of the applicant.

The maximum grant is available €9,530

At present the Council processes applications which are restricted to the following: rewiring and roof repairs including gutters, soffit and fascia. The Council will examine and judge each application received on its merits.

The following table shows the number of essential repairs grants issued since 2004:

Table 3

| 2004 | 2005 | 2006 | 2007 | Total |
| --- | --- | --- | --- | --- |
| 57 | 85 | 116 | 157 | 415 |

The following table shows the estimated number of essential repairs grants that will be issued 2008 to 2010:

Table 4

| 2008 | 2009 | 2010 | Total |
| --- | --- | --- | --- |
| 157 | 182 | 211 | 685 |

The grants are funded as follows:

Grants for privately owned dwellings – 2/3 (D.O.E.H.L.G), 1/3 (Council).

The average length of time to process applications is 6 months.

- 3.3. Homeless and Voluntary Housing Programme

In relation to children and young people who are homeless, the Council co-operates with the Health Service Executive (the HSE, who currently have overall responsibility for the housing needs of children and young people) and participates in the South Dublin Homeless Forum, which examines young people homelessness as part of the development of a homelessness preventative strategy for the County.

Disabled People who are assessed as having a social housing need by the Council can access appropriate housing through the Voluntary Housing Programme.

Homeless strategies continue to be implemented and updated as required.

The Valhalla Sheltered Housing Project  (Part VIII rec’d July 2007, Costing Aug 2007,Design Sept 2007)

This is an integrated sheltered housing scheme primarily for disabled people, designed by the Council’s Architectural Services Department in consultation with Clanmil Housing Association.

The proposal comprises of the demolition of an existing dwelling house on the site and the construction of:

- 5 x 1 person ground floor units

- 1 office / staff room

- 4 x 2 person first floor units

- 1 x 4 person duplex on 1st & 2nd floor

The units will be of universal design, suitable for people with most physical impairments.

Other features will include:

- Landscaped gardens

- Sedum roofing

- Solar Panels

- Wheelchair accessible lift

One of the aims of this project is to enhance the quality of the built environment along Watery Lane and the location is ideally suited for fully accessible living accommodation close to the village amenities and public transport.

Information regarding allocation of adapted dwellings – rental:

The provision of specially adapted dwellings is funded 100% by capital contributions from the Department of the Environment, Heritage and Local Government.

- 30 families have been allocated specially adapted dwellings since 1st January 2004.

- 18 families are currently awaiting allocation of dwellings in approved schemes which are on site.

- 21 families are awaiting allocation of dwellings in approved schemes that are not yet on site.

- 5 families have refused offers of accommodation and their cases are presently under review by Architectural Services Department to identify alternative schemes where their housing needs can be accommodated.

- The 2007 Differential Rent Scheme on which tenants’ rents are assessed shows the Council’s commitment to keeping rents at a very affordable level and protecting our most vulnerable tenants, in particular older tenants over 65 and those dependent on social welfare.

- Information regarding specific access needs is requested from housing applicants, and this enables the housing department to identify suitable housing at concept/design stage, so that appropriate unit(s) can be planned in by the Architect in consultation with the Occupational Therapist(s)/client(s).

- Allocations staff work with a Medical Doctor from the Health Service Executive (HSE) when appropriate, in order to give medical priority to persons with specific medical needs.

- Income from the following sources is disregarded for rent purposes:

- Allowances for domiciliary care of disabled children.

- Any increase in income accruing to a member of a household as a result of the payment of a Carer’s Allowance.

- Dietary and mobility allowances paid by the Health Board.

- 3.4. General Improvement Projects

South Dublin County Council is committed to improving the quality of life of all its tenants and achieving a common quality standard across its rented Housing Stock. To achieve this goal the following programmes are being undertaken:

- Major Refurbishment Works.

- Installation of Gas Fired Central Heating Systems.

- Cavity Wall and Attic Insulation.

- Window Replacement Programme.

- Electrical Upgrade Programme.

- Mains Smoke Alarm and Heat Detector Programme.

Disabled Council tenants with physical impairment or specific medical conditions are prioritised during the various programmes.  The individuals are identified through direct tenant liaison, liaison with community groups and social workers in the area.

Once they are identified, a report is requested from the Council’s chief medical officer to establish whether they will benefit from the refurbishment of their homes. Housing Projects Section works very closely with the Maintenance Section who process the Disabled Persons Grants, to assess what particular needs are required, this is done through an extensive report from an Occupational Therapist.  In most instances, works such as specially adapted showers and double banister rails, for example, are funded through the Department of the Environment, Heritage and Local Government   with a Council contribution.  Works such as installation of central heating, double glazed windows and cavity wall insulation are funded through various capital programmes utilising the Council’s Internal Capital Receipts.

- 3.5. Traveller Accommodation

The suggestions and submissions contained in the Public Consultation Report of June 2007 would be in keeping with the policy of the current Traveller Accommodation Programme 2005-2008.

The accommodation of Travellers in the County is based on the Assessment of Need carried out every four years and this takes into account any Travellers in the community who have impairments that require tailored accommodation and this is built into the housing project for each new site. Houses or bays for families with disabled members are earmarked at planning stage. There are around ten disabled people in the Traveller Community in South Dublin County and there are a small number who have developed impairments through old age or other health problems.

Where impairment occurs at a later stage, the project architect works closely with the Occupational Therapist and the resident to provide the most appropriate alteration/extension to the existing accommodation.

In the case of caravans, we provide mobile homes or adaptations through the Disabled Persons Grant from the DOE.

At present the Traveller Unit is involved in the Inter-Agency Committee for both Tallaght and Clondalkin through which specific accommodation needs are brought to the attention of the Council.

- 3.6. General Information regarding Housing Welfare issues

The Social Workers in the Housing Welfare/ Social Work Section currently carry out the following functions in relation to working with disabled people by:

- Providing support/ advice to people who wish to apply for adapted accommodation.

- Liaising with the Health Service Executive (HSE) in relation to the housing implications of an applicants care plan.

- Liaising with hospital staff in cases where a patient requires adapted accommodation.

- Supporting/advising Council tenants who require specific adaptations to be made to their existing dwellings.

- Assisting older tenants who have an impairment to move to specific adapted accommodation.

- Preparing reports for the Dept. of Environment and Local Government in cases of people from the Traveller Community requiring specially adapted mobile homes.

- Supporting applicants who are waiting for specifically designed accommodation to be constructed.

Housing Welfare Service

Referrals to our Social Workers come from a number of different sources e.g. H.S.E, Hospital Social Workers and internal referrals from other Sections within the Housing Department.  Formal meetings do not currently take place with the H.S.E. to discuss issues in general. Interagency stakeholder conferences are convened as required to address the needs of an individual, on a case by case basis.

The Housing Welfare Service provides information to clients in relation to making application for specially adapted accommodation and ongoing support is provided if necessary. In certain cases the Housing Welfare Service will liaise with the Disability Service Manager in the H.S.E. in relation to an application for adapted accommodation and/or the support plan post the allocation of accommodation.

- 3.7. Proposed Actions to implement the Disability Act (2005)

In light of the Disability Act 2005 and the Public Consultation process in 2007, in addition to the actions set out in the matrix below, the Housing Department plan to work towards achieving the following:

- To develop a working protocol between the ‘assessment officer’ (established under the Act) and the relevant sections within the Housing Department, including the Housing Welfare/Social Work section. The purpose of this would be to ensure that the housing/ support needs that are identified by the assessment officer are addressed as quickly and efficiently as possible.

- To develop a policy in relation to working with disabled people and establish procedures in conjunction with other relevant sections within the Housing Department, Health Service Executive (HSE) and relevant voluntary agencies.

- To produce clear documentation outlining the process in relation to applying for adapted accommodation and this should include information about the support service that can be provided by the Housing Welfare/ Social Work Section.

- To strengthen the link between the Housing Welfare/ Social Work Section and the Health Service Executive (HSE) Disabilities Service/ voluntary agencies (working in the area of disability). Currently, some inter-agency meetings take place to address the housing needs of specific housing applicants. The possibility of facilitating such meetings for more housing applicants, who require adapted accommodation, shall be considered.

- In relation to disabled people who are currently forced to remain in hospital longer than necessary due to the housing adaptation process, - the possibility of providing temporary adapted accommodation shall be considered.

- 3.8. Monitoring of Progress on Actions in Housing Matrix

In the Housing Department all of the actions set out in the Matrix will be contained in individual team development plans (P.M.D.S) in the Department and reviewed/modified in conjunction with the Disability Act Implementation Team on a regular basis.

- 3.9. Housing Department Action Matrix

| Priority | Action & Sub-Tasks | Timeframe |  | Budgetary Estimate | Lead Department | Linkage with | Progress/ amendments to action. | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Start Date | Completion Date |  |  |  |  |  |
| 1. | Continue to provide assistance to the Voluntary Housing Section in the provision of suitable accommodation for disabled persons. | Ongoing | Ongoing |  | Housing (Voluntary) | The Voluntary Housing Sector. Department of the Environment Heritage and Local Government (DoEHLG). |  |  |
| 1. | Provision of 10 units of accommodation for disabled persons at Valhalla, Clondalkin. | Sept. 2008 | Oct. 2009 |  | Housing (Voluntary) | Architectural Services Dept. Clanmill Housing Association. DoEHLG. | Part 8 Approved by the Council. Approval to be sought from DEHLG |  |
| 1. | Provision of 69 units of accommodation at Springfield primarily for persons with intellectual impairment | End 2007. | ##### Mid 2010 |  | Housing (Voluntary) | Respond Housing Association. St. John of Gods. DEHLG | Scheme has been approved by DEHLG |  |

| Priority | Action & Sub-Tasks | Timeframe |  | Budgetary Estimate | Lead Department | Linkage with | Detail of progress to date / amendments to action. | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Start Date | Completion Date |  |  |  |  |  |
| 1. | Modify procedures & provide assistance to persons through the Disabled Persons Grant Scheme based on changes in 2007 | Ongoing | Ongoing |  | Housing (Maintenance) | DoEHLG |  |  |
| 1. | Estimated that number of grants to be advanced over the period of the plan will be 1,363. (including LA housing and private property) 2008: 357 2009: 447 2010: 559 | Ongoing | Ongoing |  | Housing (Maintenance) | DoEHLG Occupational Therapists. |  |  |

| Priority | Action & Sub-Tasks | Timeframe |  | Budgetary Estimate | Lead Department | Linkage with | Detail of progress to date / amendments to action. | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Start Date | Completion Date |  |  |  |  |  |
| 1. | Continue to provide adapted accommodation in Council housing schemes suitable to meet the need of disabled persons. | Ongoing | Ongoing |  | Housing (Construction) | Architectural Services Department DoEHLG Occupational Therapists. |  |  |
| 1. | Estimated that number of adapted units of accommodation to be provided over the period of the plan will be 31. |  |  |  | Housing (Construction) | Architectural Services Department DoEHLG Occupational Therapists. |  |  |
| 1. | That in the carrying of the various energy/refurbishment/upgrade programmes that priority will continue to be afforded to disabled persons. | Ongoing | Ongoing |  | Housing (Projects) | Architectural Services Department Contractors on site |  |  |

- 4. ROADS AND THE PUBLIC REALM

- 4.1. Introduction

The responsibilities of the Roads Department include the maintenance and upkeep of the existing public road network. The public road network consists of carriageways, margins, footpaths and kerbs. Other responsibilities the Department has within the Public Realm include planning, design and construction of new roads and motorways, public lighting, traffic management measures incorporating provision for traffic safety and the operation of a school warden service.

The roads department welcomes and traditionally responds promptly to requests from individuals in relation to specific access issues. The professional access audits conducted in 2007 have proved invaluable in terms of assisting the department to plan access works. The Roads, Planning and Architect Departments worked together, reviewing the access audits, in order to develop the matrix of actions for the Roads Department.  Whilst doing so, staff identified several access issues that cannot be progressed directly by the Council, and these are documented separately and shall be used to work co-operatively with the agencies involved, such as Bus Átha Cliath and public telephone service providers, modifying the Roads action plan to suit co-operative approaches and timing if required.

As the audit conducted to inform this plan is the first extensive access audit on the public realm, the list of actions to be addressed is considerable.  The budget for the Roads Department for 2008-2010 cannot currently accommodate the considerable number of actions set out below within the life of this plan, however the department will endeavour to address as many actions as is possible by working in co-operation with other departments, availing of opportunities that arise through the planning process and also by amalgamating works to improve value for money.

Actions that have not been addressed by the end of 2010 will be carried forward into the next planning period. Items arising from the audits are marked as priority 1, 2, or 3 and those marked as N/A are not yet prioritised, as they arose from recent consultation with disabled people in the County.

- 4.2. Roads Action Matrix

| Priority | Action & Sub-Tasks | Timeframe |  | Budgetary Estimate | Lead Department | Linkage with | Detail of progress to date / amendments to action. | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Start Date | Completion Date |  |  |  |  |  |
| N/A | Provision of dished kerbs on Tower Road | 3/2008 | 6/2008 | €6000 | Roads |  | Acknowledgment of a request from a wheelchair user | Detailed site survey |
| N/A | Provision of dished kerbs on Wainsfort Drive | 3/2008 | 6/2008 | € 6000 | Roads |  | Acknowledgment of a request from a wheelchair user | Detailed site survey |
| N/A | Provision of dished kerbs on Pineview Avenue | 3/2008 | 6/2008 | € 6000 | Roads |  | Acknowledgment of a request from a wheelchair user | Detailed site survey |
| N/A | Provision of dished kerbs on Avonberg Road | 3/2008 | 6/2008 | € 4000 | Roads |  | Acknowledgment of a request from a wheelchair user | Detailed site survey |
| Priority | Action & Sub-Tasks | Timeframe |  | Budgetary Estimate | Lead Department | Linkage with | Detail of progress to date / amendments to action. | Next Steps |
|  |  | Start | Completion |  |  |  |  |  |
| N/A | Footpath widening and provision of an uninterrupted route on the Old Nangor Rd, between Cherrywood Villas and The Mill Shopping Centre (Clondalkin). | TBC | TBC | TBC (excess of 50000 €) | TBC | Eventual need of land acquisition. | Acknowledgment of a request from Lucan Disability Action Group | To be included in wider schemes (new apartments developments and Metro) |
| N/A | Upgrade of 4 uncontrolled crossings in Lucan Village (Lower Lucan Road, Main Street, Lucan Road, Lucan Newland Road). | 2009 | 2009 | €10000 | Roads |  | Acknowledgment of a request from Lucan Disability Action Group. | Detailed site survey |
| Priority | Action & Sub-Tasks | Timeframe |  | Budgetary Estimate | Lead Department | Linkage with | Detail of progress to date / amendments to action. | Next Steps |
|  |  | Start | Completion |  |  |  |  |  |
| N/A | Upgrade of 2 uncontrolled crossings on the Celbridge Road / Lucan Road (Junction with N4 Leixlip Road and junction with Millstream Road). | 2009 | 2009 | €5000 | Roads |  | Acknowledgment of a request from Lucan Disability Action Group. | Detailed site survey |
| N/A | Upgrade of the footpath on Lucan Newland Road: provision of an uninterrupted route between Lucan Village and the Cemetery. | 2009 | 2009 | €15000 | Road |  | Acknowledgment of a request from Lucan Disability Action Group. | Detailed site survey |
| Priority | Action & Sub-Tasks | Timeframe |  | Budgetary Estimate | Lead Department | Linkage with | Detail of progress to date / amendments to action. | Next Steps |
|  |  | Start | Completion |  |  |  |  |  |
| N/A | Footpath repaving in Lucan Village from the Gardai Station to Primrose Lane | 2008 | 2008 | From existing Road maintenance Budget | Roads |  | Acknowledgment of a request from Lucan Disability Action Group. Site survey. | Area engineer to advise action plan. |
| N/A | Footpath widening and repaving in Lucan Village | 2009 | 2009 | €5000 | Roads |  | Acknowledgment of a request from Lucan Disability Action Group. Site survey. | Detailed site survey |
| N/A | Footpath Repair outside Peamount Hospital (Newcastle) | 2008 | 2008 | €5000 |  |  | Site survey. | Detailed site survey |

| Priority | Action & Sub-Tasks | Timeframe |  |  | Budgetary Estimate | Lead Department | Linkage with | Detail of progress to date / amendments to action. | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Start |  | Completion |  |  |  |  |  |
| 1 | Upgrade of 6 locations in Clondalkin Village: 1 Provide 3 accessible parking bays; 2. Provide colour contrast to posts and street furniture (2 locations); 3. Repaving (2 locations) Provide audible signaling to traffic lights | 2008 |  | 2008 | €36000 | Roads-Traffic Roads – Maintenance (repaving | Architectural Services (Seating | Brief description of works to be performed | Detailed site survey |
| 1 | Upgrade of 9 locations in Rathfarnham Village: 1. Provide accessible parking bays, signs, hatching(4 locations); 2. Repaving (3 Locations); 3.Relocate gratings and repair tactile paving; 4. Provide handrails at 2 ramps. | 2008 | 2008 |  | € 44000 | Roads – Traffic Roads – Maintenance (Repaving) | Architectural Services (handrails) Environmental Services (Gratings) | Brief description of works to be performed | Detailed site survey |
| 1 | Upgrade of 3 locations in Tallaght Village: 1.Improve colour contrast to street furniture and signs; 2.Provide tactile surface to handrails | 2008 | 2008 |  | € 400 | Architectural Services |  | Brief description of works to be performed | Detailed site survey |
| 1 | Upgrade of 7 locations in Walkinstown Cross: dished kerbs, tactile pavings, drainage gullies relocation, a pelican equipment. | 2008 | 2008 |  | € 26000 | Roads – Traffic | Environmental Services (Gratings) | Brief description of works to be performed | Detailed site survey |

| Priority | Action & Sub-Tasks | Timeframe Start Completion Date Date |  | Budgetary Estimate | Lead Department | Linkage with | Detail of progress to date / amendments to action. | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Upgrade of 4 locations in Crumlin: dished kerbs and tactile pavings. | 2008 | 2008 | € 9000 | Roads – Traffic |  | Brief description of works to be performed | Detailed site survey |
| 1 | Upgrade of 2 locations in Hillcrest (Lucan): dished kerbs, tactile pavings and a pelican equipment. | 2008 | 2008 | € 5000 | Roads – Traffic |  | Brief description of works to be performed | Detailed site survey |
| 1 | Upgrade of 5 locations in Nutgrove: dished kerbs, tactile pavings and road markings. | 2008 | 2008 | € 10000 | Roads – Traffic |  | Brief description of works to be performed | Detailed site survey |
| 1 | Upgrade of 2 locations in Cookstown/Old Belgard Rd. (Tallaght): tactile pavings. | 2008 | 2008 | € 24000 | Roads – Traffic |  | Brief description of works to be performed | Detailed site survey |
| 1 | Upgrade of 3 locations in Newland Cross (Clondalkin): dished kerbs and tactile pavings. Upgrade a junction. | 2008 | 2008 | € 28000 | Roads – Traffic |  | Brief description of works to be performed | Detailed site survey |
| Priority | Action & Sub-Tasks | Timeframe |  | Budgetary Estimate | Lead Department | Linkage with | Detail of progress to date / amendments | Next Steps |
|  |  | Start | Completion |  |  |  |  |  |
| 1 | Upgrade of 5 locations in Oldcourt: dished kerbs, tactile pavings and road markings. | 2008 | 2008 | € 11000 | Roads – Traffic |  | Brief description of works to be performed | Detailed site survey |
| 1 | Upgrade of 5 locations in Kingswood Heights: dished kerbs, tactile pavings and footpath repair. | 2008 | 2008 | € 15000 | Roads – Traffic Roads – Maintenance (Footpath repair) |  | Brief description of works to be performed | Detailed site survey |
| 1 | Upgrade of 2 locations in New Road (Clondalkin): dished kerbs and service cover. | 2008 | 2008 | € 6000 | Roads – Traffic |  | Brief description of works to be performed | Detailed site survey |

| Priority | Action & Sub-Tasks | Timeframe Start Completion Date Date |  | Budgetary Estimate | Lead Department | Linkage with | Detail of progress to date / amendments | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Upgrade of 3 locations in Finnstown (Lucan): dished kerbs, tactile pavings and ponding to be drained. | 2008 | 2008 | € 12600 | Roads – Traffic Environmental services (ponding) |  | Brief description of works to be performed | Detailed site survey |
| 1 | Upgrade of 3 locations in Templeogue: tactile pavings and cycle track to be separated from footpath. | 2008 | 2008 | € 6400 | Roads – Traffic |  | Brief description of works to be performed | Detailed site survey |
| 1 | Upgrade of 2 locations in Whitechurch: dished kerbs and a ramp to access the church. | 2008 | 2008 | € 8000 | Roads – Traffic Architectural services (ramp) |  | Brief description of works to be performed | Detailed site survey |
| 1. | Upgrade of 3 locations in Dodder Road Lower: tactile pavings and resurfacing | 2008 | 2008 | € 8400 | Roads – Traffic Roads – Maintenance (resurfacing) |  | Brief description of works to be performed | Detailed site survey |
| 1. | Upgrade of 3 locations in The Mill, Old Bawn Road: tactile pavings and cycle track to be separated from footpath. | 2008 | 2008 | € 6400 | Roads – Traffic |  | Brief description of works to be performed | Detailed site survey |

| Priority | Action & Sub-Tasks | Timeframe |  | Budgetary Estimate | Lead Department | Linkage with | Detail of progress to date / amendments to action. | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Upgrade of 6 locations in Springfield / Maplewood (Tallaght): dished kerbs, tactile pavings and colour contrast to bollards. | 2008 | 2008 | € 9500 | Roads – Traffic |  | Brief description of works to be performed | Detailed site survey |
| 1 | Upgrade of 4 locations in Lucan Village: - Repaving (3 locations); - Provide colour contrast to street furniture; | 2009 | 2009 | € 20000 | Roads – Maintenance (Repaving) Architectural Service (street furniture) |  | Brief description of works to be performed | Detailed site survey |
| 1 | Upgrade of 8 locations in Palmerstown Village: Repaving (3 locations); Provide colour contrast to street furniture; Improve lighting in footbridge ramps; Provide audible signal to pelican equipment; Improve signage. | 2009 | 2009 | € 34000 | Roads – Maintenance (Repaving) Architectural Service (street furniture) Roads - Traffic (Pelican and signage) Road – Public lighting (footbridge lighting) |  | Brief description of works to be performed | Detailed site survey |

| Priority | Action & Sub-Tasks | Timeframe |  | Budgetary Estimate | Lead Department | Linkage with | Detail of progress to date / amendments to action. | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Upgrade of 4 locations in Rathcoole Village: - Repaving (3 locations); - Provide colour contrast to street furniture; | 2009 | 2009 | € 20000 | Roads – Maintenance (Repaving) Architectural Service (street furniture) |  | Brief description of works to be performed | Detailed site survey |
| 1 | Upgrade of 6 locations in Kingswood (N7): dished kerbs, tactile pavings and footpath. | 2009 | 2009 | € 40000 | Roads – Traffic |  | Brief description of works to be performed | Detailed site survey |
| 1 | Upgrade of 7 locations in Rowlagh (Clondalikn): dished kerbs, tactile pavings, splitter islands, accessible parking spaces and footpath. | 2009 | 2009 | € 43000 | Roads – Traffic | Architectural Services (corduroy tactile paving at stairs) | Brief description of works to be performed | Detailed site survey |
| 1 | Upgrade of 2 locations in Bawnogue (Clondalkin): dished kerbs, tactile pavings, tapping kerb and barriers. | 2009 | 2009 | € 6000 | Roads – Traffic |  | Brief description of works to be performed | Detailed site survey |

| Priority | Action & Sub-Tasks | Timeframe |  | Budgetary Estimate | Lead Department | Linkage with | Detail of progress to date / amendments to action. | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Upgrade of 7 locations in Ballyowen (Liffey Valley): dished kerbs, tactile pavings, bollards and a drainage gully to be relocated. | 2009 | 2009 | € 33000 | Roads – Traffic | Environmental Services (drainage gully) | Brief description of works to be performed | Detailed site survey |
| 1 | Upgrade of Taylor Lane (Rathfarnam): dished kerbs and tactile pavings. | 2009 | 2009 | € 4000 | Roads – Traffic |  | Brief description of works to be performed | Detailed site survey |
| 1 | Upgrade of 3 locations in Knocklyon: dished kerbs and tactile pavings. | 2009 | 2009 | € 6400 | Roads – Traffic |  | Brief description of works to be performed | Detailed site survey |
| 1 | Upgrade of 4 locations in St. John’s Drive (Clondalkin): dished kerbs, tactile pavings resurfacing and speed hump marking. | 2009 | 2009 | € 19000 | Roads – Traffic | Roads – Maintenance (resurfacing) | Brief description of works to be performed | Detailed site survey |
| 1 | Upgrade of 4 locations in Yellow Meadows (Clondalkin): dished kerbs and tactile pavings. | 2009 | 2009 | € 10000 | Roads – Traffic |  | Brief description of works to be performed | Detailed site survey |
| Priority | Action & Sub-Tasks | Timeframe |  | Budgetary Estimate | Lead Department | Linkage with | Detail of progress to date / amendments to action. | Next Steps |
| 1 | Upgrade of 3 locations in Deansrath (Clondalkin): dished kerbs, tactile pavings and obstacle removal in footpath. | 2009 | 2009 | € 5200 | Roads – Traffic |  | Brief description of works to be performed | Detailed site survey |
| 1 | Upgrade of 3 locations in Neilstown (Clondalkin): tactile pavings, colour contrast to bollards and repair swing gate to shopping centre. | 2009 | 2009 | € 10000 | Roads – Traffic | Architectural Services (swing gate) | Brief description of works to be performed | Detailed site survey |
| 1 | Upgrade of 4 locations in Quarryvale (Clondalkin): dished kerbs and tactile pavings. | 2009 | 2009 | € 17000 | Roads – Traffic |  | Brief description of works to be performed | Detailed site survey |
| 1 | Upgrade of 6 locations in Newcastle Road (Lucan): dished kerbs, tactile pavings, modify slippery metal plate and and obstacle removal in footpath. | 2009 | 2009 | € 24400 | Roads – Traffic |  | Brief description of works to be performed | Detailed site survey |
| Priority | Action & Sub-Tasks | Timeframe |  | Budgetary Estimate | Lead Department | Linkage with | Detail of progress to date / amendments to action. | Next Steps |
| 1 | Upgrade of 5 locations in Ballyroan: dished kerbs and tactile pavings. | 2009 | 2009 | € 7200 | Roads – Traffic |  | Brief description of works to be performed | Detailed site survey |
| 1 | Upgrade of 3 locations in Orwell Park: dished kerbs, tactile pavings and pedestrian barriers. | 2009 | 2009 | € 9200 | Roads – Traffic |  | Brief description of works to be performed | Detailed site survey |
| 1 | Upgrade of 3 locations in Limeklin Avenue: dished kerbs, tactile pavings and footpath resurfacing. | 2009 | 2009 | € 14400 | Roads – Traffic Roads – Maintenance (resurfacing) |  | Brief description of works to be performed | Detailed site survey |
| 1 | Upgrade of 1 location in Saggart Village: resurfacing. | 2010 | 2010 | € 10000 | Roads – Maintenance |  | Brief description of works to be performed | Detailed site survey |
| 1 | Upgrade of Newcastle Village: resurfacing (14 locations), colour contrast to street furniture (1 location) and improve signage (2 locations). | 2010 | 2010 | € 102240 | Roads – Maintenance (resurfacing) | Roads –Traffic (signage) Architectural Services (street furniture) | Brief description of works to be performed | Detailed site survey |

| Priority | Action & Sub-Tasks | Timeframe |  | Budgetary Estimate | Lead Department | Linkage with | Detail of progress to date / amendments to action. | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Upgrade of Templeogue Village: resurfacing (9 locations), accessible parking bays (2 locations) and improve signage (1 location). | 2010 | 2010 | € 73240 | Roads – Maintenance (resurfacing) | Roads – Traffic (parking bays and signage) | Brief description of works to be performed | Detailed site survey |
| 1 | Upgrade of 7 locations in Knocklyon Heights: dished kerbs, tactile pavings, splitter islands and handrails. | 2010 | 2010 | € 23400 | Roads – Traffic | Architectural Services (handrails and corduroy at stairs) | Brief description of works to be performed | Detailed site survey |
| 1 | Upgrade of 5 locations in Whitehall Rd./Whitehall Rd. West: dished kerbs, tactile pavings and footpath. | 2010 | 2010 | € 28400 | Roads – Traffic |  | Brief description of works to be performed | Detailed site survey |
| 1 | Upgrade of 3 locations in Killinarden (Tallaght): dished kerbs, tactile pavings, and bollards. | 2010 | 2010 | € 7200 | Roads – Traffic |  | Brief description of works to be performed | Detailed site survey |
| 1 | Upgrade of 3 locations in Brookfield (Tallaght): tactile pavings, and bollards. | 2010 | 2010 | € 4400 | Roads – Traffic |  | Brief description of works to be performed | Detailed site survey |
| Priority | Action & Sub-Tasks | Timeframe |  | Budgetary Estimate | Lead Department | Linkage with | Detail of progress to date / amendments to action. | Next Steps |
| 1 | Upgrade of 3 locations in Kilnamanagh (Tallaght): dished kerbs, tactile pavings, and handrails. | 2010 | 2010 | € 21800 | Roads – Traffic | Architectural Services (handrails and corduroy at stairs) | Brief description of works to be performed | Detailed site survey |
| 1 | Upgrade of 3 locations in Aylesbury: dished kerbs, tactile pavings, footpath repaving and bollards. | 2010 | 2010 | € 15600 | Roads – Traffic | Roads – Maintenance (resurfacing) | Brief description of works to be performed | Detailed site survey |
| 1 | Upgrade of 2 locations in Manor Road: dished kerbs and tactile pavings. | 2010 | 2010 | € 3200 | Roads – Traffic |  | Brief description of works to be performed | Detailed site survey |
| 1 | Upgrade of 3 locations in Kennelsfort Road: dished kerbs, tactile pavings, footpath and bollards. | 2010 | 2010 | € 13800 | Roads – Traffic |  | Brief description of works to be performed | Detailed site survey |
| 1 | Upgrade of 7 locations in St. Dominics (Tallaght): dished kerbs, tactile pavings, footpath repaving, swing gate modification and obstacle removal. | 2010 | 2010 | € 17600 | Roads – Traffic | Roads – Maintenance (resurfacing) Architectural Services (swing gate to estates) | Brief description of works to be performed | Detailed site survey |

| Priority | Action & Sub-Tasks | Timeframe |  | Budgetary Estimate | Lead Department | Linkage with | Detail of progress to date / amendments to action. | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Upgrade of 6 locations in Firhouse (Tallaght): dished kerbs, tactile pavings, footpath repaving, and tree drainage grids. | 2010 | 2010 | € 31000 | Roads – Traffic | Roads – Maintenance (resurfacing) Parks (tree drainage grids) | Brief description of works to be performed | Detailed site survey |
| 1 | Upgrade of 5 locations in Kiltalown (Tallaght): dished kerbs, tactile pavings, footpath repaving and audible signal at pelican. | 2010 | 2010 | € 27400 | Roads – Traffic | Roads – Maintenance (resurfacing) | Brief description of works to be performed | Detailed site survey |
| 1 | Upgrade of 5 locations in Fettercairn (Tallaght): dished kerbs, tactile pavings and footpath repaving. | 2010 | 2010 | € 10600 | Roads – Traffic Roads – Maintenance (resurfacing) |  | Brief description of works to be performed | Detailed site survey |
| 1 | Upgrade of 5 locations in Tymon (Tallaght): tactile pavings and footpath repaving. | 2010 | 2010 | € 14200 | Roads – Traffic Roads – Maintenance (resurfacing) |  | Brief description of works to be performed | Detailed site survey |

| Priority | Action & Sub-Tasks | Timeframe |  | Budgetary Estimate | Lead Department | Linkage with | Detail of progress to date / amendments to action. | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Upgrade of 4 locations in Fortunestown (Tallaght): dished kerbs, tactile pavings and footpath obstacle removal. | 2010 | 2010 | € 10400 | Roads – Traffic |  | Brief description of works to be performed | Detailed site survey |

The estimated funding required for Roads & Public Realm access works is €1,170,000

- 5. PARKS AND LANDSCAPE SERVICES

- 5.1. Introduction

The Council is well served by public parks and open spaces of which there are almost 4000 acres under the control of Parks and Landscape Services Section. This is mainly comprised of four large regional parks at Tymon Park, Tallaght; Corkagh Park, Clondalkin; Griffeen Valley Park, Lucan and Dodder Valley Park between Tallaght and Rathfarnham and 50 neighbourhood parks such as Sean Walsh Memorial Park, Ballymount Park and Jobstown Park in Tallaght, Ballyowen Park, Lucan and Collinstown Park, Clondalkin. There are also numerous public open spaces in various housing estates throughout the County.

Parks and Landscape Services staff are engaged in a wide range of activities from planning and design to the development and management of parks and open spaces and advising other departments, especially the Planning Department on planning applications. Within parks, some of the facilities provided and maintained are water features, pedestrian path networks, football pitches, sports facililities and children’s playgrounds. Street trees, roadside margins along main roads, landscaped embankments and roundabouts are also maintained by the department.

In Spring 2007 Capita Symonds were engaged by the Council to carry out a series of accessibility audit reports on public parks across South Dublin County.  The core aim of this exercise was to identify where the parks were in breach of the requirements of the Disability Act 2005 and recommend actions to bring the parks into compliance.

Each of the audits primarily examined whether or not the Parks Department were compliant with Part 3 of the 2005 Act.  This requires public bodies ‘to ensure, where reasonable and appropriate, their services are available to disabled people via integrated access’.  The guidance provided in the reports complies with current Approved Codes of Practice and on health and safety issues which were observed by the auditors during the inspections.

Because of the diverse range of facilities provided by the Parks Department across the County a large variety of different issues were raised in the audit reports.  However, in general the actions required fall into three main categories:

- Information - the provision of appropriate signage

- The external environment including entrances, pathways, seating, parking and playgrounds

- Buildings including toilet facilities and changing facilities.

The overall cost of the recommended works is estimated at over €2 million.  The costs of carrying out the works however are likely to be considerably higher due to factors such as  economy of scale, co-ordination with other departments and regional disparity in relation to availability of labour or labour costs.

Over the past few years there has been a growing awareness amongst Parks Departments in local authorities of their roles in creating accessible public places and major changes have been taking place.  This is evident in South Dublin County by our ongoing improvements in terms of signage, park entrances and especially in the upgrading of our playgrounds.

Exciting new developments that will benefit all the community, whilst also being of particular benefit to those with mobility impairments who wish to carefully plan their visits to the park, include the development of ‘iWalks’ which will soon be available through the Council website and iTunes.

The Parks Dept in the Council is committed to making their parks and open spaces accessible to all members of the community and as such will endeavour to incorporate all recommended actions into our works programmes.  Initially priority is being given to improving our signage and also to improving our toilet facilities.  Much of this work has already started.  For major items of expenditure such as providing parking, pathways and playgrounds works will be completed over the next few years as funding becomes available.

While the Parks Department has agreed with the majority of the recommendations contained in the audit reports we also have reservations about others.  In some instances the recommended actions are not always practicable.  This includes provision of seating in areas where local people would fear that it would lead to groups congregating at night and causing a nuisance to the local community.  In such cases we shall endeavour to work with local people and implement the recommendations if the situation changes.

In order for the Parks Department to meet its commitments and come into compliance with the law it is important that everyone is aware of our responsibilities.  The matrices of actions have been drawn up and agreed with the Senior Executive Parks Superintendents with responsibility for all the parks audited.  Following on from this a departmental meeting will be held to brief all staff on the results of the audits and on the agreed timetable of works.  A series of briefings will then be held in the relevant depots to ensure that every member of parks staff gets a greater understanding of the issues around accessibility and are made aware of the works which need to be carried out in their areas over the next three years.

The Parks Department is in the process of complying with the Disability Act 2005 as far as is practicable and financially viable based on finance available, resources and the level of anti-social behaviour in a given area.  This said the vast majority of the works identified by the access auditors in the summer of 2007 will be undertaken over the next 3/5 years as resources become available.

- 5.2.About the Parks Action Matrices

Summary action matrices prepared by the Parks Department are presented below. Overall we found that the process of producing the matrices of actions really focuses minds on what we have to do to bring our services in line with what is expected under the Disability Act 2005 and will greatly improve our ability to plan for the next three years.

Actions for the Esker, Tymon and Corkagh regions are presented first including the estimated cost excluding VAT to be carried out by the Parks Department over the next 3-5 years by district.   An additional summary of works identified during audit that are outside of the remit of the Parks department is appended to this document.  This list has been forwarded the departments and agencies concerned.

The summary of works to be carried out by the Parks Department contains 74 actions estimated at €1,961,416.20 plus VAT at 21%, giving an estimated inclusive total of €2, 091,025.20.

The Parks Department are dividing the actions to be completed as follows:

2008: Entrances and signage improvement works and works to toilet facilities to at least comply with the existing regulations

2009: Improvement works to and installation of pathways and car parks.

2010 onwards: all remaining works identified.

- 5.3. Parks – Esker District

(Esker District Parks audited include Griffeen Valley Park, Collinstown Park, Stewarts Hospital, Grange Castle Golf Club, Lucan Village Park, Liffey Valley Park.)

| Priority | ESKER Park names | Action & Sub-Tasks | Timeframe |  | Budgetary Estimate | Lead Department | Linkage with | Detail of progress to date/amendments to action | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Start Date | Completion Date |  |  |  |  |  |
| 1 | Collins Park, Griffeen Valley, Lucan Village Park, Golf Course, Lucan Demense, Stewart’s Hospital | Provide Suitable signage at the entrances around the park | Q2 2007 | Q4 2010 | 145k | Parks Dept |  | Review of Park Signage Programme |  |
| 1 | Griffeen Valley Park, Golf Course, Lucan Demense, Stewarts Hospital, | Provide suitable signage offering directions throughout the park | Q2 2007 | Q4 2010 | 45k | Parks Dept |  | Review of Park Signage Programme |  |

ESKER District Continued

| Priority | Park names | Action & Sub-Tasks | Timeframe |  | Budgetary Estimate | Lead Department | Linkage with | Detail of progress to date / amendments to action. | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Start Date | Completion Date |  |  |  |  |  |
| 1 | Golf Course | Entrance signage | Q2 2007 | Q4 2010 | 3k |  |  | Review of park signage |  |
| 1 | Collinstown Park Griffeen Valley Park. | Provide suitable gates to the entrances | Q2 2007 | Q4 2010 | 7.1k | Parks |  | K Barrier to be installed part of NDS 2007 Actions and Budgets |  |
| 1 | Griffeen Valley Park | Provide the accessible parking bays | Q3 2008 | Q3 2008 | 4.5k | Parks |  | NDS 2007 Actions & Budget 3.6k |  |
| 2 | Griffeen Valey Park, Lucan Demense Stewarts Hospital | Provide accessible parking bays | Q3 2008 | ##### Q4 2008 | ##### 8k | Parks | Corporate Services | NDS 2007 Actions and Budget Plan & Part 8 Funds dev of Park (Hayden’s Lane) 200k |  |
| 2 | Collinstown Park, Griffeen Valley Park, Golf Course, Lucan Demense | Provide suitable seating | Q3 2008 | Q4 2010 | 37.5k |  |  |  | Prepare tender for design of new seating perhaps for all departments |

| Priority ESKER | Park names | Action & Sub-Task | Timeframe Start | Timeframe Complete | Budgetary Estimate | Lead Department | Linkage with | Details re progress | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2 | Collinstown Park | Paint gate to playpark Qty 1 | Q2 2009 | Q2 2009 | 0.2k |  |  | Paint gate asap |  |
| 2 | Collinstown Park | Resurface the play areas to assist w/chair users and persons with mobility impairments. Qty 1. | Q2 2009 | Q2 2009 | 10k | Parks |  | No actions until future of playground decided |  |
| 4 | ALL | Keep paths clear and clean |  |  | 0.2k | Parks Dept |  | Part of maintenance schedule |  |
| 1 | Golf course | Provide a panic alarm | Q4 2008 | Q4 2008 | 0.5k | Parks | Corporate Services |  | Refer to DAIT |
| 1 | Golf Course | Provide a fitted loop | Q4 2008 | Q4 2008 | 0.5k | Parks | Corporate Services |  | Refer to DAIT |

| Priority ESKER | Park names | Action & Sub-Task | Timeframe Start | Timeframe Complete | Budgetary Estimate | Lead Department | Linkage with | Details re progress | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2 | Golf Course | Provide a suitable handrails to the external steps | Q4 2008 | Q4 2008 | 0.5k | Parks | Corporate Services |  | Refer to DAIT |
| 2 | Golf Course | Apply permanent colour contrasting nosings to the steps | Q4 2008 | Q4 2008 | 0.2k | Parks | Corporate Services |  | Refer to DAIT |
| 2 | Golf Course | Install grab rails and widen doorway in toilet | Q4 2008 | Q4 2008 | 0.75k | Parks | Corporate Services |  | Refer to DAIT |
| 2 | Golf Course | Change taps at handbasins. | Q4 2008 | Q4 2008 | 0.8k | Parks | Corporate Services |  | Refer to DAIT |
| 2 | Golf Course | Provide an easy to use lock | Q4 2008 | Q4 2008 | 0.2k | Parks Dept | Corporate Services | Obtain & install contractor/direct Labour | Refer to DAIT |

| Priority ESKER | Park names | Action & Sub-Task | Timeframe Start | Timeframe Complete | Budgetary Estimate | Lead Department | Linkage with | Details re progress | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2 | Golf Course | Provide a paper towel and soap dispenser adjacent to the washbasin | Q4 2008 | Q4 2008 | 0.4k | Parks Dept | Corporate Services | Obtain & install contractor/direct labour | Refer to DAIT for tendering |
| 2 | Golf Course | Provide a colour contrasting strip behind each fitting | Q4 2008 | Q4 2008 | 0.2k | Parks Dept | Corporate Services | Obtain & install contracto/direct labour | Refer to DAIT |

| Priority ESKER | Park names | Action & Sub-Tasks | Timeframe |  | Budgetary Estimate | Lead Department | Linkage with | Detail of progress to date / amendments to action. | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Start Date | Completion Date |  |  |  |  |  |
| 2 | Golf Course | Provide a mirror located away from the wash hand basin suitable for wheelchair users and ambulant disabled people | Q4 2008 | Q4 2008 | 0.1k | Parks | Corporate Services | As above | Refer to DAIT |
| 2 | Golf Course | Provide suitable handrails to both side of the ramps | Q4 2008 | Q4 2008 | 1K | Parks | Corporate Services | As above | As above |
| 2 | Golf Course | Replace the double leaf doors with a colour contrasting “Penny Farthing” style door if appropriate | Q4 2008 | Q4 2008 | 1.5K |  | Corporate Services | As above |  |

| Priority ESKER | Park names | Action & Sub-Task | Timeframe Start | Timeframe Complete | Budgetary Estimate | Lead Department | Linkage with | Details re progress | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2 | Golf Course | Fit main entrance door with a delayed action close | Q4 2008 | Q4 2008 | 0.1K |  | Corporate Services | As above |  |
| 2 | Golf Course | Lower Reception counter | Q4 2008 | Q4 2008 | 1K |  | Corporate Services |  |  |
| 2 | Golf Course | Provide Armrests in the locker room | Q4 2008 | Q4 2008 | 0.4K |  | Corporate Services |  |  |
| 2 | Golf Course | There are a number of items required to assist disabled persons when evacuating the building | Q4 2008 | ##### Q4 2008 | ##### 1.5K |  | Management Company |  |  |

| Priority ESKER | Park names | Action & Sub-Task | Timeframe Start | Timeframe Complete | Budgetary Estimate | Lead Department | Linkage with | Details re progress | NEXT STEPS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 4 | Golf Course | Ensure there is a policy to ensure that the floor is kept dry at all times | Q2 2007 Assessment |  |  | Parks | Management Company |  |  |
| 4 | Golf Course | Provide an accessible shower for use by visitors | Q4 2010 | Q4 2010 | 3K | Parks | Management Company |  |  |

- 5.4. Parks Tymon District

(Parks audited are Firhouse Weir, Ballycragh Park, Rathfarnham Castle Park, Tymon Park, Bancroft Park, Avondale Terrace Park)

| Priority | TYMON – Park Name(s) | Action & Sub-Tasks | Timeframe |  | Budgetary Estimate | Lead Department | Linkage with | Detail of progress to date / amendments to action. | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Start Date | Completion Date |  |  |  |  |  |
| 1 | Rathfarnham Castle Park, Dodder Valley Ballycragh Tymon FirhouseWeir Bancroft Avondale | Provide suitable signage at all entrances | 2Q 2007 | Q4 2010 | 155k | Parks | Part of signage review programme |  | Prepare tender for design of new signs |
| 2 | Rathfarnham Castle Park | Provide high level signage to the bays incorporationg the international symbol for access | 2Q 2008 | Q4 2010 | 1k | Parks Dept | OPW/Parks | Part of Signage Review Programme |  |

| Priority | Tymon – Park Name(s) | Action & Sub-Task | Timeframe Start | Timeframe Complete | Budgetary Estimate | Lead Department | Linkage with | Details re progress | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2 | Dodder Valley Bancroft | Provide a suitable gate to the entrances | Q2 2007 Q3 2008 | Q4 2008 | 3.5K | Parks |  | Provision of K Barriers as park of the NDS 2007 Actions and Budget Programme |  |
| 1 | Rathfarnham Castle Park & Tymon | Therefore provide suitable signage offering directions throughout the park | Q2 2008 | Q4 2010 | 11K | Parks |  | Works Programme 2008 |  |
| 2 | Rathfarnham Castle Park | Reposition and highlight bollards | Q2 20010 | On going | 0.4k | Parks |  | Obtain & Install as part of overall future masterplan |  |
| 2 | Rathfarnham Castle Park | Resurface the access route surface to provide a slip resistant and reasonably smooth surface. | Q2 2010 | On going | 20k | Parks |  | Path under review as part of overall future masterplan |  |
| Priority | Tymon – Park Name(s) | Action & Sub-Task | Timeframe Start | Timeframe Complete | Budgetary Estimate | Lead Department | Linkage with | Details re progress | Next Steps |
| 2 | Rathfarnham Castle Park Dodder Valley | Provide a bench/seating with suitable arm supports throughout the park to assist ambulant disabled persons | Q2 2010 | On going | 40k | Parks | Corporate Services | Obtain & install as part of overall future masterplan | Prepare tender for design of new seating perhaps for all depts. |
| 4 | ALL | Ensure that all pathways are kept clear of debris/mud /overgrown grass etc to assist people with visual & mobility impairments | ongoing |  |  |  |  | Part of maintenance routine |  |
| 2 | Dodder Valley Tymon | Provide Accessible Parking Bays | Q2 2010 Q3 2008 | On Going On Going | 15K | Parks |  |  |  |
| 2 | Dodder Valley Tymon | Create new paths | Q3 2009 | Q4 2010 | 61.5K | Parks Dept. |  |  |  |
| 1 | Tymon | Provide a panic alarm | Q3 2008 | Q2 2009 | 0.7k | Parks Dept |  |  |  |
| Priority | Tymon – Park Name(s) | Action & Sub-Task | Timeframe Start | Timeframe Complete | Budgetary Estimate | Lead Department | Linkage with | Details re progress | Next Steps |
| 2 | Tymon | Move hazardous bollards ensure that any bollards and litterbins etc contrast in colour and luminance with the surroundings | Q2 2009 | Q4 2009 | 0.3k | Parks |  |  |  |
| 2 | Tymon | Remark the accessible parking bays | Q3 2008 | ##### Q4 2008 | ##### 9k | Parks |  | Part of Capital Programme, ugrade Carpark at Limekiln |  |
| 2 | Tymon | Resurface the car park to provide an even and stable surface. | Q1 2008 | ##### Q1 2008 | ##### 10k | Parks |  | Complete |  |

| Priority |  | Tymon – Park Name(s) |  | Action & Sub-Task |  | Timeframe Start |  | Timeframe Complete |  | Budgetary Estimate |  | Lead Department |  | Linkage with |  | Details re progress |  | Next Steps |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2 | Tymon |  | Provide contrasting tactile danger warning to the top and bottom of the external steps |  | Q3 2009 |  | Q2 2010 |  | 0.5k |  | Parks |  |  |  | Obtain & Install |  |  |  |  |
| 2 | Tymon |  | Provide suitable handrail to steps. |  | Q3 2009 |  | Q2 2010 |  | 0.5k |  | Parks |  |  |  |  |  |  |  |  |
| 2 | Tymon |  | Apply permanent colour contrasting nosings to all steps |  | Q3 2009 |  | Q2 2010 |  | 0.2k |  | Parks |  |  |  |  |  |  |  |  |

| Priority | Tymon –Park Name(s) | Action & Sub-Task | Timeframe Start | Timeframe Complete | Budgetary Estimate | Lead Department | Linkage with | Details re progress | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2 | Tymon. | Amendments to Toilet Block | Q3 2009 | Q2 2010 | 2.3k | Parks |  |  | Relate to contractor |
| 4 | Tymon | Maintenance to ensure Bridge is accessible | Q3 2010 | ##### On Going | ##### 0.1k | Parks |  |  |  |
| 4 | Tymon | Replace Bridges | Q3 2010 |  | 75k | Parks |  |  |  |

- 5.5 Parks Corkagh District

(Corkagh District includes Rathcoole Park, Corkagh Park, Killinarden Park, Sean Walsh Park, Kiltalown House Park, Camac Valley Camping and Caravan Park, Corkagh Park/Clondalkin Park)

| Priority | Corkagh – Park Name(s) | Action & Sub-Task | Timeframe Start | Timeframe Complete | Budgetary Estimate | Lead Dept. | Linkage with | Details re progress | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | All Parks | Provide Suitable signage at the main entrance of the building | Q2 2007 | Q4 2010 | 165k | Parks | Management of Camac Valley Tourist Camping & Caravan Park | Review of signage for Parks Dept | Assess ASB & implement where practicable |
| 1 | Sean Walsh Park | Directional Signage is unsuitable for persons with a visual impairment | Q2 2007 | Q4 2010 | 10k Est | Parks |  | Part of Signage Review Programme. To be completed as funding becomes available. |  |
| 1 | Camac Valley Caravan Park, Corkagh Park | Provide a fitted induction loop/portable loop interpretive Centre | Start 2009 | Completion 2010 | 13.5K est | Corporate Services | Parks Dept and Mgt of Camac Valley Tourist Camping and Caravan Park |  | Acquire through tender DAIT |

| Priority | Corkagh – Park Name(s) | Action & Sub-Task | Timeframe Start | Timeframe Complete | Budgetary Estimate | Lead Department | Linkage with | Details re progress | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Clondalkin Park, Corkagh Park, SWP | There are no wheelchair accessible parking facilities provide | Q1 2008 | Q4 2012 | 404.5k | Parks Dept | Roads Dept | A new plan for the carpark is to be designed. Should the plan be approved by Council works will commence asap | Works have commenced |
| 1 | Clondalkin Park | At present a number of entrances around the park are unsuitable for wheelchair users. | Q2 2007 | Q4 2007 | 4k | Parks |  | Park financed by NDS 2007, Actions & Budgets and Levies 2007 and Capital Works | Review gate width & install K barrier |
| 1 | Sean Walsh Park | There is no designated drop off point at this facility | Q4 2008 | Q4 2010 | 1.5K for assessment | Parks | Roads |  | Assess by Q4 2010. |
| Priority | Corkagh – Park Name(s) | Action & Sub-Task | Timeframe Start | Timeframe Complete | Budgetary Estimate | Lead Department | Linkage with | Details re progress | Next Steps |
| 2 | Camac Valley Caravan Park | Provide contrasting tactile danger warning to the top and bottom of the external steps | Q2 2008 | Q2 2008 | 1k | Parks | Management of Camac Valley Tourist Camping & Caravan Park |  | Refer to Corkagh Depot & Camac Valley Mgt. |
| 2 | Camac Valley, Rathcoole Park, Corkagh Park | Provide suitable handrails to the external steps | Q2 2009 | Q4 200 | 10.5k | Parks | as above |  | Refer to Corkagh Depot & Camac Valley Mgt |
| 2 | Camac Valley Caravan Park, Corkagh Park, Rathcoole Park | Nosings to the steps are not readily identifiable | Q2 2008 | Q2 2008 | 1.8k, | Parks Dept | Management of Camac Valley Tourist Camping and Caravan Park |  | Refer to Corkagh Depot & Management of Camac Valley Camping and Caravan Park – Obtain quotes |
| Priority | Corkagh – Park Name(s) | Action & Sub-Task | Timeframe Start | Timeframe Complete | Budgetary Estimate | Lead Department | Linkage with | Details re progress | Next Steps |
| 2 | Corkagh Park | Provide level access to the picnic tables within the park | Q2 20010 | Q4 20010 | 10k | Parks Dept |  |  | Possible solutions to be ascertained and priced. |
| 2 | Camac Valley Caravan Park | The surface of the play area is not suitable for wheelchair users. | Start 2010 approx |  | 150k | Parks | Management of Camac Valley Tourist Camping and Caravan Park |  | Camac Valley: Playground needs to be upgraded including surfacing. |
| 2 | Camac Valley Caravan Park | The existing seating is not suitable for ambulant disabled persons. | Q1 2008 | Q3 2008 | Parks | Management of Camac Valley Tourist Camping and Caravan Park |  |  | Refer to Corkagh Depot and Management of Camac CCP |

| Priority | Corkagh – Park Name(s) | Action & Sub-Task | Timeframe Start | Timeframe Complete | Budgetary Estimate | Lead Department | Linkage with | Details re progress | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2 | Camac Valley Caravan Park and Corkagh Park | At present there is no contrast between the sink and urinal fittings and the background in the WCs | Start Q1 2009 | Complete Q4 2009 | 1k | Parks | Camac Valley Mgt as above |  | DAIT Acquire through tender process |
| 2 | Camac Valley Caravan Park and Corkagh Park | At present the controls to the compartments in both male & female WCs and showers are difficult to operate | Q1 2009 | Q4 2009 | 3.8k | Parks | Parks Camac Mgt as above Corporate Services |  | Acquire through tender |
| 2 | Camac Valley Caravan Park and Corkagh Park | Provide horizontal grab rails to either side of cubical in all toilets | Q1 2009 | Q4 2009 | 4.8k | Parks | As above |  | As above |
| 2 | Camac Valley Caravan Park and Corkagh Park | Currently the accessible WCs in the shower blocks do not meet standards | Q1 2009 | Q4 2010 | 40k | Parks | As above |  | As above |

| Priority | Corkagh – Park Name(s) | Action & Sub-Task |  | Timeframe Start |  | Timeframe Complete |  | Budgetary Estimate |  | Lead Department |  | Linkage with |  | Details re progress |  | Next Steps |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2 | Camac Valley Caravan Park | The external doors are double leaf |  | Q1 2009 |  | Q4 2009 |  | 2k est |  | Parks |  | As above |  |  |  | As above |  |
| 2 | Camac Valley Caravan Park | Provide a lowered section at the reception counter to accommodate wheelchair users. |  | Q1 2009 |  | Q4 2009 |  | 3K |  | Corporate Services |  | Parks Dept & Management of Camac Valley Tourist Camping & Caravan Pk |  |  |  | Acquire through tender process DAIT |  |
| 2 | Clondalkin Park | There is currently no pathways from the Cherrywood Avenue, wildflower meadow entrance to the sports pitches |  | Q4 2008 |  | Q4 2008 |  | 10k |  | Parks |  |  |  | Parks Works Programme 2008 |  | Construct Path |  |
| 2 | Corkagh Park, Sean Walsh Park | The pathways are not suitable for wheelchair egress /walking aids |  | Q2 2008 |  | Q4 2008 |  | 100k |  | Parks Dept |  |  |  | Parks Works Programme 2008 |  | Construct Paths |  |
| Priority | Corkagh – Park Name(s) | Action & Sub-Task | Timeframe Start |  | Timeframe Complete |  | Budgetary Estimate |  | Lead Department |  | Linkage with |  | Details re progress |  | Next Steps |  |  |
| 2 | Sean Walsh Park | At present there are bridges throughout the park. All require retro-fit works to enable accessibility |  | Q3 2007 |  | Q4 2008 |  | 65k |  | Parks Dept. |  |  |  | NDS 2007 Actions and Budget 15K and Parks Works Programme 2007 50K |  | Works completed expect painting of bridges |  |

| Priority |  | Corkagh – Park Name(s) |  | Action & Sub-Task | Timeframe Start | Timeframe Complete | Budgetary Estimate | Lead Department | Linkage with | Details re progress |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | . |  |  |  |  |  |  |
| 4 |  | All Parks |  | Ensure that all pathways are kept clear of debris, mud, overgrown grass etc to assist persons with visual and mobility impairments. | Start immediately | Ongoing | N/A | Management of Camac Valley Tourist Camping and Caravan Park | Parks Dept | Maintenance to be completed within maintenance |
| 4 |  | Camac Valley Caravan Park & Corkagh Park |  | The flooring in the toilets is not slip resistant. Ensure policy that the floor is kept dry at all times | Start immediately | Completion ongoing | 0k | As above | Parks | Within maintenance programme of Camac Valley Tourist Camping & Caravan Park |
| 4 |  | Camac Valley Caravan Park, Corkagh Park, Killinarden Park |  | The seating is not designed to offer support for ambulant disabled persons. | Q1 2009 | Q4 2009 | 31.07k | Parks Dept | Mgt of Camac Valley Tourist Camping and Caravan Park. Part of restoration programme of Corkagh |  |
| 4 | Corkagh Park |  | Ensure that the surface of footpaths in the fishing area is kept as smooth and even as possible at all times. |  | ongoing | ongoing | 15k | Parks | Parks Dept & Management of Angling Facilities |  |

Total estimated funding required is €200,000.

- 6. CEMETERIES

- 6.1. Introduction

The Environmental Services Department is endeavouring to ensure that the cemeteries within the Country are as accessible as possible.  Following access audits during 2007, the actions set out in the matrices below have been chosen for progression and completion in 2008.

- 6.2. Saggart Cemetery

| Priority | Action & Sub Tasks | Timeframe |  | Budgetary Estimate | Lead Department | Linkage with | Detail of progress to date/amendments to action. | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Burial Ground Approach Routes & Street Furniture | Start Date | Completion Date |  |  |  |  |  |
| 1 | Cemetery is set back off main route, Garter Lane. Not obvious to passersby. Provide suitable visually contrasting directional signage to further highlight location of the cemetery to assist persons with visual impairment. | Jan 08 | Mar 08 | €600 | Environment | Roads |  |  |
| 1 | Provide suitable visually contrasting signage to wall at cemetery to indicate the location | Jan 08 | Mar 08 | €300.00 | Environment | Roads |  |  |
| 3 | No designated drop off point provided near cemetery entrance. Consider providing permission for visitors requiring assistance to park near the entrance arch. Suitable signage indicating who to contact for permission should be displayed near the entrance. The area in front of the gate should be resurfaced to provide a level and slip resistant surface for use by wheelchair users. | July 08 | Sep 08 | €2,500 | Environment |  |  |  |

- 6.3.  Bohernabreena Cemetery

| Priority | Action & Sub Tasks | Timeframe |  | Budgetary Estimate | Lead Department | Linkage with | Detail of progress to date/amendments to action. | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Start Date | Completion Date |  |  |  |  |  |
|  | WC’S: GENERAL PROVISION |  |  |  |  |  |  |  |
| 1 | Provide accessible toilet in line with guidance of NDA Building for Everyone. Suitable directional signage Suitable door controls, lock and light switch easily reached and operated: Hand washing and drying facilities within reach of someone seated on WC; A panic alarm fitted in a suitable area A spatula lever flush on transfer side of WC Colour contrasting grab rails fitted | Nov 07 | Dec 07 | €6,000 | Environment |  |  |  |

| Priority | Action & Sub Tasks | Start Date | Completion Date | Budget Estimate | Lead Dept | Linkage | Details of progress to date/amendments | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BURIAL GROUND ENTRANCES |  |  |  |  |  |  |  |
| 1 | Provide signage as close as possible to the entrances indicating the facilities/assistive equipment etc. available within the building for use by disabled visitors. | Jan 08 | Mar 08 | €300 | Environment |  |  |  |
|  | BURIAL GROUND APPROACH ROUTES & STREET FURNITURE |  |  |  |  |  |  |  |
| Section 1.6 Priority 2 | Approaches to the crossovers on the pedestrian pavement do not have suitable tactile warning for persons with visual impairment. Provide contrasting tactile blister paving to the following crossovers to provide guidance/warning to persons with visual impairment: Approach route pavement within Burial Ground Crossing at 2 entrances | Jan 08 | Jun 08 | €4,800 | Environment | ROADS |  |  |

| Priority | Action & Sub Tasks | Start | Completion | Budget Estimate | Lead Dept | Linkage | Details of progress to date/amendments | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BURIAL GROUND CAR PARKING |  |  |  |  |  |  |  |
| Section 2.1 Priority 2 | Accessible parking facilities for people with mobility impairment. Accessible parking spaces to be marked 4.8m x 2.4m with a 1.2m transfer zone to side and rear. Designated spaces positioned close to the car park entrances as possible. Suitable high level signage incorporating international symbol for access should accompany the designated space to help limit misuse of designated space | Jan 08 | Jun 08 | €1,800 | Environment |  |  |  |

| Priority | Action & Sub Tasks | Start Date | Completion Date | Budget Estimate | Lead Dept | Linkage | Details of progress to date/amendments | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BURIAL GROUND HORIZONTAL CIRCULATION ROUTES |  |  |  |  |  |  |  |
| 2 | Dropped kerb to pavement from main entrance pedestrian gate to the routes around the cemetery. Approach route within Burial Ground. | Jan 08 | Jun 08 | €400 | Environment |  |  |  |
|  | BURIAL GROUND VERTICAL CIRCULATION ROUTES |  |  |  |  |  |  |  |
| 2 | Provide tactile danger warning to top/bottom of external steps to provide suitable guidance/warning to persons with a visual impairment. Also on Steps from Main Road Steps within Cemetery | Jan 08 | Jun 08 | €750 | Environment |  |  |  |
|  | Provide handrails to external steps. Handrails should have an oval/circular profile. Suitable complete that contrasts in colour and luminance the surroundings against without being highly reflective. Steps at side of secondary entrance within cemetery. | Jan 08 | Jun 08 | €1,200 | Environment |  |  |  |

| Priority | Action & Sub Tasks | Start Date | Completion Date | Budget Estimate | Lead Dept | Linkage | Details of progress to date/amendments | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2 | Nosings to the steps are not readily identifiable and may present a trip hazard to persons with visual impairment. Apply permanent colour contrasting nosings to all steps. Ensure top/bottom nosings contrast with nosings on the remaining steps. Specifically on steps from main road and steps within cemetery | Jan 08 | Jun 08 | €2,000 | Environment |  |  |  |
|  | WC’S:. GENERAL PROVISION |  |  |  |  |  |  |  |
| 2 | Horizontal drop down grab rails to either side of the male/female WC in toilets to assist ambulant disabled persons while lowering and raising themselves | Jan 08 | Jun 08 | €900 | Environment |  |  |  |

| Priority | Action & Sub Tasks | Start | Completion | Budget Estimate | Lead Dept | Linkage | Details of progress to date/amendments | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2 | Taps to wash hand basins in toilets may be difficult to operate by persons with dexterity impairment/limited strength. Provide 1 set of lever style taps to 1 No. wash hand basin in all standard toilets. | Jan 08 | Jun 08 | €750 | Environment |  |  |  |
|  | Burial Ground Car Parking |  |  |  |  |  |  |  |
|  | Car park surface has a surface of loose stones and is unsuitable for wheelchair users. Resurface the car park to provide an even and stable surface. | July 08 | Sep 08 | €10,000 | Environment |  |  |  |

- 6.4.  Esker Cemetery

| Priority | Action & Sub Tasks | Timeframe Start Completion |  | Budgetary Estimate | Lead Department | Linkage with | Detail of progress to date/amendments to action. | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Burial Ground Entrances |  |  |  |  |  |  |  |
|  | Improve signage at entrances. Ensure text size and colour contrast correspond with the specifications detailed in NDA Buildings | Jan 08 | March 08 | €400 | Environment |  |  |  |
|  | Burial Ground Approach Routes & Street Furniture |  |  |  |  |  |  |  |
| Section 1.6 Priority 2 | Crossovers on pedestrian pavement do not have suitable tactile warning for persons with visual impairment. Provide contrasting tactile blister paving to the following crossovers to provide suitable guidance and warning to persons with visual impairment | Jan 08 | June 08 | €2,400 | Environment | Roads |  |  |
| Priority | Action & Sub Tasks | Start Date | Completion Date | Budget Estimate | Lead Dept | Linkage | Details of progress | Next Steps |
|  | Burial Ground Car Parking |  |  |  |  |  |  |  |
|  | No wheelchair accessible parking facilities provided in car park within cemetery. Some if not all of the car park should be resurfaced. Designated spaces should be positioned as close to the entrance to the cemetery as possible. High level signage should accompany the designated space to help limit misuse of the accessible parking space | Jan 08 | June 08 | €6,000 | Environment |  |  |  |
|  | Burial Ground Entrances |  |  |  |  |  |  |  |
| 4 | There are 2 pedestrian gates. One of the gates get stuck half opened on the surface. Re-Grade surface so gate passes smoothly over. Daytime hours, if arrangement alters catches to the pedestrian gates should be replaced with handles that are easily used by persons with limited manual dexterity. | Sep 08 | Dec 08 | €800 | Environment |  |  |  |

- 6.5. Newcastle Cemetery

| Priority | Action & Sub Tasks | Timeframe |  | Budgetary Estimate | Lead Department | Linkage with | Detail of progress to date/amendments to action. | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Start Date | Completion Date |  |  |  |  |  |
|  | Burial Ground Approach Routes & Street Furniture |  |  |  |  |  |  |  |
|  | Provide directional signage along route from Main Street, Newcastle and along R120 to indicate location of graveyard. The signage indicating Burial Ground entrance could be obscured if cars are parked in front of it. Provide high level visually contrasting signage to further indicate cemetery location. | Jan 08 | March 08 | €1,500 | Environment | Roads |  |  |
| 2 | There is no dedicated drop off point provided on R120. The entrance gates are set slightly back off the road, providing space for 2/3 cars to pull up off the main route. Provide markings on lay-by area to indicate suitable area for cars to pull up. | Jan 08 | June 08 | €600.00 | Environment | Roads |  |  |
|  | Burial Ground Vertical Circulation Routes |  |  |  |  |  |  |  |
| 2 | Some of the secondary routes have a step. Provide graded access to assist ambulant disabled persons to access these areas and remove trip hazards. | Jan 08 | June 08 | €600.00 | Environment |  |  |  |
|  | Burial Ground Horizontal Circulation Routes |  |  |  |  |  |  |  |
| 3 | Provide a bench/seating with suitable arm supports throughout the burial ground to assist ambulant disabled persons | Jul 08 | Dec 08 | €600 | Environment |  |  |  |

- 7.  LIBRARY SERVICES

- 7.1.Introduction

South Dublin County Libraries provide a progressive, community based public library service to all who live, work or study in South Dublin County administrative area.  Serving a population of 240,000 the library service loans approximately 1,000,000 items to the community each year.  The public library service is an important focal point at the heart of the local community and aims to be pro-active and dynamic in addressing its manifold needs, particularly in the areas of information, culture, heritage, literature and lifelong learning.

South Dublin County Libraries Development Plan (2007-2011) states that a major aim of the library service is to “provide a space for all and a space that presents no barriers to access”. While physical access to our buildings has been and will continue to be to be a major part of any access project, much emphasis has also been placed on new and innovative methods of service delivery and achieving excellence in the delivery of those services. An important element of this striving for excellence is that a relevant and effective library service be delivered to all citizens through all life stages, from childhood and into old age.

- 7.2 Physical Access

Extensive access improvement works have been undertaken at Lucan and Whitechurch Libraries since 2005. A works programme commenced in late 2007 at Castletymon Library which incorporates automatic doors, upgrades to existing ramps and to accessible toilet facilities. Refurbished library buildings at the County Library, Tallaght and at Ballyroan Library will be fully compliant as regards physical access. Substantial work remains to be carried out at Clondalkin Library, and the Libraries Department intends, as far as is practical, to progress these improvements over the next three years.

Initiatives which have been delivered by South Dublin County Libraries to ensure that our buildings are accessible to all include:

- Extensive Opening Hours – 54.5 hours per week for all full-time libraries

- Automated entrance doors

- External and internal wheelchair ramps

- Transit Wheelchairs at all libraries

- Customized signage and tactile markings for customers with visual impartment

- Height Adjustable furniture for public access computers

- Low level

- Induction loop systems in all libraries

- Assistive technologies and hardware which includes scanners, screen enhancers, mice and  keyboards

- 7.3. Library Services

Initiatives which have been delivered by South Dublin County Libraries, while perhaps not introduced specifically under the various access programmes, nevertheless are widely used by and have been further expanded for our disabled customers .South Dublin County Council is the first library authority in Ireland to develop and deliver the award winning e books project in 2007. The e books initiative allows customers to download books, music recordings and DVD’s, completely free of charge, to their pc or MP3 players. This service, among many other online ones, can be accessed through the South Dublin County Libraries website and allows twenty four hour access to library services and materials.

Services developed and delivered to date include:

- Home Library Service to customers, who through illness or impairment are unable to visit our libraries.

- Access to a constantly expanding e books library

- Library materials  available in different formats- Large Print books, audio and preloaded audio books, C.D , D.V.D and C.D ROMs

- Reading materials and Software programmes for children with learning difficulties

- Mufti media materials for adults with learning and literacy difficulties.

- Browse aloud software on the library website

- Access to a host of online reference resources through South Dublin County Libraries website.

- Promotion of eInclusion and eGovernment services through the library website.

- 7.4 Access Matrix

7.4.1 Access Works and Service Provision 2008

| Priority | Action & Sub-Tasks | Timeframe |  | Budgetary Estimate | Lead Department | Linkage with | Detail of progress to date / amendments to action. | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Start Date | Completion Date |  |  |  |  |  |
| 1. | Access Works Castletymon Library – Installation of Library Signage | June 2008 | August 2008 | €5902 | Libraries Department | Configure/ Signage Company | One estimate for works received | Subject to funding, to look at signage systems |
| 1. | Access Works Castletymon Library Provision of two accessible car parking spaces. | June 2008 | December 2008 | €5000 | Libraries Department | Shopping Centre management company | One estimate received | To open discussions with management company seeking permission for works and allocation of spaces. |
| 1 | Access Works Whitechurch Library Installation of tactile and Braille signage | August 2008 | ##### December 2008 | ##### €1500 | Libraries Department | Signage Company | One estimate received. | To proceed to installation |
| 1 | Service Provision County Library Production and conversion of local studies publications to audio and electronic formats | January 2008 | December 2008 | €10,000 | Libraries Department | Recording Technician | Work had commenced on first publication | To proceed to production of four other titles. |
| 1 | Staff Training/ Awareness Awareness/ Training opportunities for staff working with supervising and managing people with mental health difficulties | August 2008 | December 2008 | €3000 | Libraries Department | H.R Department Agencies working with people with mental health difficulties Training Bodies. | An Chomhairle Leabharlanna ( the Library Council has carried out some preliminary work in this area and has sought submissions from Library authorities staff | To identify/source customised training opportunities. |

7.4.2. Clondalkin Library and E Books Provision 2009

| Priority | Action & Sub-Tasks | Timeframe |  | Budgetary Estimate | Lead Department | Linkage with | Detail of progress to date / amendments to action. | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Start Date | Completion Date |  |  |  |  |  |
| 1. | Access Works Clondalkin Library Install low level writing counter surface at library desks | January 2009 | March 2009 | €7000 | Libraries Department | Contracted Company |  | To seek estimates for works |
| 1. | Access Works Clondalkin Library Install a low level wring surface at library desks. | January 2009 | March 2009 | €1500 | Libraries Department | Contracted Company. |  | To seek estimates for works |
| 1. | Access Works Clondalkin Library Upgrade of fire alarm to visual warning standards. | January 2009 | ##### April 2009 | ##### €2000 | Libraries Department | Contracted company |  | To seek estimates for works |
|  | Access Works Clondalkin Library To install an intercom system to allow customers to request assistance at entrance area | January 2009 | March 2009 | €800 | Libraries Department | Contracted company |  | To seek estimates for works |
| 1. | Access Works Clondalkin Library Install corduroy hazard warning surfaces on staircase. | January 2009 | March 2009 | €700 | Libraries Department | Contracted company |  | Estimates for works to be sought |
| 1 | Service Provision To purchase and provide for an increase in the number of eBooks available to our customers | January 2009 | December 2009 | €10,000 | Libraries Department | Libraries Department E Books Service provider | Service developed and introduced in 2007. | To increase number of titles available to our customers. |

7.4.3 Assistive Technologies Programme 2010

| Priority | Action & Sub-Tasks | Timeframe |  | Budgetary Estimate | Lead Department | Linkage with | Detail of progress to date / amendments to action. | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Service Provision Development of customised assistive technologies packages for branch libraries at Ballyroan, Clondalkin, Castletymon, Lucan and Whitechurch Libraries. | Start date January 2010 | Completion Date December 2010 | €15,000 | Libraries Department | I.T Services C.R.C(Central Remedial Clinic) N.C.B.I (National Council for the Blind of Ireland) | Currently being investigated and developed for the County Library. | To tailor and modify specifications for each branch library |

7.5. Programme Expenditure

The total expenditure over the lifetime of the programme will be €62,402 and is comprised as follows

2008         €25,402

2009         €22,000

2010         €15,000

The programme will be funded through the National Disability Strategy funding and from the Libraries Department resources.

South Dublin County Libraries intends to build on access initiatives and continue to strive to achieve universal access to our buildings and services.

- 8.   COMMUNITY SERVICES

- 8.1. Introduction

A comprehensive support and advisory service is provided to voluntary community based organisations throughout the County. The service is operated through a team of Community Officers and Community Workers.  South Dublin County Council recognises that it is not sufficient to provide the physical infrastructure such as housing, roads, parks etc. for new communities but that it is also necessary to provide for the human dimension. The aim of the Community Services Department is to help communities to create a better social and economic environment. The department supports this aim by providing a very comprehensive community development and support service.

The face of South Dublin is changing. Since this Council was formed in 1994 we have experienced many changes. There is a welcoming growth in diversity of cultures, life styles and background. Our economy has changed, as has the physical environment. Our challenge is to meet these changes and provide an optimistic future for our community and our children. Many new areas are being developed including the new town of Adamstown. A great or greater than ever number of organisations are providing the essential services and care needed. No one sector can do it all whether it is the State, businesses, families or local communities. Many significant problems can be solved when individuals and organisations work together and include all concerned in making and implementing decisions.  South Dublin County Council recognises exceptional efforts through a Community Awards Scheme, which fosters pride in our County and our community.   The Council also employs a full time Arts Officer, promoting Art for all, and engaging in interagency projects to promote opportunities for disabled and non disabled artists in the community.

Under the National Agreement, The Programme for Prosperity and Fairness, the government committed itself to tackling the spatial concentration of poverty and exclusion in urban areas. In order to do so, the RAPID (Revitalising Areas by Planning, Investment & Development) Programme was launched in 2001. Of the twenty-five urban RAPID areas, three areas are located in West Tallaght and one in North Clondalkin. RAPID provides for investment and development relating to youth development, unemployment, crime and safety, family support, education and health. The programme focuses in particular on social inclusion, and on the needs of specific target groups, one of which is disabled people. The RAPID Programme and its local Area Implementation Teams work in partnership with the community and state agencies and decide how best to address local needs and ensure the provision and co-ordination of appropriate quality services. Over the last six years the RAPID Programme in South Dublin has focused in particular on ensuring adequate access to services for disabled people. Two Areas in particular which RAPID has focused on are 1) enhanced accessibility for disabled persons in all playground and sports facility constructions; and 2) on mental health, whereby RAPID facilitates a mental health working group in North Clondalkin and works to de-stigmatise mental health issues through awareness raising, information and education in both areas. Additionally the RAPID teams work in partnership with and offer support to community-based disability groups in both areas.

There are a number of Community Centres & Neighbourhood Centres acting as focal points for community activity in their areas throughout South Dublin County. Some Centres have been purpose-built while others have come about through adaptation or conversion of existing structures. Access audits in 2007 highlighted access barriers to community facilities.  The Community Services Department is committed to addressing and removing these barriers, to ensure that all members of the public can enjoy public facilities. Access works were carried out in six Community facilities in 2007.

The Council aims to bring all the service providers working in the area to come together under one roof and provide an opportunity for disabled people in the County area to access information at a more personal level in areas like education, health, employment and training, social welfare entitlements, transport and community and voluntary services. To facilitate this objective the Council held an Opportunities Day for Disabled People in 2007. There were more than 20 organisations represented on the day. Each organisation had an information stand and had staff members available to speak to the information seekers about their activities and their services for disabled people. Over two hundred people attended on the day.

- The Government under the National Children’s Strategy, launched in November 2000, included a commitment to develop National Play and Recreation Policies.

- The agreed Programme for Government built on that Commitment stating that “We will develop a National Play and Recreation Policy which will aim to ensure that all children have access to at least a minimum standard of play and recreation facilities”

Ready Steady Play – National Policy

The following are some of the objectives which have been set out for this policy.

- To give children a voice in the design and implementation of play policies and facilities

- To raise awareness of the importance of play

- To maximise the range of public play opportunities available to all children, particularly children who are marginalised, disadvantaged or disabled.

- To develop a partnership approach in funding and developing play opportunities

Objectives of the Council’s Play policy

- Facilitate and support provision of appropriate, accessible and safe playgrounds and play areas for young people in South Dublin County

- Support and enable local communities to maximise opportunities for play provision by providing guidance on location and access, equipment and safety, the landscape and amenities, maintenance and supervision.

Commitments in the Social Partnership Agreement, ‘TOWARDS 2016’ are also encompassed in our policies and actions.

The Vision as set out in ‘Towards 2016’ is as follows:

The parties to this agreement share a vision of an Ireland where people with disabilities have, to the greatest extent possible, the opportunity to live a full life with their families and as part of their local community, free from discrimination.

To achieve this vision, the Government and the social partners will work together over the next ten years towards the following long-term goals with a view to continued improvements in the quality of life of people with disabilities:

- Every person with a disability would have access to an income which is sufficient to sustain an acceptable standard of living;

- Every person with a disability would, in conformity with their needs and abilities, have access to appropriate care, health, education, employment and training and social services;

- Every person with a disability would have access to public spaces, buildings, transport, information, advocacy and other public services and appropriate housing;

- Every person with a disability would be supported to enable them, as far as possible, to lead full and independent lives, to participate in work and in society and to maximise their potential, and;

- Carers would be acknowledged and supported in their caring role.

The government and the social partners agree that the National Disability Strategy represents comprehensive Strategy for this aspect of the life cycle framework and that implementation of the strategy should be the focus of policy over the lifetime of the agreement.

In line with this vision the Council shall ensure ease of access for all to Council facilities and particularly in new build facilities which are the subject of direct consultation with relevant bodies.

- 8.2. Action Matrix 2008/2009

| Priority | Location | Action & Sub-Tasks | Timeframe |  | Budgetary Estimate | Lead Department | Linkage with | Detail of progress to date / amendments to action. | Next Steps |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | The abbreviation ‘CC’ = Community Centre |  | Start Date | Completion Date |  |  |  |  |  |
| 1 | Ballyowen CC | Car Parking with signage and Direction signage Braille and Tactile signage | 2008 | 2008 | €1,700 | Community Services | Ballyowen Castle Community Centre |  | Secure Funding |
| 1 2 | Fettercairn CC | Car Parking with signage and Direction signage Braille and Tactile signage. Automated Doors | 2008 2008 | 2008 2008 | €1,700 €2,000 | Community Services | Fettercairn Community Centre |  | Secure Funding |
| Priority | Location | Action & Sub-Tasks | Timeframe |  | Budgetary Estimate | Lead Department | Linkage with | Detail of progress to date / amendments to action. | Next Steps |
|  |  |  | Start | ##### Completion |  |  |  |  |  |
| 1 2 | Killinarden CC | Car Parking with signage and Direction signage Braille and Tactile signage. Automated Doors | 2008 | 2008 | €1,700 €2,000 | Community Services | Killinarden Community Centre |  | Secure Funding |
| 1 | Quarryvale CC & Leisure Centre 1 | Car Parking with signage and Direction signage Braille and Tactile signage. | 2008 | 2008 | €1,700 | Community Services | Quarryvale Community & Leisure Centre |  | Secure Funding |
| 2 | Knockmitten C C 1 | Car Parking with signage and Direction signage Braille and Signage Automated Doors | 2008 2008 | 2008 2008 | €1,700 €2,000 | Community Services | Knockmitten Community Centre |  | Secure Funding |
| Priority | Location | Action & Sub-Tasks | Timeframe |  | Budgetary Estimate | Lead Department | Linkage with | Detail of progress to date / amendments to action. | Next Steps |
|  |  |  | Start | Completion |  |  |  |  |  |
| 1 | St. Ronan’s C C | Car Parking with signage and Direction signage Braille and Tactile signage. | 2008 | 2008 | €1,700 | Community Services | St Ronan’s Community Centre |  | Secure Funding |
| 1 2 | St Aengus CC | Car Parking with signage and Direction signage Braille and Tactile signage. Automated Doors | 2008 | 2008 | €1,700 €5,000 | Community Services | St Aengus Community Centre |  | Secure Funding |
| 1 | Killinarden Playground | Install grab rails in Centre Playground equipment. | 2008 | 2008 | €800 | Community Services | Killinarden Community Centre |  | Secure Funding |
| Priority | Location | Action & Sub-Tasks | Timeframe |  | Budgetary Estimate | Lead Department | Linkage with | Detail of progress to date / amendments to action. | Next Steps |
|  |  |  | Start | Completion |  |  |  |  |  |
| 1 | Jobstown Playground | Provide correctly configured dual handrails in identified locations | 2008 | 2008 | €500 | Parks Department | Community Services |  | Secure Funding |
|  | Bawnogue C C 1 2 | Car Parking with signage and Direction signage Braille and Tactile signage. Automated Doors | 2008 2008 | 2008 2008 | €1,700 €2,000 | Community Services | Bawnogue Community Centre |  | Secure Funding |
| 1 2 | Belgard C C | Car Parking with signage and Direction signage Braille and Tactile signage. Automated Doors | 2008 | 2008 | €1,700 €2,000 | Community Services | Belgard Community Centre |  | Secure Funding |
| Priority | Location | Action & Sub-Tasks | Timeframe |  | Budgetary Estimate | Lead Department | Linkage with | Detail of progress to date / amendments to action. | Next Steps |
|  |  |  | Start | Completion |  |  |  |  |  |
|  | Earlsford C C | Car Parking with signage and Direction signage Braille and Tactile signage. | 2008 | 2008 | €1,700 | Community Services | Earlsford Centre |  | Secure Funding |
| 1 2 | Jobstown C C | Car Parking with signage and Direction signage Braille and Tactile signage. Automated Doors | 2009 2008 | 2009 2008 | €1,700 €5,000 | Community Services | Jobstown Community Centre |  | Secure Funding |
| 1 | St. Marks Centre | Car Parking with signage and Direction signage Braille and Tactile signage. | 2009 | 2009 | €1,700 | Community Services | St. Marks Youth & Family Centre |  | Secure Funding |
| Priority | Location | Action & Sub-Tasks | Timeframe |  | Budgetary Estimate | Lead Department | Linkage with | Detail of progress to date / amendments to action. | Next Steps |
| 1 & 2 |  | Minor works to be carried out in 16 Centre’s. eg: new doors, door handles, portable ramps, handrails etc in toilets. | Start 2008 | Completion 2009 | Cost unknown as a survey to cost such, needs to be carried out in the 16 Centre’s by a contractor. Allow €60,000 for such work | Community Services | Ballyowen, Fettercairn, Quarryvale, Killinarden, Knockmitten, Quarryvale Resource Centre, St Ronan’s, Liscarne Court, Rowlagh, Quarryvale CC Bawnogue, Earlsfort, St Aengus, Belgard, Jobstown, and St. Marks. |  | Secure Funding |
| 1 2 | Bawnogue Enterprise Centre | Car Parking with signage and Direction signage Braille and Tactile signage. Automated Doors | 2008 | 2008 | €1,700 €5,000 | Development Department | Community Services |  | Secure Funding |
| Priority | Location | Action & Sub-Tasks | Timeframe |  | Budgetary Estimate | Lead Department | Linkage with | Detail of progress to date / amendments to action. | Next Steps |
|  |  |  | Start | Completion |  |  |  |  |  |
| 1 2 | Killinarden Enterprise Centre | Car Parking with signage and Direction signage Braille and Tactile signage.(includes six other blocks in the complex) Automated Doors | 2008 | 2008 | €2,900 €5,000 | Development Department | Community Services |  | Secure Funding |
| 1 2 | Brookfield Enterprise Centre | Direction signage Braille and Tactile signage. Automated Doors | 2008 2008 | 2008 2008 | €300 €2,000 | Development Department | Community Services |  | Secure Funding |
| Priority | Location | Action & Sub-Tasks | Timeframe |  | Budgetary Estimate | Lead Department | Linkage with | Detail of progress to date / amendments to action. | Next Steps |
| 1 & 2 |  | Minor works to be carried out in 3 Centre’s. Bawnogue, Killinarden and Brookfield Enterprise Centres eg: doors, door handles, handrails etc. | Start 2008 | Completion 2009 | Cost unknown as a survey to cost such, needs to be carried out in the 3 Centres by a contractor. Allow €10,000 for work. | Development Department | Bawnogue, Killinarden and Brookfield Enterprise Centres |  | Secure Funding |

Total Funding Required €124,800

- REPORT SUMMARY

This document is South Dublin County Council’s plan to implement, in the County, the provisions of the Disability Act that apply to Local Authorities.  The vision underpinning this plan, is to provide disabled people with equality of opportunity to access and participate in the social, economic, environmental and cultural life of South Dublin County.

Part One of this plan provided demographic information regarding disabled people in South Dublin County.  The policy framework in which actions listed shall take place, both at National level and also at Council level have also been set out in Part One, sections two and three.  The approach to ensuring an accessible built environment, through the County Development Plan, Development Management Guidelines and Building Control regulations is set out in Part One, section four.  The final section in Part One sets out the approach to developing this plan, which included access auditing and a public and staff consultation process.

Part Two of this plan introduces the action matrices for Corporate Departments, including Customer Services, Human Resources and Information Technology.  These are followed by detailed matrices for the Housing Services, Roads and the Public Realm, Parks and Landscape Services, Cemeteries, Library and Community Services Departments.  As the timing of the request from the Department of the Environment, Heritage And Local Government (DEHLG) to the Council for this plan coincided with the implementation of existing inclusion and access improvement programmes underway by the Council, many of the actions listed here are already underway. The Council has proactively implemented actions to meet commitments under the Barcelona Declaration, a substantial Programme of Access Works was conducted in 2005-2007 funded under the National Disability Strategy and several measures and projects were undertaken by the Disability Liaison/Access Officer and the Social Inclusion Unit to address the inclusion needs of target groups, including disabled people, as part of a National Anti-Poverty Strategy.

Although the Council has always taken a progressive approach to ensuring an accessible County, the Disability Act Implementation Team that came together to develop this plan, found that there is much more to be done.  Therefore the team ensured that this plan is both realistic and achievable, and that there is a strategy to monitor and evaluate progress at both departmental and corporate level, so that the momentum is maintained. As many priority works as possible will be completed during the next two years.  Budgetary constraints will affect the implementation plan, however every department will keep an updated list of access works, updating this list as informed by the public, and will ensure that outstanding works are carried forward in plans until such time as they are all addressed.

At South Dublin County Council we welcome input from members of the public and other service providers and stakeholders to inform the development of our services.   With the assistance of partners in the County we are confident that the actions and commitments contained in this plan can be met.

We would like to thank the many members of the public and all local and national agencies who took the time to engage in our consultation process in order to make the goal of a universally accessible County a tangible reality.

http://www.brainhe.com/TheSocialModelofDisabilityText.html

An Assessment Officer, established under Section 8 of the Disability Act 2005, may refer a person with a disability to the Director of Services of the Housing Section of the relevant Housing Authority, if she or he deems it appropriate that the person, who has been identified as likely to require housing support, is made known to the housing authority as early as possible following the completion of the assessment under Section 8 of the Disability Act 2005. The Director of Services of the Housing Section may designate an appropriate official for the purpose of engaging / liaising with an Assessment Officer or a Liaison Officer. In such instances, the Assessment Officer shall notify the appropriate Liaison Officer that a referral to the Housing Authority has taken place. (www.environ.ie).