TDTF ‘Dial to Stop’ campaign

1800 220 220

Tallaght Drugs Task Force are developing a “Dial to Stop Drug Dealing” campaign.  The Tallaght, Dublin 24 area has been chosen by the National Drugs Strategy Team to participate in phase 1 of the National Campaign.

Duration: 6 weeks

Phase 1: October 6th – November 16th 2008

- Evaluation. The evaluation programme is finalised and we will undertaking:

Pre-campaign message testing and campaign strategy qualitative focus groups

Pre-campaign benchmark polling in all 12 selected areas in the first week of September

Post-campaign evaluation polling – one week after the end of each phase

A report on each phase will be presented within 3 weeks of the ending of the phase

Following the completion of phase three an overall evaluation report will be produced – deadline July 2009.

- Response Mechanisms. A diverse range of response mechanisms will be offered

a free phone number 1800 220 220

an option to talk directly to the gardai via the free phone number

Free texting

A dedicated website with an email form

- Response Management. A call centre providing 24/7 service will be contracted to handle response. The centre chosen must:

- handle the sensitive, extremely confidential and often abrasive nature of the calls and texts

- give up to the minute – ‘real time’ - reports to the chosen destination

- produce daily summary call received reports

- Be able to handle varying volume of calls - up to 300 per day if necessary.

All information supplied will be sent by the call centre to a gardai email address.

1. Aims & Objectives

- To generate calls to the number.

- To gather as much good information as possible.

- To further build up partnership approaches between local communities and the Gardaí in tackling drug dealing.

- To strongly promote the message that any level of drug dealing in local communities is unacceptable.

- To provide a mechanism for people living in such communities through which they can provide any information they have on such activity in a safe and non-threatening way.

2. Key Target Audiences & Insights

- Those currently or recently involved in drug dealing/drugs misuse.

- Direct Family members of those involved in drug dealing/drugs misuse.

- Those living in communities with active drug dealing.

We are segmenting these audiences into three age cohorts – adults, young adults and older children.

3. Campaign Messages

- Any level of drug dealing in local communities is unacceptable

- Second-hand information is good

- The number is free

- Callers/Responders can remain anonymous

- Callers/Responders may talk to Gardai if they want

- The group requesting the information is an alliance of local organizations under the auspices of xxx Drugs Task Force