Outline Proposal for Sustainable Energy Programme

Step 1: Create Resources

Format:

- Video /  Podcasts (Audio)

- Templates-Forms

- User Guides (Written)

Identify who will create these: internal to SDCC or external help required?

Topics  (Stages):

- Understanding your outgoings: How to read your bills (energy / fuel)

- Visual Audit: How to carry this out

  - Case Study, e.g. Clondalkin L.C.

- Reducing purchasing costs: Choosing your supplier

- Efficient Energy Use (Identifying savings)

Identify who will create these and where the information is retained?

Are these topics sufficient, can they be communicated in a clear and simple manner?

Step 2: Case Studies

- Clondalkin L.C.

- South Dublin Co Co

- Another (Private) Business

Identify private business with significant energy savings made through a similar process

Step 3: Focus Group Trial

Choose 4 local businesses that would participate in the programme and take them through the stages, and are willing to talk to others (be ambassadors for programme)

- Understanding bills

- Visual Audit

- Choosing Supplier

- Identifying savings

Minimum 2 businesses to 5 businesses to be identified and work through this process. Requires minimum 2 meetings with business

Step 4: Workshop Seminar

3 Months after programme begins, workshop is carried out (), with local businesses. Workshop includes practical elements to demonstrate how to

- Understanding bills

- Visual Audit

- Choosing Supplier

- Identifying savings

Resources available are launched, to ensure information is available on on-going basis.

September 2011, 3 – 4 Hours, energy saving the focus