## June 2011
Outcome 6: Business Sustainability and Development Programme
No | Objective | Action | Indicator | Timeframe | Responsibility | Interdependence with other actions
6.1 | 6.3 Series of seminars to promote the joint programme |  | Programme of seminars published | 31st May 2011 | South Dublin Chamber | Chamber linking to various projects in relation to water audits, energy efficiency, mobility, security and technology
1 | Understand who and what are available to programme | Identify SDCC staff and various initiatives currently taking place or in development | Introductory meetings held | 17th June 2011 | Andrea Carroll and Frank Nevin | Scheduling, and identification of appropriate projects
2 | Social Media for Businesses | Social Media Programme for SMEs - Social Media Means Business Conference | Conference Held | 8th June 2011 | Ronan Herron, Tommy Kavanagh, Andrea Carroll | Resources identified by SDubCoCo and promotion of conference.
|  | Social Media Programme for SMEs - Training Programme | Training Programme developed, with dates and actions in place | 17th June 2011 | Ronan Herron, Tommy Kavanagh, Andrea Carroll | Suitable programme for training to be developed, based on resources and availability
3 | SME Energy Costs programme | Develop interactive resources and training (including case studies and workshop). Identify actions and people associated with it. | Plan in place and human resources identified. Dates for initiatives identified | 1st July 2011 | Maire O'Sullivan, Eddie Conroy, Andrea Carroll | Resources identified and scheduling complete
6.4 | 6.4 Set up structure for one-on-one business advice and mentoring |  | No of business engaged in process | Ongoing | Frank Nevin and Peter Byrne | Resource in place
1 | Awareness | Make businesses aware of my appointment and potential for programme | Introductor email sent, and networking events attended | 10th June 2011 | Andrea Carroll | Scheduling of networking events and database details in place
2 | Understanding | Talk to businesses about the issues that they are facing to understand what their needs are | Survey businesses and talk to business people on this issue | 1st July 2011 | Andrea Carroll | Scheduling of events to access businesses, and survey response rate
3 | Consultation | Carry out one to ones with businesses in South Dublin Area to address their issues, advise them on resources available and options for improvement | One to One meetings carried out | Ongoing | Andrea Carroll | Availability

## July 2011
Outcome 6: Business Sustainability and Development Programme
No | Objective | Action | Indicator | Timeframe | Responsibility | Interdependence with other actions
6.1 | 6.3 Series of seminars to promote the joint programme |  | Programme of seminars published | 30th August 2011 | South Dublin Chamber | Chamber linking to various projects in relation to water audits, energy efficiency, mobility, security and technology
1 | Understand who and what are available to programme | Identify SDCC staff and various initiatives currently taking place or in development | Follow up on initial meetings held to identify potential programmes | 29th July 2011 | Andrea Carroll | Scheduling, and identification of appropriate projects
2 | Social Media for Businesses | Social Media Programme for SMEs - Training Programme | Training Programme developed, and initial carried out. Further dates planned | 22nd July 2011 | Ronan Herron, Tommy Kavanagh, Andrea Carroll | Suitable programme for training to be developed, based on resources and demand
3 | SME Energy Costs programme | Develop interactive resources and training (including case studies and workshop). Identify actions and people associated with it. | Plan in place and human resources identified. Dates for initiatives identified | 29th July 2011 | Maire O'Sullivan, Eddie Conroy, Andrea Carroll | Resources identified and scheduling complete
4 | Ensure business owners are aware of the information services available | Identify what information is currently available and where this can be accessed, and ensure clear access route for businesses | Effective and coherent information portal created and regularly maintained | 30th August 2011 | Georgina Byrne, Andrea Carroll | Overlap with existing services
5 | Communication with Businesses | Ensure that communication betweek businesses and the County Council is clear and effective | Review and Edit business relevent documents, including rates document, prior to publication | Ongoing | Maria Donohoe, Elaine Leech, Andrea Carroll | Identification of relevant documents
6.4 | 6.4 Set up structure for one-on-one business advice and mentoring |  | No of business engaged in process | Ongoing | Frank Nevin and Peter Byrne | Resource in place
1 | Awareness | Make businesses aware of my appointment and potential for programme | Introductory email sent, and networking events attended | 22nd July 2011 | Andrea Carroll | Scheduling of networking events and database details in place
2 | Understanding | Talk to businesses about the issues that they are facing to understand what their needs are | Ongoing discussions with business owners regarding their needs | 29th July 2011 | Andrea Carroll | Scheduling of events to access businesses, and survey response rate
3 | Consultation | Carry out one to ones with businesses in South Dublin Area to address their issues, advise them on resources available and options for improvement | One to One meetings carried out | Ongoing | Andrea Carroll | Availability

## August 2011
Outcome 6: Business Sustainability and Development Programme
No | Objective | Action | Indicator | Timeframe | Responsibility | Interdependence and Progress
6.1 | 6.3 Series of events to promote the joint programme |  | Programme of seminars published | 30th September 2011 | South Dublin Chamber | Chamber linking to various projects in relation to water audits, energy efficiency, mobility, security and technology
1 | Understand who and what are available to programme | Identify SDCC staff and various initiatives currently taking place or in development | Follow up on initial meetings held to identify potential programmes | Ongoing | Andrea Carroll | Connections made through Planning, Architects, Library Service, Communications and IT with potential programmes identified. This step is ongoing as other opportunities arise. Andrea spending some time every week in the County Council Buildings with staff
2 | Social Media for Businesses | Social Media Programme for SMEs - Training Programme | Training Programme developed, and initial carried out. Further dates planned | 30th September 2011 | Ronan Herron, Tommy Kavanagh, Andrea Carroll | 3 Initial training sessions carried out with good attendance. Hosted by Ronan Herron and assisted by Andrea Carroll. Good attendance for each, with further demand for introductory sessions. More advanced training will be carried out from September 2011, on specific social media issues.
3 | SME Energy Costs programme | Develop interactive resources and training (including case studies and workshop). Identify actions and people associated with it. | Plan in place and human resources identified. Dates for initiatives identified | 30th September 2011 | Maire O'Sullivan, Eddie Conroy, Andrea Carroll, Joe Fallon, Garry Warren | Resources identified and programme and IT under development. Currentl identifying potential companies for the case studies.
4 | Ensure business owners are aware of the information services available | Identify what information is currently available and where this can be accessed, and ensure clear access route for businesses | Effective and coherent information portal created and regularly maintained | 30th November 2011 | Georgina Byrne, Andrea Carroll, Siobhan Bermingham, Maria Donohue | Library Services currently identifying the information available and the levels of information to be disseminated. Format for communicating this currently being discussed
5 | Communication with Businesses | Ensure that communication between businesses and the County Council is clear and effective. | Review and Edit business relevent documents, including rates document, prior to publication | 31st August 2011 | Maria Donohoe, Elaine Leech, Andrea Carroll | Identification of relevant documents and understanding of how the Council is communicating with businesses. Andrea Carroll to advise on essentials of effective communication with businesses
6 | Create information resource for businesses in County | Identified gap in library services for business - significant resources available but under utilised by business. Create business hub | Creation of business hub, and relevant training offered | 30th September 2011 | Georgina Byrne, Andrea Carroll, Siobhan Bermingham, | Currently reviewing the resources available for business in the county libraries - and deficiencies and reviewing how best to encourage business owners to use this resouce
6.2 | 6.2 Set up structure for one-on-one business advice and mentoring |  | No of business engaged in process | Ongoing | Frank Nevin and Peter Byrne | Resource in place
1 | Awareness | Make businesses aware of my appointment and potential for programme | Communication ongoing with businesses through email, social media, networking and events and one to ones | Ongoing | Andrea Carroll | Chamber members are aware of this initiative and face to face meetings are happening. Using public events to reach businesses outside of the Chamber
2 | Understanding | Talk to businesses about the issues that they are facing to understand what their needs are | Ongoing discussions with business owners regarding their needs | 30th September 2011 | Andrea Carroll | Carry out survey of businesses to identify their needs and issues, as well as documenting the outcome of conversations
3 | Consultation | Carry out one to ones with businesses in South Dublin Area to address their issues, advise them on resources available and options for improvement | One to One meetings carried out | Ongoing | Andrea Carroll | A range of issues identified during one to ones. These issues are being considered when developing the sustainable business programme.

## September 2011
Outcome 6: Business Sustainability and Development Programme
No | Objective | Action | Indicator | Timeframe | Responsibility | Interdependence and Progress
6.1 | 6.3 Series of events to promote the joint programme |  | Programme of seminars published | 30th September 2011 | South Dublin Chamber | Chamber linking to various projects in relation to water audits, energy efficiency, mobility, security and technology
1 | Understand who and what are available to programme | Identify SDCC staff and various initiatives currently taking place or in development | Follow up on initial meetings held to identify potential programmes | Ongoing | Andrea Carroll | Connections made through Planning, Architects, Library Service, Communications and IT with potential programmes identified. This step is ongoing as other opportunities arise. Andrea spending some time every week in the County Council Buildings with staff
2 | Social Media for Businesses | Social Media Programme for SMEs - Training Programme | Training Programme developed, and initial carried out. Further dates planned | 30th September 2011 | Ronan Herron, Tommy Kavanagh, Andrea Carroll | 3 Initial training sessions carried out with good attendance. Hosted by Ronan Herron and assisted by Andrea Carroll. Good attendance for each, with further demand for introductory sessions. More advanced training will be carried out from September 2011, on specific social media issues.
3 | SME Energy Costs programme | Develop interactive resources and training (including case studies and workshop). Identify actions and people associated with it. | Plan in place and human resources identified. Dates for initiatives identified | 30th September 2011 | Maire O'Sullivan, Eddie Conroy, Andrea Carroll, Joe Fallon, Ronan Herron | Resources identified and programme and IT under development. 4 companies identified for case studies and dates in September agreed to carry out initial audits.
4 | Ensure business owners are aware of the information services available | Identify what information is currently available and where this can be accessed, and ensure clear access route for businesses | Effective and coherent information portal created and regularly maintained | 30th November 2011 | Georgina Byrne, Andrea Carroll, Siobhan Bermingham, Maria Donohue, Jim Nolan, Frank Nevin | Library Services currently identifying the information available and the levels of information to be disseminated. Format for communicating this currently being discussed
5 | Communication with Businesses | Ensure that communication between businesses and the County Council is clear and effective. | Review and Edit business relevent documents, including rates document, prior to publication | 30th September 2011 | Maria Donohoe, Elaine Leech, Andrea Carroll, Frank Nevin | Identification of relevant documents and understanding of how the Council is communicating with businesses. Andrea Carroll to review documents to ensure effective communications with businesses
6 | Create information resource for businesses in County | Identified gap in library services for business - significant resources available but under utilised by business. Create business hub | Creation of business hub, and relevant training offered | 31st October 2011 | Georgina Byrne, Andrea Carroll, Siobhan Bermingham, | Currently reviewing the resources available for business in the county libraries - and deficiencies and reviewing how best to encourage business owners to use this resouce. New suite of business books ordered. This programme will launch in October 2011
6.2 | 6.2 Set up structure for one-on-one business advice and mentoring |  | No of business engaged in process | Ongoing | Frank Nevin and Peter Byrne | Resource in place
1 | Awareness | Make businesses aware of my appointment and potential for programme | Communication ongoing with businesses through email, social media, networking and events and one to ones | Ongoing | Andrea Carroll | Chamber members are aware of this initiative and face to face meetings are happening. Using public events to reach businesses outside of the Chamber
2 | Understanding | Talk to businesses about the issues that they are facing to understand what their needs are | Ongoing discussions with business owners regarding their needs. Business survey completed. | 30th September 2011 | Andrea Carroll | Ongoing attendance at business events and networks to talk to businesses. Business requirements survey carried out and to be completed by 12th September 2011. Results will be compiled into report.
3 | Consultation | Carry out one to ones with businesses in South Dublin Area to address their issues, advise them on resources available and options for improvement | One to One meetings carried out | Ongoing | Andrea Carroll | 14 Face to Face meetings carried out to discuss business issues, and a range of issues identified. These issues are being considered when developing the sustainable business programme.