## Objective 1
Litter Management Plan 2011-2014 Implementation Plan
Themes | Objectives | Actions | Update/Progress to date quarter four October 2011 | Update/Progress to date quarter one January 2012 | Update/Progress to date quarter two April 2012 | Update/Progress to date quarter three June 2012 | Update/Progress to date quarter four October 2012
1 | Develop programmes on the basis of targeting the various litter categories, blackspots and illegal means of disposing of waste/refuse
E | Cigarette litter | Provide Stubbi at key events and talks | This is carried out on an ongoing basis
Target generators for enforcement
|  | Provision of Anti-Litter/Anti-graffiti Awareness grants | This is an annual awareness grant on the provision that the DOEHLG provides funding. Applications must meet the DOEHLG criteria
AC | Packaging | Recycling /Repak
C | Gum litter | National Gum litter task force campaign
|  | Provision of Anti-Litter/Anti-graffiti awareness grants | The 2011 grants are in the process of being diseminated to all successful applicants
Pr | Graffiti | Provision of Anti-Litter/Anti-graffiti awareness grants | The 2011 grants are in the process of being diseminated to all successful applicants
|  | Anti-graffiti workshops for community groups | Graffiti Wipeout Workshops. Community Groups - Whitechurch Green Clean Initiative, Balgaddy Working Together Group, Foxborough Maintenance Association Lucan, one to allocate
|  | Anti-graffiti workshops for schools | Graffiti Wipeout Workshops. Three for schools and four for community groups - Schools - St. Andrews N.S, Chapel Hill, Lucan – 05/05/11, Scoil Cnoc Mhuire S.N.S, Knockmore Avenue, Killinarden, Tallaght, 20.06.11, St Thomas Senior School, Jobstown, 11.5.11.
Mobile outlets
| Fast food | Anti-Litter posters to fast food take aways in the community | Cross departmental bye-law/policy on the erection of posters in the County is being developed
| Dog fouling | Dog fouling enforcement signs | Introduction of Dog Litter Stencils. Roll out of new signage in parks to reflect Parks Bye-laws 20ll and support enhanced enforcement of same by Park Rangers.
Parks Department to pilot a dog runs in Griffeen Valley Park
|  | Dog fouling awareness pop-up | This is developed and ready for loan to business, community groups, residents, schools etc
|  | Dog fouling enforcement stencils | Dog Wardens piloting stencil programme in Parks.
|  | Mutli-use bins will continue to be the receptacles for dog litter | Mutli-use bins will continue to be the receptacles for dog litter
|  | Introduction of Dog Litter Stencils for Footpaths in areas. | Dog Wardens to piloting stencil application in Parks.
| Poster signage | leaflet regarding the erection of signage in the County
|  | Cross departmental bye-law/policy on the erection of posters. | Presentation going to SPC regarding this matter.
| End of life vehicles | Advice on correct means of disposal regarding end of life vehicles is avialable on the Council website | Advice on correct means of disposal regarding end of life vehicles is avialable on the Council website
|  | Cleansing crew operate in South Dublin County Council to remove waste from area | Cleansing crew operate in South Dublin County Council to remove waste from area

## Objective 2
Litter management plan
Themes | Objectives | Actions | update/progress to date quarter four October 2011 | update/progress to date quarter one January 2012 | update/progress to date quarter two April 2012 | update/progress to date quarter three June 2012 | update/progress to date quarter four October 2012
2 | Develop a customer focused litter complaints procedure in order to deal effectively and efficiently with complaints | Promotion of Litter hotline Pilot Fix Your Street Customer Contact System Designated EPA Complaints Co-Ordinator | Environmental Enforcement Division established September 2011
Pr | Promote the customer care system to highlight litter complaints. | will be promoted on Council website and through social media
| Promote the use of the EPA’s anti Dumping hotline 1850-365121 | will be promoted on Council website and through social media | Link to EPA hotline on SDCC Environmental Homepage

## Objective 3
Litter management plan
Themes | Objectives | Actions | update/progress to date quarter four October 2011 | update/progress to date quarter one January 2012 | update/progress to date quarter two April 2012 | update/progress to date quarter three June 2012 | update/progress to date quarter four October 2012
3 | Continue to actively enforce litter pollution and waste management legislation, bye laws and standards | Ongoing Enforcement of Litter Pollution and Waste Management. Promote/Encourage Coporate Awareness of Litter Awareness and Enforcement Promote/Encourage Awareness of Information Systems as Enforcement Management Tool | Environmental Enforcement Division established September 2011
E | Implement a schedule of routine and non – routine inspections | Ongoing schedules of toutine and non-routine inspections by Litter Warden Service and Environmental Enforcement Officers
Pr | Continue to actively enforce the legislation with regard to litter pollution and waste management. | Ongoing Enforcement of Litter Pollution and Waste Management by Litter Warden Service and Environmental Enforcement Officers
Litter wardens operate in the County to investigate and prosecute illegal dumping and issue on the spot fines for litter offences..
Litter Wardens operate throughout the County on a seven day basis.
|  | Dog Wardens to introduce Dog Fouling Stencils on Footpaths. | Dog Fouling Stencils applied in Corkagh and Tymon Regional Parks
Litter wardens operate in the County to investigate and prosecute illegal dumping and issue on the spot fines for litter offences.If fines not paid the matter is brought to the District Court for prosceution. Promote/Encourage Coporate Awareness of Litter Awareness and Enforcement Promote/Encourage Awareness of Information Systems as Enforcement Management Tool
Litter wardens operate in the County to investigate and prosecute illegal dumping and issue on the spot fines for litter offences.If fines not paid the matter is brought to the District Court for prosceution.
Gardai have the power to issue on the Spot Fines for Littering.
|  | Extension of CCTV network throughout the county to support Enforcement of Litter Pollution Act. Promote/Encourage Coporate Awareness of Litter Awareness and Enforcement Promote/Encourage Awareness of Information Systems as Enforcement Management Tool | Six CCTV cameras installed at illegal dumping/antisocial blackspots throughout the county.
|  | Dog Wardens to introduce Dog Fouling Stencils on Footpaths. | Dog Fouling Stencils applied in Corkagh and Tymon Regional Parks
Provision of new litter bins to be considered as part of overall litter bin provision strategy for county.
|  | Introduction Dog Fouling Stencils on Footpaths. | Dog Fouling Stencils applied in Corkagh and Tymon Regional Parks
|  | The fine is €150 on the spot fine for littering under the Litter Pollution Act,and if brought to court the maximum fine can be up to €3000.00. Increase in Litter Fines to be considered as part of the review of the Litter Pollution Act | South Dublin County Council a Working Review Group. Inaugural meeting 13th October 2011
|  | There are currently 6 Litter wardens in the County. Investigate the potential role of additional Council Staff for purpose of Enforcement under the Litter Pollution Act. | Recommendation from HR Department awaited
|  | The fine is €150 on the spot fine for littering under the Litter Pollution Act,and if brought to court the maximum fine can be up to €3000.00 SDCC representation on Regional Working Group for purpose of informing review of the Litter Pollution Act | Inaugural meeting of Working Group scheduled 13th October 2011
|  | To be considered as part of review of Litter Pollution Act. | Inaugural meeting of Working Group scheduled 13th October 2011
|  | The fine is €150 on the spot fine for littering under the Litter Pollution Act,and if brought to court the maximum fine can be up to €3000.00 SDCC representation on Regional Working Group for purpose of informing review of the Litter Pollution Act | Inaugural meeting of Working Group scheduled 13th October 2011
A/C | Promote and enforce the waste bye-laws | Investigate the potential role of additional Council Staff for purpose of Enforcement under the Litter Pollution Act. | Recommendation from HR Department awaited
Ongoing by the Litter Warden Service.
|  | There is currently a litter data base to track fines, payment of fines, court prosecutions. Publish weekly Enforcement statistics in Local Newspapers | Local Newspapers Contacted
|  | There are currently 6 Litter wardens in the County.Litter Wardens are responsible for the investigation and prosecution of illegal dumping.The prosecution of serious offences through the Courts. The issue of on the spot fines for litter offences. Investigate the potential role of additional Council Staff for purpose of Enforcement under the Litter Pollution Act. | Recommendation from HR Department awaited
Litter Wardens are responsible for the investigation and prosecution of illegal dumping. Pro-active inspection of skip bags by Litter Warden Service to enhance Enforcement.
A person who engages in waste collection is required under section 34 of the Act to hold a waste collection permit.This matter is investigated by the Waste Enforcement Section.
|  | Spatial mapping of all blackspots throughout the County. Extension of CCTV Network. Target generators for enforcement. | Spatial Mapping in progress. Six CCTV cameras installed at illegal dumping/antisocial blackspots throughout the county.
Promote and enforce appropriate regulations regarding signage
| Develop a programme of enforcement warning signs | Prepare Signage Strategy for County. Cross departmental to implement bye-law/policy on the erection of posters. | Report submitted to SPC committees in September 2011.
| Publish litter enforcement statistics on a six monthly basis | Enforcement statistics published weekly Annual reporting to EPA under RMCEI Plan.
Prepare an operational plan for the litter management section with targets and standards of cleanliness incorporated.
Prepare an annual programme to highlight the responsibilities of sectors under the Litter Pollution Act
| Continue to work towards publicising details of successful prosecutions and enforcement activities within current data protection legislation while at the same time endeavouring to secure some change in the legislation which will enable a Name and Shame Approach | Publish weekly Enforcement statistics in Local Newspapers | Local Newspapers Contacted

## Objective 4
Litter management plan
Themes | Objectives | Actions | update/progress to date quarter four October 2011 | update/progress to date quarter one January 2012 | update/progress to date quarter two April 2012 | update/progress to date quarter three June 2012 | update/progress to date quarter four October 2012
4 | Improve the litter disposal systems available to the public | Procedure in place for the identification of area's requiring installation of new bins or replacement bins. Area's are examined by the litter wardens and the cleansing engineer to assess the level of litter generation and the requirement for a litter bin. priority is given to those area's close to shops,school and bus stops. Exisitng collection routesare examined with a view to expaning the collections, this is subject to staff resources. | An installation programme for new and replacement bins resumed in summer 2011. Initially the list of priority locations for litter bins is being addressed.
Pr, Pa, C | Continue to research litter disposal system and prepare a programme to update existing units | Cleansing staff and litter wardens to examine areas for installation of new and replacement bins. | Lists for approved new bins and replacement bins are maintained by the Council's cleansing section.
|  | Council to survey existing services | An installation programme for new and replacement bins resumed in summer 2011. Initially the list of priority locations for litter bins is being addressed.
|  | Litter bins emptied Monday-Friday by Cleansing Staff on 5 routes. | Litter bins are emptied are per schedule which is guided by volume of waste.
|  | Cleansing staff to install replacement bins.Litter wardens and Cleansing staff to review locations for inclusion on list. | Litter bins installed in numerous locations following resumption of programme.
|  | Staff to review locations and assess the requirement for the bin.. | installation programme for new and replacement bins resumed in summer 2011 priority list of bins to be installed.
|  | Provision of new litter bins to be considered as part of overall litter bin provision strategy for county having regard to resources available to service them. | It is council policy to not have litter bins in parks
|  | Survey to be undertaken of the existing litter bins throughout the county.Data to be mapped for information purposes. | This survey is currently being undertaken by the cleansing section staff
|  | The weight of waste material collected in the litter bins each month is recorded. | Consider publishing monthly weights recorded in litterbins.
|  | Provision of new litter bins to be considered as part of overall litter bin provision strategy for county having regard to resources available to service them. | It is council policy to not have litter bins in parks
|  | Cleansing staff to assess the requirement in such areas based on waste generation. | It is council policy to have litter bins in areas that are waste generators. Discussions to be convened with private transport providers with respect to litter management.
Cleansing staff to assess the requirement in such areas based on waste generation.
|  | There is currently a kerbside collection system in place for householders in the County. There is no charge on this collection and customers are requested to dipose of their recyclable materials in a responsible manner in these bins | point 2: There general experience supports that bins at bring banks increase dumping
Litter bins are 75 litres in size and are standard across the county for maintenance purposes.
|  | Cleansing staff to assess the requirement in such areas based on waste generation. Bins collected Monday to Friday. | waste in bins are empty are per schedule which is guided by volume of waste
Provision of new litter bins to be considered as part of overall litter bin provision strategy for county having regard to resources available to service them.
|  | Bins emptied Monday-Friday. | Resources to address seven day collections are not available.
|  | Litter bins emptied Monday-Friday by Cleansing Staff on 5 routes.Resources are not available to implement 7 day service. | Resources to address seven day collections are not available.
Areas assessed by Cleansing staff and litter wardens to determine waste generators and the the requirement for bins in these areas
| Instigate a continuous improvement programme. | The Council Cleansing and Operations crew collect dumped waste from areas as promptly as possible. | The staff operate to schedules prepared using information received from litter wardens, elected members, member sof the public and Council staff.
The Council Cleansing and Operations crew collect dumped waste from areas as promptly as possible.
| Identify pathways towards eliminating causes and adjusting litter bin locations | Procedure in place for the identification of area's requiring installation of new bins or replacement bins. Areas are examined by the litter wardens and the cleansing engineer to assess the level of litter generation and the requirement for a litter bin. Priority is given to those areas close to shops,school and bus stops. Exisitng collection routes are examined with a view to expanding the collections, this is subject to staff resources. | installation programme for new and replacement bins resumed in summer 2011 priority list of bins to be installed.
| Work with Transport service provider towards eliminating litter at their service areas | Discussions to be convened with private transport providers with respect to litter management.
| Working with local businesses on the provision & servicing of bins | under the current litter act business are required to maintain an area of 100m outside the premises of their business

## Objective 5
Litter management plan
Themes | Objectives | Actions | update/progress to date quarter four October 2011 | update/progress to date quarter one January 2012 | update/progress to date quarter two April 2012 | update/progress to date quarter three June 2012 | update/progress to date quarter four October 2012
5 | Expand the recycling opportunities within the County
Pr | Implement the recommendations of the Recycling strategy. | The Council's community recycling strategy is currently being reviewed
A/C |  | Bring Banks already provided at main car parks to public parks.
Pa |  | There is an existing kerbside collection of dry recyclables to households in the County, bottle banks and textile banks are located throughout the county and the Council operates the Civic Amenity at Ballymount to receive materials. | Survey of all recycling units being undertaken by Council with view to mapping data and utilising data to implement improvements to the current arrangements.
|  | There are recycling bring banks throughout the county.Tender for Textile Banks to be implemented. | Servicing of textile banks is due to tendered in the coming weeks.
|  | Information relating to Recycling Facilities is available on the South DublinCounty Council Website and lists materials accepted, locations. Information on recycling facilities in the Dublin Region is available on Dublinwaste.ie | Council to utilise Civic Amenity in its Halloween Strategy to remove unwanted waste.

## Objective 6
Litter management plan
Themes | Objectives | Actions | update/progress to date quarter four October 2011 | update/progress to date quarter one January 2012 | update/progress to date quarter two April 2012 | update/progress to date quarter three June 2012 | update/progress to date quarter four October 2012
6 | Continue to monitor and review road cleansing service in order to provide an improved service.
C, Pr | Monitor and review existing contract and produce a report to include measures to provide an improved service if required. | The Council Cleansing Service operates throughout the county to clean fly tipping, collect material from litter bins, instigate the removal of dead animals and general litter removal.
|  | Road sweeping schedule available on Council Website for information. | Provide information on the link to Residents associations and Community groups.
|  | Road Sweeping Schedule determined by Contractor to ensure regular sweeping of Motorways, Dual Carriageways, Local Roads, Estates. | The current road sweeping contract expires at the start of February 2012. Advertisements for the procurement of a new service contract are due to be placed on Monday October 10th. It is proposed that the new service to be procured will give an improvement in the level of service which is currently achieved.
|  | Cleansing Services operate Monday to Friday. In emergency cases staff are on call . | Resources not available for 7 day working.
|  | The Council Cleansing Service operates throughout the county to clean fly tipping, collect material from litter bins, instigate the removal of dead animals and general litter removal. | The Council Cleansing staff operate Monday to Friday; Roadsweeping is operational 7 days a week subject to Road status.
|  | Road sweepers operate on daily basis sweeping Dual carriageways, Local roads, Housing estates and Industrial estates. | Roadsweeping is operational 7 days a week subject to Road status.
|  | The Council Cleansing Service operates throughout the county to clean fly tipping, collect material from litter bins, instigate the removal of dead animals and general litter removal from all areas. | Consideration to be given for inclusion in new road sweeping tender.

## Objective 7
Litter management plan
Themes | Objectives | Actions | update/progress to date quarter four October 2011 | update/progress to date quarter one January 2012 | update/progress to date quarter two April 2012 | update/progress to date quarter three June 2012 | update/progress to date quarter four October 2012
7 | Develop a litter management programme for designated urban areas within the County – Tallaght city, Clondalkin town centre and other designated areas | As part of the years work there is a number of operations and campaigns aimed at reducing the level of littering in the county thereby reducing the resource required to clear up after the offenders. The litter management programme for areas is summarised as follows: • Dedicated cleansing staff target central locations using handcart, green machine and litter bin operatives • Dedicated litter warden for the each of the areas with specific duties to target the urban areas through routine daily patrols and inspections, including on weekends • Road sweeping and gulley cleaning provided by contract on a scheduled basis • Continued expansion of the network of litter bins in these areas • Additional resources are regularly deployed to these areas by the Operations Unit management as required. These resources undertake litter picking of public open spaces and within residential areas. | The Litter Management Plan will be reported on quarterly to each of the Area Committee Meetings. Actions taken in each of the towns and villages or within specific locations will be reported on to the relevant area committee as the need arises.
Pr | Prepare a detailed operation programme to handle the specific demands of key town centres and other designated areas. | Road sweepers operate on daily basis sweeping Dual carriageways, Local roads, Housing estates and Industrial estates. | New Street sweeping tender to be implemented following tender for operation.
C | Set targets and standards for the maintenance programme in such areas. | The Council works towards achieveing a litter free County on an ongoing basis
Pa | Review standards in each area on a monthly basis |  | Publically published by IBAL
A/C
E

## Objective 8
Litter management plan
Themes | Objectives | Actions | update/progress to date quarter four October 2011 | update/progress to date quarter one January 2012 | update/progress to date quarter two April 2012 | update/progress to date quarter three June 2012 | update/progress to date quarter four October 2012
8 | Prepare litter management, education and awareness programmes that promote community and business involvement, community identity and responsibility, personal responsibility, youth activity etc.
Pr | Organise a green school network to highlight litter and its negative effect. | green schools network seminar provided to secondary and primary schools every year | seminar taking place on 4/10/2011
A/C | Arrange a school competition with an emphasis on the elimination of litter | Anti-litter/Anti-graffiti Schools Competition carried out every year | this competition is currently with schools and has a deadline of 28/10/2011
Pa | Encourage all schools to register for the green schools programme | all schools are contacted with a schools newsletter that informs them about the green schools programme | 1st Newsletter of 2011 - 2012 school year has been sent out to school in September. News letter can be viewed on www.sdcc.ie
All scools offered Environmental awareness talks on green schools programme
|  | All schools offered support through out the green schools programme. In addition all young people are environmental awareness support through www.sdcc.ie | this is carried out through the green school programme
In 2011-2012 school year two Secondary Schools from the County taking part in Neat Streets - the pilot anti litter programme for secondary schools. It is linked to the Green-Schools programme and involves students working with their communities to develop initiatives to tackle litter in their local areas.
| Prepare a litter awareness training programme for staff | a programme regarding litter awareness will be developed and provided to Environmental staff
Awareness talks are provided on an ongoing basis to schools and community centres
| Develop a package of supports including notices, leaflets and advertising to highlight the obligations of dog owners. | Dog fouling enforcement signs
|  | Dog fouling leaflet | responsible dog ownership leaflet developed and available online & in hard copy
|  | Dog poop-scoopers | available to the public
|  | Dog fouling awareness pop-up | responsible dog ownership stand developed and available on a loan system to businesses, community groups, residents associations and schools
|  | Dog fouling enforcement stencils | Dog Wardens are piloting this scheme in Parks.
Dog fouling awareness event
| Continue to promote anti litter campaigns. | All anti-litter campaigns are promoted on a continual baisis  National Spring Clean  Gum Litter Taskforce  Beautiful South Dublin County  Responsible Dog Ownership – Dog Fouling  Litter and the Law Leaflet | The beautiful South Dublin County Competition is currently being organised.
this is carried out on an ongnoing basis through anti-litter awareness talks and visits
|  | this is carried out on an ongonig basis | through the green school programme
Prepare a survey to highlight the attitude of various sectors to litter in the County and develop a programme with representatives of communities, groups and businesses to implement the goal of the plan - South Dublin County Council – a litter free County.
| Encourage community involvement in the achievement of a litter free County | provision of anti-litter/anti-graffiti talks
|  | provision of anti-litter/anti-graffiti events | Graffiti Wipeout Workshops. Three for schools and four for community groups - Schools - St. Andrews N.S, Chapel Hill, Lucan – 05/05/11, Scoil Cnoc Mhuire S.N.S, Knockmore Avenue, Killinarden, Tallaght, 20.06.11, St Thomas Senior School, Jobstown, 11.5.11.
|  | provision of anti-litter/anti-graffiti grants to local community groups | Graffiti Wipeout Workshops. Community Groups - Whitechurch Green Clean Initiative, Balgaddy Working Together Group, Foxborough Maintenance Association Lucan, one to allocate
|  | Beautiful South competition | The beautiful South Dublin County Competition is currently being organised.
|  | Eco-week | Eco week has been set for 23-27th April 2012
community clean-up guidelines
awareness talks are provided on an ongoing basis
The Council services are actively promoted through www.sdcc.ie, facebook and twitter
community clean-up guidelines
|  | awareness talks are provided on an ongoing basis | Graffiti Wipeout Workshops 2011 Community Groups - Whitechurch Green Clean Initiative, Balgaddy Working Together Group, Foxborough Maintenance Association Lucan, one to allocate
Promote the use of Community Clean up Guidelines
Litter wardens operate in the County to investigate and prosecute illegal dumping and issue on the spot fines for litter offences. Council promotes Community Clean Up Guidelines for interested parties to get involved in maintaining their areas.
|  | Council promotes Community Clean Up Guidelines for people to organise clean ups in the area. | Council to provide materials to Community centres to distribute to groups undertaking clean ups in the area. Council to collect and dispose of waste material collected.
Engage with the organisations represented on the County Development Board to promote a litter free County as agreed in Priority Action 23
| Promote the Social Credit System | organisations are encouraged to take part in the Social Credit scheme

## Objective 9
Litter management plan
Themes | Objectives | Actions | update/progress to date quarter four October 2011 | update/progress to date quarter one January 2012 | update/progress to date quarter two April 2012 | update/progress to date quarter three June 2012 | update/progress to date quarter four October 2012
9 | Encourage active participation in Anti Litter Campaigns
Pr, Pa, A/C | Promote anti litter campaigns i.e. National Spring Clean, | promote all anti-litter campaigns on a continual basis | the 2011 Anti-litter/anti-graffiti awareness grant scheme is currently being distributed to all successful applicants. This grant assists anti-Litter and Anti-Graffiti-Awareness Initiatives that seek to promote public awareness and education in relation to litter and/or graffiti. Schools – schools in Lucan Sarsfield Park area were targeted with Anti Litter Talks in May 2011 when the area was idenitified under the Public Realm as having a litter problem.
| Promote participation in competitions such as Beautiful South Dublin County. | Review Beautiful South Dublin County in order to generate more participation | The beautiful South Dublin County Competition is currently being organised.
| Promote the anti litter campaigns using the website and social media. | All anti-litter initatives are promoted via the website and social media | currently promoting: www.fixyourstreet.ie, community clean-up guidelines & the Halloween initiative
the 2011 Anti-litter/anti-graffiti awareness grant scheme is currently being distributed to all successful applicants. This grant assists anti-Litter and Anti-Graffiti-Awareness Initiatives that seek to promote public awareness and education in relation to litter and/or graffiti. this was advertised in the local media, on www.sdcc.ie, on facebook and twitter
| Encourage the participation of the communities, schools, groups and businesses in anti-litter campaigns and the use of the Community Clean up Guidelines | provision of anti-litter/anti-graffiti talks, distribution of Community Clean up Guidelines | Graffiti Wipeout Workshops 2011 Community Groups - Whitechurch Green Clean Initiative, Balgaddy Working Together Group, Foxborough Maintenance Association Lucan, one to allocate Graffiti. Wipeout Workshops. Three for schools and four for community groups - Schools - St. Andrews N.S, Chapel Hill, Lucan – 05/05/11, Scoil Cnoc Mhuire S.N.S, Knockmore Avenue, Killinarden, Tallaght, 20.06.11, St Thomas Senior School, Jobstown, 11.5.11 The following schools in the Tallaght area were contacted in september regarding the provision of Anti Litter Talks.These schools are near open spaces which were idenitified under the Public Realm as having a litter problem: St. Mark's J.N.S St. Mark's S.N.S St. Anne's N.S St. Brigid's J.N.S St. Aidan's N.S Scoil Chaitlín Maude Sacred Heart S.N.S Sacred Heart J.N.S Scoil Cnoc Mhuire S.N.S Scoil Cnoc Mhuire J.N.S St. Aidan's Community School. Killinarden Community School. St. Mark's Community School.
provision of anti-litter/anti-graffiti events, Social Credits System
|  | provision of anti-litter/anti-graffiti grants to local community groups, Promote Community Clean up guidelines | the 2011 Anti-litter/anti-graffiti awareness grant scheme is currently being distributed to all successful applicants. This grant assists anti-Litter and Anti-Graffiti-Awareness Initiatives that seek to promote public awareness and education in relation to litter and/or graffiti.
|  | Beautiful South competition, Facebook, Social Credits | The beautiful South Dublin County Competition is currently being organised.
Tidy Towns
| Publicise and highlight the results of the anti litter campaigns. | Publicity and highlighting of anti litter campaigns is carried out on an ongoing basis

## Objective 10
Litter management plan
Themes | Objectives | Actions | update/progress to date quarter four October 2011 | update/progress to date quarter one January 2012 | update/progress to date quarter two April 2012 | update/progress to date quarter three June 2012 | update/progress to date quarter four October 2012
10 | Develop a communications programme to promote a litter free County – including the promotion of the use of www.southdublin.ie and www.dublinwaste.ie
Pr | Make use of the different medias | Awareness on Graffiti in community via newsletters, news media and Internet campaigns is carried out through out the year eg green times for schools and the Rapid newsletter for rapid area's | this is carried out on a continual basis
A/C | - Newsletter
E | - Website
Pa | - Notices in local press
C | - Press release
- Photo shoots
| - Social Media | Facebook is used for awareness campaigns | this is carried out on a continual basis
|  | Twitter/social media is used for awareness campaigns | this is carried out on a continual basis
|  | provision of anti-litter/anti-graffiti talks, distribution of Community Clean up Guidelines/social credits and Environmental awareness | this is carried out on a continual basis
|  | due to data protection legislation name and shame is no longer permissable | due to data protection legislation name and shame is no longer permissable
|  | the possibility of advertising in Tallaght stadium to promote keeping the County tidy will be investigated | this will be explored
| Highlight the anti litter message | The anti-litter message is highlight on a continual basis via different initiatives, camping and media
|  | dog enforcement stencil initiative | Dog Wardens to piloting stencil application in Parks.
Prepare a yearly programme to target the various sectors within the County
|  | Halloween and Christmas anti-litter/recycling intatives are run each year | Halloween Bulbs not Bonfires Initiative has begun
| Develop the litter section of the website to ensure up to date information and constant development and improvement. | This is currently under review

## Objective 11
Litter management plan
Themes | Objectives | Actions | update/progress to date quarter four October 2011 | update/progress to date quarter one January 2012 | update/progress to date quarter two April 2012 | update/progress to date quarter three June 2012 | update/progress to date quarter four October 2012
11 | Optimise the application of available technology in the enforcement and prevention of litter
Pr | Deploy available technology such as CCTV where possible
E |  | CCTV considered to be essential for monitoring bring banks to reduce incidents of dumping and vandalism and to support prosecutions. | The project of CCTV has been identified under public realm and CCTV has been installed at Ballyowen shopping centre bring banks, Bottle Banks Drumcairn Avenue, Ard Mor Court/Drive, Kilcronan Court, Saint Mark’s Avenue, with a control room at County Hall. A Rapid Deployment Camera was also purchased as part of this programme to optimise enforcement through out the County
A/C
Pa |  |  | survey of bring banks through out the County nearing completion
|  | Mobile CCTV employed in Dublin Mountains under P.U.R.E. regional initiative to combat continuous dumping at specific locations | Dublin Mountain parternship considering installation of CCTV cameras in carparks at Cruagh, Tibradden and Hellfire carparks in the Dublin Mountains.
This is being explored in context of the Rapid Deployment Camera

## Objective 12
Litter management plan
Themes | Objectives | Actions | update/progress to date quarter four October 2011 | update/progress to date quarter one January 2012 | update/progress to date quarter two April 2012 | update/progress to date quarter three June 2012 | update/progress to date quarter four October 2012
12 | Utilise systematic data analysis systems to monitor and plan Litter management and decision making
Pr | Continue to participate in and utilise the National Litter Monitoring Survey to ensure informed decision making
A/C | Continue to monitor the reports from IBAL | Spatial Mapping of litter dumping blackspots throughout the county. | Progress ongoing by Spatial Mapping Team South Dublin County Council
E | Review data on a quarterly basis | Litter statistics are reviewed at a weekly litter enforcement meeting | Litter statistics are reviewed at a weekly litter enforcement meeting
| Update operational plan and actions based on review | updates are carried out based on litter enforcement meeting reviews | updates are carried out based on litter enforcement meeting reviews
| Highlight & actively measure SDCC´s position in national litter survey on SDCC.ie - act as an encouragement to improve or maintain position - foster competitive pride. | publically published IBAL | Published in national media by IBAL

## Objective 13
Litter management plan
Themes | Objectives | Actions | update/progress to date quarter four October 2011 | update/progress to date quarter one January 2012 | update/progress to date quarter two April 2012 | update/progress to date quarter three June 2012 | update/progress to date quarter four October 2012
13 | Continue to research and implement best practice models
Pr | Examine initiatives in other local authorities and countries | this is carried out as need arises
E | Instigate a programme of continuous improvement with regard to litter management and control | this is carried out on a continual basis | this is carried out on a continual basis
A/C
C
Pa

## Objective 14
Litter management plan
Themes | Objectives | Actions | update/progress to date quarter four October 2011 | update/progress to date quarter one January 2012 | update/progress to date quarter two April 2012 | update/progress to date quarter three June 2012 | update/progress to date quarter four October 2012
14 | Ensure the provision of a litter management plan for all major events
Pr, A/C, | Communicate the need for a litter management plan for all major events and enforce the conditions. | included in licence Agreement | included in licence Agreement
Need to identify the events where this should apply and target accordingly

## additional comments
additional comments | Actions | update/progress to date quarter four October 2011 | update/progress to date quarter one January 2012 | update/progress to date quarter two April 2012 | update/progress to date quarter three June 2012 | update/progress to date quarter four October 2012
Area of Corkagh :Removal of cottages in area of Corkagh Park adjacent to the Old Mill to help reduction in litter and dumping. | Cottages are protected structures in Co Dev Plan and so cannot be touched. | Cottages are protected structures in Co Dev Plan and so cannot be touched.
stop planting trees that shed leaves along motorway | No action proposed
anti-litter enforcement stickers for bins |  | litter bins are being assessed for the use of fine warnings
Keep the Clondalkin Recycling Initiative going | CCRI mentioned in LMP introduction | CCRI mentioned in LMP introduction.CCRI are also by the Council
one free trip to the dump each year | this will occure in conjunction with blubs not bonfires intative | leaflet to be distributed to all households in the County for one visit per household to Civic Amenity on October Bank holiday weekend
We propose that the Council do a cost benefit analysis on withdrawal of the waiver against the price of dealing with the consequent increase in illegal dumping, with a view to re-introducing a waiver supported by SDCC. |  | Waiver system being dealt at a national level
We would like Clondalkin Village to be a designated Poster-Free area | presentation going to SPC in septebember regarding this topic | this matter is currently being looked at by an SPC working group
elections both Local and National, that each candidate should pay approx €2,000 per candidate towards the removal of the plastic ties from lamppost
Reinstatement of the Junk Collections service to counteract illegal dumping. | No junk collections undertaken since 2008. | other initiatives have replaced the junk collection eg free day at civic amenity over bank holiday weekend
Enforce the law as regards fly tipping and dumping | There are currently 6 Litter wardens in the County.Litter Wardens are responsible for the investigation and prosecution of illegal dumping.The prosecution of serious offences through the Courts. The issue of on the spot fines for litter offences.
Review the number & workload of the litter wardens & environment dept against the litter mgt needs of the county- actively engage with changes to work practices where necessary to ensure the right resources are targeting the right areas to ensure Tallaght is a litter free zone. | There are currently 6 Litter wardens in the County.Litter Wardens are responsible for the investigation and prosecution of illegal dumping.The prosecution of serious offences through the Courts. The issue of on the spot fines for litter offences.
part time litter officers, aswell as the full time ones. These people could act at weekends and bank holidays in chasing litters. Businesses should be fined for persistant littering. | There are currently 6 Litter wardens in the County. | this is being examined in relation to IR issues
more checkups on litters, go through the rubbish & fine them. | There are currently 6 Litter wardens in the County.Litter Wardens are responsible for the investigation and prosecution of illegal dumping.The prosecution of serious offences through the Courts. The issue of on the spot fines for litter offences.
Possible liaison with Tallaght Court to have people who are given community service assist cleansing/graffiti crews; | Probation service | works currently carried out by probation service
Use Operations staff to provide junk collections; | The Council does not undertake Junk Collections. The last collections were carried out in 2008. | Junk collection has been replaced by other initiatives
Litter be picking before grass cutting | Operations Staff to Co-ordinate with Parks Staff when scheduling grass cutting operations. | Operations crew in attendance prior to grass cutting has facilitated Parks Department maintain grass cutting schedule.
The Environmental SPC should be involved in any review of the road cleansing service. While it is noted that the council recently renegotiated a reduced cost for the current road-sweeping contract whilst retaining the same level of service, there remains significant concerns in many quarters that the level of service currently on offer is not satisfactory. | the Environmental SPC is a strategic policy committee and is not therefore a forum for operational matters | this matter is currently being looked at by an SPC working group
The Council could create Litter Free Zones starting off with the town centres. | The Council works towards achieveing a litter free County on an ongoing basis
Supply Car-Tidy for cars. | Provide Car tidy at key events and talks | Car tidy's are provided at key events and talks
Council staff to actively intervene into estates that do not have a history of cleaning-up | Parks Staff having been doing this for years and recent support from Operations Crew in Environment has made significant impact in West Tallaght, North Clondalkin and South West Clondalkin. | ongoing response
Consultation Days for the Draft Litter management plans: Increased public awareness for future litter management plans | report goes to area members | report goes to area members
Access to the schedule for Clean ups in the community outside school | Street cleaning schedule available on the website | Street cleaning schedule available on the website
More Recycling Bins for school. | recycling bins available through waste providers | recycling bins available through waste providers
Define, launch & champion a local initiative to work alongside the "Tidy Districts" to promote and give visibility to what SDCC believe is best practice for a residential area & a business - this should include tangible metrics & SDCC.ie should be used to promote & measure local objectives to establish of improve performance | Beautiful South Competition | The beautiful South Dublin County Competition is currently being organised.
Run a competition for sports teams to clean up their local areas and provide prizes of a new team kit (maybe with Anti-Litter logos); | this will be examined
Community groups and members of the public be encouraged to ask for parks and the litter service.