Tallaght Area Committee

Meeting of the Tallaght Area Committee -  26/03/12

Item No.  H-I (12) - Taking in Charge Listing - Roads and Services

No. of Houses	Estate	Locatio	Developer

Works Outstanding

C	ESTATES WHERE TAKING IN CHARGE RECOMMENDATIONS ARE BEING PREPARED:

176	Ferncourt (Phase 1 & 2)	Ballycullen	Maplewood

Homes

Developer has completed surface works and

most drainage works as identified on

remedial list. Inspection by environmental

services identified remaining issues which

have been remitted to the developer for

attention. These issues have been dealt with

and the estate is ready to be taken in charge.

C1	ESTATES WHERE ROADS ONLY - HAVE BEEN TAKEN IN CHARGE

498	Sundale (Phase 1 - 6)	Tallaght	Kelland Homes

Ltd.

Roads TIC on  8th March, 2004

Underground services not yet recommended

for TIC. Council met Kelland Homes in

Jan 2012 and advised that wayleave will be

needed for water mains. Drainage survey

and revised drawings submitted and being

checked. Report due on underground

services and to be provided to the developer

D	ESTATES WHERE TAKING IN CHARGE WORKS ARE STILL OUTSTANDING

588	Carrigmore	Fortunestown 	Devondale Ltd.

Apartments and duplexes are private and 	Lane

under 	Management Company. Drainage

not to be taken in charge. Only roads,

footpaths, public lighting for taking in

charge. SDCC has clarified surface works

required, however CCTV and as

constructed drawings have not been

received which prevents establishing full

scale of works needed to services and

150	DeSelby	Tallaght	Kelland Homes

Ltd.

Meeting with Kelland in Jan 2012 identified

that the surface works are complete.

The Developer is preparing as Built

Drawings & CCTV to facilitate next stage

which is review of underground services.

No. of Houses	Estate	Locatio	Developer

Works Outstanding

40	Maplewood Estate	Tallaght	Maplewood

Homes Ltd

Environmental Services identified issues

with 	drainage and notified developer.

CCTV survey 	of underground services

reviewed and Building Control have sought

revised CCTV as evidence of proper

completion of underground services.

361	Marlfield	Tallaght	Durkan New

Homes

Marlfield is a mixed residential

development, mostly private and a

Management Agreement for the

development has been submitted.

The developer has not submitted a

completed taking in charge request in that

CCTV surveys of underground services

have not yet been received.

The lack of CCTV prevents SDCC

progressing with analysis of underground

services. As constructed drawings were

remitted to the developer as they were

not accurate.

The other significant issue in the

development is the standard of public

lighting and the Council have requested

a meeting with the developer to progress

these issues.

4	Sylvan Avenue	Kingswood	Mondale

Const. Ltd.

Final inspection to be carried out, minor

surface works were remaining at last

inspection. Taking in charge drawings and

schedule being prepared by building control.

230	Verschoyle (Phase 1)	Tallaght	Kingscroft

Developments

Drainage cannot be taken in charge as it

drains into a private drain.

Following a claim on the bond for the

development, Kingscroft returned to site,

and Environmental services have reviewed

the issues and developer has completed the

items required.

Kingscroft contacted the Council this

month (March) to confirm the remaining

surface works needed and to agree a

schedule to finalise them as soon as

possible. Joint inspection of development

to be arranged.

G	ESTATES UNDER CONSTRUCTION:

519	Elder Park Rise	Killinarden	Kelland

Commencement of works June 2010 on 9

show house units only completed but works

have now ceased and site has been secured.

The planning permission does not expire

until March 2013 and a permission amending

part of the development was granted in late 2010.

No. of Houses	Estate	Locatio	Developer

Works Outstanding

Pairc An Tsioda	Silken Park	Durkan New

Homes

Development is under construction, taking

in charge premature and not offered yet for

taking in charge by developer.

J	ESTATES WHERE BOND IS BEING CLAIMED

Arena Development	Whitestown 	P E Elliott

On May 19, 2011, KPMG were appointed 	Way

receivers for PE Elliott. The Council have

surveyed surface works and tests etc

required by receiver to bring the

development to TIC standard.

It is hoped that if progress can be made

with the bondholder on the Priorsgate

development that matters can then focus

on Arena, Belgard Square West and

Tallaght Cross which are all secured with

same bondholder.

491	Belgard Square West/Cookstown Way	Tallaght	Dez

Developments

Private apartment development.

Defects list compiled and claim on bond lodged.

It is hoped that if progress can be made

with the bondholder on the Priorsgate

development that matters can then focus

on Arena, Belgard Square West and

Tallaght Cross which are all secured with

the same bondholder.

210	Priors Gate	Tallaght	P. Elliott

Apartments. Private development.  Request

to take bridge in charge.The developer

entered receivership at end of May 2011

(KPMG) and the Council has placed a claim

on the bond for remaining works. In

respsonse the bondholder has advised they

do not intend to engage their contractor

and are now in discussions with SDCC to

agree value of works same to achieve

completion. The Council has remitted its

costed list of works which are being

surveyed by bondholder. It is hoped that if

progress can be made with the bondholder

on this development that matters can then

focus on Arena, Belgard Square West and

Tallaght Cross which are all secured with

the same bondholder.

No. of Houses	Estate	Locatio	Developer

Works Outstanding

387	Tallaght Cross	Tallaght	Keenbury

Properties Ltd.

Private apartment development. Company

in receivership, limited areas to be taken in

charge and meeting being arranged with

receiver for April 2012. Simultaneously

SDCC issued a defects list and claim on

bond was submitted to bond holder.

It is hoped that if progress can be made

with the bondholder on the Priorsgate

development that matters can then focus

on Arena, Belgard Square West and

Tallaght Cross which are all secured with

the same bondholder.