Clondalkin Area Committee

Meeting of the Clondalkin Area Committee -

Item No.  H-I ( 10 ) - Taking in Charge Listing - Roads and Services

No. of Houses	Estate	Location	Developer

Works Outstanding

D	ESTATES WHERE TAKING IN CHARGE WORKS ARE STILL OUTSTANDING

Aylmer Heath	Newcastle	Knightstone

Development

The development commenced in late 2006,

with the stated proposal for the completion of

80 units. Permission expired in August 2010

and only 49 of overall total permitted

development of 112 were completed.

Following the issue of an enforcement warning

letter, the developer, Knightsone Construction

has contacted SDCC  A meeting took place in

late April 2012, the list of works was agreed,

a site meeting is scheduled for this week and

a schedule for completion is to be agreed.

It is understood that NAMA/AIB are involved

in the funding of remedial works and it is

therefore hoped that this will give a greater

likelihood of completion.

The option of enforcement & bond claim are

still available to the Council and a deadline for

completion of works has been set for later in the year.

743	Ballynakelly	Newcastle	Tenbury

Developments

Residential Development of 743 dwellings,

including a neighbourhood centre and creche.

Permission is for 8 years, not expiring until

August 2014.

House construction not yet complete. Main

Access road will serve as access for

construction traffic in later phases so taking

in charge may be premature. However receiver

has carried out some works to tidy up the

entrance area the developer (funded by the

receiver )is engaged with the Council in

preparing TIC package for some parts of the

development

Management Agreement received for part of

the development. Substantial security

remains in place.

No. of Houses	Estate	Location	Developer

Works Outstanding

43	Brownsbarn Woods	Brownsbarn	Durkan

Residential

Management Agreement for development. A

Request was received for TIC of roads and

public lighting. Wayleave requested for drainage

tank prior to taking in charge.

Open Space areas are not for taking in charge.

Developer advised that CCTV & as

Constructed drawings are inadequate.

Bond remains in place.

325	Mill Race	Saggart	Neville

Development

Main road and drainage to be taken in 	Partnership

charge.  Final surfacing of road concluded Aug

2011and has been approved however a

review of underground services and public lighting is

needed. The Council received developers

TIC pack but CCTV, drawings, surveys and

tests 	etc  to identify next steps were

inadequate and have been returned to the

developer with directions for correct submission.

The bond is in place and request for

reduction on foot of the TIC request has been

refused as the development is not yet taken

in charge and developer has not yet

submitted all required documentation etc Re-

submission of TIC pack is anticipated.

E	ESTATES WHERE INSPECTIONS OF COMPLETED WORKS ARE IN PROGRESS:

106	The Glebe	Newcastle	Tenbury

Developments

Mixed residential development. 	Ltd

Developer offered estate for taking in charge

at end August 2011, CCTV survey

not received. However developer recently

carried out works to public lighting, traffic

calming and open space. Developer reviewing

underground services  as part of the works

Security being held pending receipt of report

from Building Control on completion of all

works to public services in the development.

G	ESTATES UNDER CONSTRUCTION:

203	Broadfield Phase 2	Rathcoole	Cavan

Developments

Under Construction: The developer will be

offering publicly accessible areas for Taking in

Charge at a later date when the completion of

the development is more advanced

69	Cross Forge	Saggart	Briarsgate

Development

Construction of 4 no..show houses completed

Commencement notices for 23 units, site under

construction.

No. of Houses	Estate	Location	Developer

Works Outstanding

184	Peyton Estate	Rathcoole	Blackchurch

Homes(Stanleys)

Under Construction

The developer will be offering publicly

accessible areas for Taking in Charge at a later

date when the completion of the development

is more advanced