Meeting of the Clondalkin Area Committee - 20/02/13

Item No.  H-I (4) - Taking in Charge Listing - Roads and Services

No. of Houses	Estate	Location	Developer

Works Outstanding

C	ESTATES WHERE TAKING IN CHARGE RECOMMENDATIONS ARE BEING PREPARED:

7	Monastery Gate	Clondalkin	M. Gate Ltd

Phase 1 is taken in charge, Phase 2 relates to

7 infill units: Surface works complete on last

inspection. Development to be advertised for

taking in charge as services completed to

standard per the Councils Senior Engineer

Building Control

106	The Glebe	Newcastle	Tenbury

Developments

Developer offered estate for taking in charge 	Ltd

at end August 2011. Following threatened

claim on security developer returned to site,

completing the vast majority of works.

However a liquidator was then appointed and

following discussions the Council has

sequestered security to complete the

outstanding  works in order to progress the

taking in charge of the estate: mainly traffic

calming, pumping equipment, attenuation.

Advertising of the development for taking in

charge is imminent   The security claimed will

be utilised to carry out outstanding works.

D	ESTATES WHERE TAKING IN CHARGE WORKS ARE OUTSTANDING

Aylmer Heath	Newcastle	Knightstone

Development

The development commenced in late 2006,

with the stated proposal for the completion of

80 units. Permission expired in August

2010 	and only 49 of overall total permitted

development of 112 were completed.

The Council has outlined its list of works

on foot of enforcement notices and warning

letters. The Council also placed a claim on the

bond (which remains in place) and the

developer has now engaged and has provided

as constructed drawings and CCTV to

commence the taking in charge review of

services.

The Council are reviewing the survey

documents and have advised the developer that

maps are inaccurate. When all the relevant

information is validated and correct a  meeting

is to be arranged to review defects and a

schedule for completion.

No. of Houses	Estate	Location	Developer

Works Outstanding

743	Ballynakelly	Newcastle	Tenbury

Developments

Residential Development of 743 dwellings,

including a neighbourhood centre and

creche. Permission is for 8 years, not

expiring until August 2014, but some parts of the

development are subject of permissions

expiring later. House construction not yet

complete.

Receiver authorised the 	developer to make

a taking in charge request

for part of the development. It has been

clarified that construction access for later

stages	 of development is possible by routes

other 	than the existing access road which

opens up the possibility of taking in charge

for some of the development.  The developer (funded by

the receiver )was engaged with the Council

in preparing TIC package for some parts of

the development, services for a total of

200-250 units 	may be involved.  However a

liquidator is now appointed and 	the

liquidator and receiver are in dialogue as to the

best approach to progress taking in charge.

The Council has requested the CCTV and as

constructed drawings for those parts which

may be taken in charge to initiate the process

and a further meeting is scheduled with the

receiver to seek resolution.

43	Brownsbarn Woods	Brownsbarn	Durkan

Residential

Management Agreement for development

however this relates to open space only which

is not to be taken in charge	. A request was

received for taking in charge of roads, public

lighting, drains only.

Developer has completed most surface level

defects but has not provided the requested

wayleave for drainage through open space and

the CCTV & as constructed drawings have

been returned to the developer (Sept 2012) as

they were inadequate. There are also issues

with the entrance to the estate.

The bond remains in place.

No. of Houses	Estate	Location	Developer

Works Outstanding

325	Mill Race	Saggart	Neville

DevelopmentPar

Main road and drainage to be taken in 	tnership

charge. Final surfacing of road concluded Aug

2011and has been approved however a

review of underground services and public

lighting is needed. The Council received

developers taking in charge pack but

CCTV,drawings, surveys and tests etc  to

identify next steps were inadequate and have

been returned to the developer with

directions for correct submission.

The bond is in place and reductions have

been refused 	as the development is not yet

taken in charge and developer has not yet

submitted all required documentation.

A bond claim was lodged on the 15.10.12 and

following threatened legal action on bank for

failure to comply with the bond, the developer

has since contacted the Council and a meeting

has been arranged with a view to agreeing a

schedule to address the outstanding issues.

F1	ESTATES SUBJECT TO LEGAL DIFFICULTIES:

107	Blackthorn Hill	Rathcoole	Durkan New

Homes Ltd.

Surface works completed in 2008 and approved

by Parks and Building Control however the

developer did not seek to have the

development taken in charge at the time nor

did they submit the full technical requirement

of the taking in charge package to enable the

process to be completed.

As required under recent legislation services in

the development were transferred to the

management company . The Council have

received enquiries from the residents regarding

taking in charge and have advised as to the

steps required.

G	ESTATES UNDER CONSTRUCTION:

203	Broadfield Phase 2	Rathcoole	Cavan

Developments

Under Construction: The developer will be

offering publicly accessible areas for Taking in

Charge at a later date when the completion of

the development is more advanced

69	Cross Forge	Saggart	Briarsgate

Development

Approximately 40 units either constructed or

under construction and security is in place.

Developer is liaising with Building Control on

compliance with taking in charge standards as

the development advances. Premature for

taking in charge as is under construction.

No. of Houses	Estate	Location	Developer

Works Outstanding

184	Peyton Estate	Rathcoole	Blackchurch

Homes(Stanleys)

Under Construction

The developer will be offering publicly

accessible areas for Taking in Charge at a later

date when the completion of the development

is more advanced

J	ESTATES WHERE BOND IS BEING CLAIMED

67	Castlelyon Estate, Cornerpark	Newcastle	Opus

Development

Bond expired end Aug 2012, extension sought	Ltd

by Council before expiry but bank has not

provided extended bond.Under Mgmt

Company but developer has not provided

reports etc for the Council to assess release of

the bond. Therefore claim lodged and list of

surface defects being reviewed to progress

same.  All units not sold so failure to maintain

a bond will prevent sales as compliance with

the bond condition will not exist.