COMHAIRLE CONTAE ÁTHA CLIATH THEAS
SOUTH DUBLIN COUNTY COUNCIL

MEETING OF LUCAN  AREA COMMITTEE

Tuesday, 28 May, 2013

HEADED ITEM NO. 12

Taking in Charge Listing - Roads and Services

No. of Houses	Estate	Location	Developer

Works Outstanding

C	ESTATES WHERE TAKING IN CHARGE RECOMMENDATIONS ARE BEING PREPARED:

4	Cnoc Aoibhinn	Lucan	Weston

Properties Ltd.

The developers company has been dissolved

however the Minister via the Chief State

Solicitor has consented to the taking in charge

process for public services proceeding.

Development advertised for taking in charge in

March 2013 and due before next Area

Committee.

3	Copse	Lucan	Weston

Properties Ltd

The developers company has been dissolved

however the Minister via the Chief State

Solicitor has consented to the taking in charge

process for public services proceeding.

Development advertised for taking in charge in

March 2013 and due before next Area

Committee.

235	Larkfield	Lucan	Fitzgibbon Bros

Following discussions with the bondholder,

the developer returned to site and completed

minor works and submitted CCTV surveys.

The development has been advertised for

taking in charge and a wayleave for execution

between the Councils Water Services division

and the developer has been drafted.

110	Mount Bellew	Lucan	Fitzgibbon Bros

Owing to the failure of Fitzgibbon Bros to

complete works, a claim was placed

on their bond in 2011. Following

discussions with the bondholder and the

Council, the developer returned to the site

and completed the remaining surface

works. The development is advertised for

taking in charge and is due before the next area

committee.

27	Moy Glas (Phase 2)	Lucan	Castlethorn/Cou

rtland/Lyncourt

27 units involved. The majority of this estate

is taken in charge. Remainder of estate

approved for taking in charge by Senior

Engineer . Estate advertised for taking in

charge in March and due before next area

No. of Houses	Estate	Location	Developer

Works Outstanding

D	ESTATES WHERE TAKING IN CHARGE WORKS ARE OUTSTANDING

Adamstown Square/Park	Lucan	Castlethorn

Approximately 190 of 225 units occupied.

Developer liaising with Parks and Building

Control on taking in charge works and a taking

in charge package being prepared. Bond in

place.

252	The Paddocks	Lucan	Mapelwood

Homes Ltd

A receiver, Paul McCann of Grant Thornton

has been appointed to control some assets of

Maplewood Developments. Initial discussions

identified Phase 1(Paddocks

Grove,Walk,Drive,Square,Way,Place, Crescent

and Road) as focus for taking in charge.  There

are also legal matters relating to  wayleaves for

some areas that will remain under Mgmt

Comp control particularly at Paddocks Place

and Square. A liquidator is also appointed

however and the Council are since working

with him and the receiver to identify all

required works to services which the liquidator

will carry out. Taking in charge works are

now intended for Phases 1 and 2.

Given the legal complexity both a liquidator

and receiver being involved with different

aspects, both parties are in dialogue as to

preparing a site resolution plan to bring the

development to taking in charge standard. The

Council is retaining security until the works

are completed and will be retaining the

required security related to the remaining parts

of the permitted development to be

constructed. Both the liquidator and the

receiver have been notified of the security held

and have been in dialogue with the Building

Control Section re a taking in charge package

and this remains outstanding.

Public lighting issues reported at Paddocks

View resulted from recent vandalisation and the

receiver is costing the under-grounding of

cabling to avoid further issues.

No. of Houses	Estate	Location	Developer

Works Outstanding

D2	ESTATES WHERE TAKING IN CHARGE WORKS ONGOING ON FOOT OF BOND CLAIM ETC

224	Hansted	Lucan	McInerney

Construction

Following the Council claim on the bond in

Oct 2011 and after lengthy interactions, the

bondholder advised in writing (March 2012) of

their intention to honour the bond and hired

agents to liaise with the Council on agreeing

the value of works subject of the claim.

Works commenced Jan 2013 and scheduled for

completion by end-May as delays have

occurred due to flooding in attenuation tanks.

Paralell to the works are a number of legal

issues being pursued to ensure taking in charge

may progress after works are done, such as

obtaining wayleaves from the receiver for access

to maintain certain services post-taking in

charge. The receiver has consented to the

wayleaves which are being mapped by the

Councils Building Control Section.

f2	ESTATES SUBJECT TO ENFORCEMENT ACTION:

108	Rossberry	Lucan	Kingscroft Ltd

& Hollioake Ltd

Two developers built Rossberry, Kingscroft

and Hollioake.

The Council has claimed security lodged for

completion of remedial works to part of 	the

development carried out by Hollioake and is

retaining the balance of security pending

completion of Deeds of Transfer for the open

space, which is almost completed.

However the estate as a whole cannot be taken

in charge as the Council requires unfettered

access to services and in the part developed by

Kingscroft, there remain issues with two

remaining residents with walls etc blocking

access to various public services; manholes,

hydrants and public lighting. The Council has

served enforcement notices relating to the

unauthorised developments and the majority of

residents have set back the unauthorised walls

to allow access to services. If the Enforcement

Notice is complied with the Council will

proceed with taking in charge. In the interim

the receiver has consented to the Council

completing other remaining taking in charge

related works using the security claimed.

G	ESTATES UNDER CONSTRUCTION/CONSTRUCTION CEASED:

166	Adamstown Castle 3	Adamstown	Castlethorn

Construction

Relates to Castlegate Mews, Lawn, Court,

Heath not taken in charge (remainder of

permitted development was taken in charge

April 2012. Report as to taking in charge

request awaited from developer and relevant

Depts.

No. of Houses	Estate	Location	Developer

Works Outstanding

173	Adamstown Castle 4	Adamstown	Castlethorn

Construction

Relates to Castlegate Vale, Downs, Copse,

Terrace, Row, Grange. Update as to taking in

charge package from developer pending.

50	Adamstown Castle 5	Adamstown	Castlethorn

Construction

Relates to Castlegate Hall and Rise, 50 units.

Not occupied.

61	Hansted Grove	Lucan	Tierra Ltd

Development under construction, adjacent to

existing Hansted development and Adamstown

Link Road. 61 units permitted, 17 2bed and

44 3bed.  13 units commenced to date. Bond

received for development.

10	Hawkridge	Lucan	Welcan Builders

Ltd.,

Houses partially completed, not occupied.

Permission expired. Development under

control of IBRC liquidator, site secured

recently following anti-social behaviour at

location.

St Edmonds	Lucan	Glenkerrin

Homes

Part of the development has been completed

and is substantially occupied and a bond is in

place. An extension of duration has been

granted for the rest of the development which is

currently fenced from the completed part of the

development. On appointment of a receiver the

Council reviewed the site and outlined initial

requirements for a taking in charge process but

no request was made.

50	Tullyhall (Phase 3) Mews	Lucan	Eleveden

Properties Ltd

Permission is for approximately 50 units

following An Bord Pleanala decision. Less

than 15 units built and some occupied.

Works have ceased on this site at present

however the remaining site is secured. An

extension of duration for the permission has

been granted to August 2016.

Recently reported issues with drainage have

been repaired and issues with public lighting

have been referred to the Councils Public

Lighting section for resolution. The Developer

has made an application to the ESB for

connection to permanently resolve issues with

public lighting.

No. of Houses	Estate	Location	Developer

Works Outstanding

N	PRIVATE DEVELOPMENT OPEN SPACE NOT COMPLETED

107	Esker Manor	Lucan	Brian M.

Durkan Ltd

Mixed residential development. Management

agreement submitted.  Partially private.

Public services completed to standard with

exception of play area which is not provided

and bond has been retained. Planning Dept

issued claim on the bond equiring response

from surety by Jan 28 2013. Response was

received and the Council have outlined options

for meeting requirements of the permission.

The developer is currently engaged with Parks

staff on a solution.

30	Fforster Square	Tierra Ltd

30 Apartments commenced June 2006.

Developer handed control to Mgmt Comp in

2011. Developer seeking release from bond and

the taking in charge of 200m of road at

Fforster Crescent. Of the 220m of road offered

for taking in charge there is an outstanding

road core test which must  be done in order to

progress the taking in charge process. Play

facilities are also required and  the Parks

department are in discussions re same. The

Parks Department are also in discussions re

the replacement of trees.