## Summary
Derelict Sites 2013 to date
Total In Progress | 59
Review in 2013 | 35
Standard Inspections | 24
Other
Awaiting Inspection Report | 14
Notices Served | 23
Other | 22
Notices
Total to date
Section 11 | 9
Section 8(2) | 14
Section 8(7) | 3
AREA
Tallaght (T)
Section 11 | 3
Section 8(2) | 9
Section 8(7) | 3
Clondalkin (C)
Section 11 | 1
Section 8(2) | 4
Section 8(7) | 0
Lucan (L)
Section 11 | 3
Section 8(2) | 0
Section 8(7) | 0
Rathfarnham (R)
Section 11 | 2
Section 8(2) | 1
Section 8(7) | 0
Note on A9: sdcc:Checking ownership, liasing with banks, Receivers, Liquidators, Solicitors, Estate Agents

## Tallaght
Derelict Sites
Ref No | Open | Address 1 | AREA | Report Req | Report Rec'd | Notice S11 | Expiry S11 | Notice S8(2) | Expiry S8(2) | Notice S8(7) | Comment
DS 1725 | OPEN | 69 Kiltalown Road, Jobstown | T | 2013-09-16 | 2013-10-23 | [5 empty] | Property sold at auction. Will continue to monitor.
DS 1725X | OPEN | 69A Kiltalown Road, Jobstown | T | 2013-09-16 | 2013-10-23 | [5 empty] | Property sold at auction. Will continue to monitor.
DS 1398 | OPEN | 9 SUNCROFT PARK | T | 2013-11-12 | 2014-01-03 | [5 empty] | For Sale with DNG
DS 1595 | OPEN | 1 - 2 Ballymount Road Lower | T | 2013-07-31 | 2014-01-03 |  |  | 2014-02-21
DS 1696 | OPEN | 30 Kilcarrig Crescent | T | 2013-11-06 | [6 empty] | Secured by Housing Dept. Being investigated under Derelict Sites Act 1990
DS 1458 | OPEN | Site at St James Road (formerly Greenhills Shopping Arcade) McHugh | T | 2013-11-13 | 2014-01-15 |  |  | 2014-01-15 | 2014-01-29 |  | Receiver appointed 22 Jan 2014. Copy of S 8(2) Notice sent to Receiver on 5 Feb 2014.
DS 1506 | OPEN | Site of 1 + 2 Wellington Cottages and former Burmah Garage, Wellington Lane | T | 2013-09-10 | 2013-12-11 |  |  | 2013-11-14 | 2013-12-26 | 2014-01-15
DS 1509 | OPEN | Site adjacent to (at rear of) St Peters Boys School, | T | 2014-01-20 | [6 empty] | Section 8(2) to be served
DS 1559 | OPEN | Former Esso Garage Site, Main Street | T | 2013-08-01 | 2013-09-24 | [5 empty] | Site sold. Will continue to monitor.
DS 1742 | OPEN | 26 Ard Mor Close | T | 2014-02-04 | [6 empty] | Being investigated under Derelict Sites Act 1990
DS 1630 | OPEN | Two storey house to west of school, Main Street | T | 2013-09-10 | 2013-09-30 |  |  | 2013-11-14 | 2013-12-26 |  | Owners have undertaken to carry out works to abate dereliction.
DS 1633 | OPEN | Former Saggart Arms pub & hoarding | T | 2013-11-14 | 2013-11-15 |  |  | 2014-01-15 | 2014-01-29 |  | S 8(2) Notice returned undelivered. To be served by hand.
DS 1641 | OPEN | Site at rear of 10 College Drive, Manor Avenue, Terenure | T | 2013-11-06
DS 1653 | OPEN | 11A Corrig Close, Greenpark | T | 2013-11-25 | 2014-01-16 | [5 empty] | Section 8(2) to be served
DS 1591X | OPEN | House adjoining former Keogh's shop at corner of Stoney Lane | T | 2013-09-10 | 2013-09-25 |  |  | 2013-11-14 | 2013-12-26 | 2014-01-28
DS 1703 | OPEN | Site at Balrothery Estate (adjacent to No.'s 13 + 24) | T | 2013-11-06 | 2013-12-12 | [5 empty] | Liaising with Liquidator. Sale of site to close imminently.
DS 1731 | OPEN | Former Scout's Den | T | 2013-11-21 | 2013-12-11 | 2014-02-03 | 2014-04-14
DS 1732 | OPEN | Site opposite Alymer Drive | T | 2013-11-21 | 2013-12-11 | [5 empty] | S 11 Notice to be served
DS 1706 | OPEN | Site of the former Harlem Court, Old Court Road | T | 2013-09-10 | 2013-09-19 |  |  | 2013-11-14 | 2013-11-28 |  | Commencement Notice served Oct 2013. Site being monitored.
DS 1707 | OPEN | 1 Cherryfield Avenue | T | 2013-09-10 | 2013-09-19 |  |  | 2013-11-14 | 2013-12-26 | 2014-01-28
DS 1719 | OPEN | 41 Swiftbrook Drive | T | 2013-11-06 | 2014-01-03 | [5 empty] | Secured by Housing & site cleared by Public Realm. Owner deceased - Liaising with solicitor acting for family who has advised property will be sold.
DS 1722 | OPEN | 1 Bawnlea Drive, Jobstown | T | 2013-09-10 | 2013-09-19 | 2014-01-29 |  |  |  |  | Repossessed by bank. Public Health Nuisance Notice served on bank. Being investigated under Derelict Sites Act
DS 1735 | OPEN | 3 Swiftbrook Avenue | T | 2013-11-28 | 2014-01-03 | [5 empty] | Awaiting ownership details
DS 1737 | OPEN | Cottage beside site opposite Alymer Drive | T | 2013-12-12 | [6 empty] | Receiver appointed. S 11 Notice will be served on Receiver
DS 1741 | OPEN | Belgard Rd Wall collapsed 'just past the slip road into bargain town and lidl' | T | 2014-01-23 | [6 empty] | Being investigated for danger under Sanitary Services Act (Dangerous Places/Structures)
DS 1709 | OPEN | 7 Montpelier View, Jobstown | T | 2013-09-10 | 2013-09-16 | 2014-02-14 | 2014-03-28 | 2013-12-12 | 2014-01-16 |  | Section 8(2) Notice returned undelivered. To be affixed to property in accordance with S 6(1)(d) of Derelict Sites Act 1990
DS 1726 | OPEN | 38 Russell Crescent, Jobstown | T | 2013-09-16 | 2013-10-22 | 2014-01-22 | 2014-03-05 |  |  |  | S 11 Notice affixed to door of property
DS 1727 | OPEN | Site Beside no. 1 Ballymount Road | T | 2013-09-25 | 2014-01-03 |  |  | 2014-02-05 | 2014-02-21
DS 1730 | OPEN | Site next to 13 Bancroft Close, Tallaght, Dublin 24 | T | 2013-11-13 | 2013-12-19 | [5 empty] | Awaiting ownership details
Note on I29: rkenneally: Section 8(2) Revoked