Rathfarnham/Templeogue-Terenure Area Committee

Meeting of the Rathfarnham/Templeogue-Terenure Area Committee -  14.10.2014

Item No.  H-I (10) - Taking in Charge Listing - Roads and Services

No. of Houses	Estate	Location	Developer

Works Outstanding

C	ESTATES WHERE TAKING IN CHARGE RECOMMENDATIONS ARE BEING PREPARED:

4	Templeroan Mews	Knocklyon	 Noel Reynolds

Valid taking in charge request received for

development. This Development has been

advertised for taking in charge in July 2014

D	ESTATES WHERE TAKING IN CHARGE WORKS ARE OUTSTANDING

260	Stocking Wood	Rathfarnham	Deane Homes

Mixed Residential development. No taking in

charge request yet received and security in

place. Parent planning 	permission is for 10

years and does not expire until Sept 2015,

revised permissions do not expire until 2019.

Utilising security or enforcement are

compromised while the permissions are live.

Receiver appointed Jan 2012 only for part of

the development. Receiver advised that 	not

all security will be released as the security is

for the full development, not only that in

receivership.

The receiver has advised of intention to fund

taking in charge works from recent house sales

and has carried out some works in the estate,

notably safety works to boundaries of the

building site. The technical requirements of

taking in charge process have been outlined to

the receiver and CCTV has been completed. In

parallel to this, as-built details of the

remaining underground network, site layout,

public open space, public lighting are being

completed as part of taking in charge

obligations. Meanwhile Kingscroft are

continuing to develop the 30+ house site to

the South-East of the Roundabout.

Realistically, the timing of the completion and

sale of the Kingscroft development, the

proving of all underground networks,

preparation and approval of all as-built

drawings, surfacing of remaining roads should

all coincide in the winter of 2014.Remedial

works including the provision of a new park

were due to commence on the 1st of

September. It has been confirmed by our

Senior Engineer that this work started on the

site on the 02.09.2014. Pavement

Investments have commenced development of

the northside compound area & these dwellings

should be complete and occupied by 2015

No. of Houses	Estate	Location	Developer

Works Outstanding

G	ESTATES UNDER CONSTRUCTION/CONSTRUCTION CEASED:

181	College Square, Wainsfort Manor	Terenure	Ballymore

Properties Ltd

Private development currently controlled by

Management company. No taking in charge

request from developer. Development not

completed under SD04A/0242, the 104

apartments not commenced and 62 of 77

permitted houses completed. The developer is

now commencing 42 units under a revised

planning permission (SD11A/0313)and has

completed CCTV survey to prove

underground services are to taking in charge

standard. A new bond has also been put in

place to secure service completion in future.

182	Dalriada Estate	Ballycullen	Ellier

Development

Mixed Residential Development  for 182 units 	Ltd

granted by An Bord Pleanala.  Further

extension of duration granted to Feb 2015.

The bond for the development remains in

place. Management Agreement submitted. No

taking in charge request from developer and

approximately 100 of the units in the

development are constructed and the

permission is still active. The developers

received planning permission for a revised

layout to part of this scheme recently,

SD13A/0005 refers. This development will

most likely commence in the coming months.

Given that certain roads are shared between

existing and proposed development and that

the storm and foul water systems are shared, it

would be premature to discuss taking in charge

until the development is complete as while

construction will be ongoing a risk to services

would exist were they taken in charge.

13	Hersil Wood	Knocklyon 	Pinza Property

Road	Company

Phase 1 of the development under construction

- 13 houses

6	Silver Acre House	Sarah Curran 	Homeland

Avenue	Investments Ltd

6 houses under construction

No. of Houses	Estate	Location	Developer

Works Outstanding

K	PRIVATE DEVELOPMENTS(NO TIC REQUEST)

11	Crannagh Way	Rathfarnham	Grovewood

Contractors Ltd.

Crannagh Way contains 11 semi detached

units built around 1996/97. Access to the

development is through Crannagh Grove/Road

which was itself taken in charge in 1986.

The planning permission stated that the

development was to be private and conditions

required the establishment of a management

structure for ongoing service maintenance.

The development was carried out by

Grovewood Contractors however it was never

offered for taking in charge. There was no

condition requiring lodgement of security

applied by An Bord Pleanala who granted

permission under 06S.099068. No record of

bond or security lodged exists. As the

statutory period for the taking of enforcement

action has expired a number of years, the

Council cannot compel the developer to

complete the development.

Initial surveys of surface defects that would

have to be remedied in order to bring the

development to taking in charge standard are

approximately €45,000, with public lighting

standards being the main issue.

The house owners may offer the services to be

taken in charge but funds will have to be

identified to complete taking in charge

remediation.