## Laneways Cleaning List Upda (2)
Location | Listed for Cleaning week Commencing | Completed Week Ending | Completed Y/N | Comment
Beechfield Close - Rear of No.s 01 -21 | 2014-04-14 | 2014-04-20 | yes
Beechfield Close - Rear of No.s 02 - 18 (GATED) | 2014-04-14 | 2014-04-20 | No | No Access - Gated
Beechfield Rd - Rear of No.s 62 - 91 | 2014-04-14 | 2014-04-20 | yes
Cherryfield Ave - Rear of No.s 04 - 56 | 2014-04-14 | 2014-04-20 | yes
Cherryfield Ave - Rear of No.s 15 - 69 | 2014-04-14 | 2014-04-20 | yes
Cherryfield Drive - Rear of No.s 25 - 42 | 2014-04-21 | 2014-04-25 | yes
Cherryfield Rd - Rear No.s 12 - 184 | 2014-04-21 | 2014-04-25 | yes
College Drive to Fortfield Rd - Ped Walkway | 2014-04-21 | 2014-04-25 | yes
Cromswellsfort Rd - Rear of No.s 80 - 122 | 2014-04-28 | 2014-05-04 | yes
Cromwellsfort Rd - Rear of No.s 124 - 138 | 2014-04-28 | 2014-05-04 | yes
Cromwellsfort Rd - Rear of No.s 18 - 78 | 2014-04-28 | 2014-05-04 | yes
Cromwellsfort Rd - Rear of No.s140 - 158 | 2014-04-28 | 2014-05-04 | yes
Greentrees rd - Side of No. 87A | 2014-04-28 | 2014-05-04 | yes
Hillsbrook Ave - rear of No.s 02 - 72 | 2014-04-28 | 2014-05-04 | yes
Hillsbrook Cresnt to Muckross Cresnt - Ped walkway | 2014-05-05 | 2014-05-09 | yes
Hillsbrook Grove - Rear of No.s 15 - 22 | 2014-05-05 | 2014-05-09 | yes
Hillsbrook Grove - Rear of No.s 27 - 38 | 2014-05-05 | 2014-05-09 | yes
Kaedeen Pedestrian Walkway | 2014-05-05 | 2014-05-09 | yes
Kilakea Close - Rear of No.s 06 - 20 | 2014-05-05 | 2014-05-09 | yes
Kilakea Drive - Rear of No.s 10 - 20 | 2014-05-05 | 2014-05-09 | yes
LANE - Whitehall Rd West to Beechfield Rd | 2014-05-12 | 2014-05-16 | NO | No Access - Gated
Lane from 26 St Finbar's Close to 21 St Mel's Ave | 2014-05-12 | 2014-05-16 | yes
Lime Lane | 2014-05-12 | 2014-05-16 | yes
Limekiln Close - Side of No. 12 | 2014-05-19 | 2014-05-23 | yes
Limekiln Green - rear of No.s 01 - 34 | 2014-05-19 | 2014-05-23 | yes
Limekiln Green - rear of No.s 120 -130 | 2014-05-19 | 2014-05-23 | yes
Limekiln Green - Rear of No.s 133 - 137 | 2014-05-19 | 2014-05-23 | yes
Limekiln Green - Rear of No.s 141 - 144 | 2014-05-19 | 2014-05-23 | yes
Limekiln Green - Side of No. 80 | 2014-05-19 | 2014-05-23 | yes
Limekiln Rd - Rear of No.s 107 - 117 | 2014-05-19 | 2014-05-23 | yes
Limekiln Rd - Rear of No.s 121 - 137 | 2014-05-19 | 2014-05-23 | yes
Limekiln Rd - rear of No.s 145 - 163 | 2014-05-19 | 2014-05-23 | yes
Limekiln rd - Rear of No.s 171 -189 | 2014-05-19 | 2014-05-23 | yes
Limekiln Rd - Rear of No.s 41 - 51 | 2014-05-19 | 2014-05-23 | yes
Limekiln Rd - Side of No. 105 | 2014-05-19 | 2014-05-23 | yes
Limerkiln Green - Side of No. 85 | 2014-05-19 | 2014-05-23 | yes
Mountdown Rd - Rear of No.s 15 - 25 | 2014-05-26 | 2014-05-30 | yes
Muckross Ave - rear of No. 44 (SHOPS) | 2014-05-26 | 2014-05-30 | yes
Muckross Ave - Rear of No.s 08 - 73 | 2014-05-26 | 2014-05-30 | yes
Muckross Ave - Rear of No.s 81 -103 | 2014-05-26 | 2014-05-30 | yes
Muckross Green - Rear of No.s 36 - 46 | 2014-05-26 | 2014-05-30 | yes
Muckross Green - Rear of No.s19 -32 (PrivateDitch) | 2014-05-26 | 2014-05-30 | yes
Muckross green -Rear of No.s 01 -14 (PrivateDitch) | 2014-05-26 | 2014-05-30 | yes
Muckross Grove - Rear of No.s 11 - 18 | 2014-05-26 | 2014-05-30 | yes
Muckross Park - Rear of No.s 05 - 28 | 2014-05-26 | 2014-05-30 | yes
Old Tymon Lane | 2014-06-02 | 2014-06-06 | yes
Quarry Drive - Rear of No.s 03 - 08 | 2014-06-02 | 2014-06-06 | yes
Quarry Drive - Rear of No.s 13 - 14 | 2014-06-02 | 2014-06-06 | yes
Rockfield Ave - Rear of No.s 121 - 131 | 2014-06-02 | 2014-06-06 | yes
Rockfield Ave - Rear of No.s 137 - 147 | 2014-06-02 | 2014-06-06 | yes
St Anthony's Crescent - Rear of No.s 02 - 46 | 2014-06-09 | 2014-06-13 | yes
St Anthony's crescent - Rear of No.s 65 - 97 | 2014-06-09 | 2014-06-13 | yes
St Brendan's Crescent - Rear of No.s 01 -123 | 2014-06-09 | 2014-06-13 | yes
St Brendan's Crescent - Rear of No.s 02 -98 | 2014-06-09 | 2014-06-13 | yes
St Brigid's Drive - Rear of No.s 01 -10 | 2014-06-09 | 2014-06-13 | yes
St Columbas' Rd - rear of No.s 02 -86 | 2014-06-09 | 2014-06-13 | yes
St Conleth's Rd - Rear of No.s 02 - 88 | 2014-06-09 | 2014-06-13 | yes
St Finbar's Close - Rear of No.s 01 - 29 | 2014-06-09 | 2014-06-13 | yes
St James' Rd - rear of No.s 02 -186A | 2014-06-16 | 2014-06-20 | yes
St James' Rd - rear of No.s 188 -270 | 2014-06-16 | 2014-06-20 | yes
St James' Rd - Rear of No.s 229 - 247 | 2014-06-16 | 2014-06-20 | yes
St James' Rd - Rear of No.s 272 - 308 | 2014-06-16 | 2014-06-20 | yes
St James' Rd - Rear Of No.S 289 - 249 | 2014-06-16 | 2014-06-20 | yes
St James' Rd - Rear of No.s 310 - 324 | 2014-06-16 | 2014-06-20 | yes
St James' Rd - Rear of No.s 326 - 354 | 2014-06-16 | 2014-06-20 | yes
St Joseph's Rd - Rear of No.s 14 - 44 | 2014-06-23 | 2014-06-27 | yes
St Joseph's Rd - Rear of No.s 64 - 104 | 2014-06-23 | 2014-06-27 | yes
St Killian's Ave - Rear of No.s 01 - 43 | 2014-06-23 | 2014-06-27 | yes
St Killian's Ave - Rear of No.s 02A - 14 | 2014-06-23 | 2014-06-27 | yes
St malachy's drive - Rear of No.s 01 - 56 | 2014-06-23 | 2014-06-27 | yes
St Malachy's Drive - Rear of No.s 02 - 50 | 2014-06-23 | 2014-06-27 | yes
St Mel's Ave - Rear of No.s 02 - 16 | 2014-06-23 | 2014-06-27 | yes
St Mel's Avenue - Rear of No.s 01 - 21 | 2014-06-23 | 2014-06-27 | yes
St Patrick's Rd - Rear of No.s 10 - 102 | 2014-06-23 | 2014-06-27 | yes
St Peter's Crescent - Rear of No.s 01 - 83 | 2014-06-30 | 2014-07-04 | yes
St Peter's Crescent - Rear to No.s 02 -72 | 2014-06-30 | 2014-07-04 | yes
St Peter's Drive - Rear of No.s 01 - 33B | 2014-06-30 | 2014-07-04 | yes
St Peter's Rd - Rear of No. 02 - 88 | 2014-06-30 | 2014-07-04 | yes
St Peter's rd - Rear of No.s 90 - 238 | 2014-06-30 | 2014-07-04 | yes
St Peter's Road - Rear of No.s 01 - 107 | 2014-06-30 | 2014-07-04 | yes
St Peter's Road - Rear of No.s 109 - 125 | 2014-06-30 | 2014-07-04 | yes
St Peter's Road - To side of No. 107 - ESB station | 2014-06-30 | 2014-07-04 | yes
Tibradeen Close - Rear of No.s 06 - 20 | 2014-06-30 | 2014-07-04 | yes
Tibradeen Close - Side of No. 9 | 2014-06-30 | 2014-07-04 | yes
Wainsfort Rd to Wainsfort Park - Ped Walkway | 2014-07-07 | 2014-07-11 | yes
Whitehall Park - Rear of No.s 01 - 14 | 2014-07-07 | 2014-07-11 | yes
Whitehall Park - Rear of No.s 15 - 27 | 2014-04-07 | 2014-04-11 | yes
Whitehall Rd - Entrance to Badminton Hall | 2014-04-07 | 2014-04-11 | yes
Whitehall Rd West - Rear of No.s 10 - 34 | 2014-04-07 | 2014-04-11 | yes
Whitehall Rd West - Rear of No.s 86 -98 | 2014-04-07 | 2014-04-11 | yes
Whitehall Road West - Rear of No.s 106 - 144 | 2014-04-07 | 2014-04-11 | yes
Whitehall Road West at rear of No.s 146 and 172 (with branch to Muckross Grove) | 2014-04-07 | 2014-04-11 | yes
Whitehall Road West at rear of No.s 146 and 172 (with branch to Muckross Grove) | 2014-07-07 | 2014-07-11 | yes
Beechfield Close - Rear of No.s 01 -21 | 2014-09-01 | 2014-09-05 | yes
Beechfield Close - Rear of No.s 02 - 18 (GATED) | 2014-09-01 | 2014-09-05 | yes
Beechfield Rd - Rear of No.s 62 - 91 | 2014-09-01 | 2014-09-05 | yes
Cherryfield Ave - Rear of No.s 04 - 56 | 2014-09-29 | 2014-10-03 | yes
Cherryfield Ave - Rear of No.s 15 - 69 | 2014-09-29 | 2014-10-03 | yes
Cherryfield Drive - Rear of No.s 25 - 42 | 2014-10-06 | 2014-10-10 | yes
Cherryfield Rd - Rear No.s 12 - 184 | 2014-10-06 | 2014-10-10 | yes
College Drive to Fortfield Rd - Ped Walkway | 2014-10-06 | 2014-10-10 | yes
Cromwellsfort Rd - Rear of No.s 124 - 138 | 2014-10-13 | 2014-10-19 | no | Work yet to Commence
Cromwellsfort Rd - Rear of No.s 18 - 78 (PRIVATE) | 2014-10-13 | 2014-10-19 | no | Work yet to Commence
Cromwellsfort Rd - Rear of No.s140 - 158 (PRIVATE) | 2014-10-13 | 2014-10-19 | no | Work yet to Commence
Greentrees rd - Side of No. 87A | 2014-05-26 | 2014-05-26 | yes
Hillsbrook Ave - rear of No.s 02 - 72 | 2014-10-13 | 2014-10-19 | no | Work yet to Commence
Hillsbrook Cresnt to Muckross Cresnt - Ped walkway | 2014-10-20 | 2014-10-26 | No | Work yet to Commence
Hillsbrook Grove - Rear of No.s 15 - 22 | 2014-10-20 | 2014-10-26 | No | Work yet to Commence
Hillsbrook Grove - Rear of No.s 27 - 38 | 2014-10-20 | 2014-10-26 | No | Work yet to Commence
Kaedeen Pedestrian Walkway | 2014-10-20 | 2014-10-26 | No | Work yet to Commence
Kilakea Close - Rear of No.s 06 - 20 | 2014-10-20 | 2014-10-26 | No | Work yet to Commence
Kilakea Drive - Rear of No.s 10 - 20 | 2014-10-20 | 2014-10-26 | No | Work yet to Commence
LANE - Whitehall Rd West to Beechfield Rd | 2014-10-20 | 2014-10-26 | No | Work yet to Commence
Muckross Green - Rear of No.s19 -32 (PrivateDitch) | 2014-11-17 | 2014-11-23 | No | Work yet to Commence
Muckross green -Rear of No.s 01 -14 (PrivateDitch) | 2014-11-17 | 2014-11-23 | No | Work yet to Commence
Muckross Grove - Rear of No.s 11 - 18 | 2014-11-17 | 2014-11-23 | No | Work yet to Commence
Muckross Park - Rear of No.s 05 - 28 | 2014-11-17 | 2014-11-23 | No | Work yet to Commence
Old Tymon Lane | 2014-01-29 | 2014-01-31 | yes
Old Tymon Lane | 2014-11-17 | 2014-11-23 | No | Work yet to Commence
Quarry Drive - Rear of No.s 03 - 08 | 2014-11-17 | 2014-11-23 | No | Work yet to Commence
Quarry Drive - Rear of No.s 13 - 14 | 2014-11-17 | 2014-11-23 | No | Work yet to Commence
Rockfield Ave - Rear of No.s 121 - 131 | 2014-11-17 | 2014-11-23 | No | Work yet to Commence
Rockfield Ave - Rear of No.s 137 - 147 | 2014-11-17 | 2014-11-23 | No | Work yet to Commence
Cherryfield Ave - Rear of No.s 04 - 56 | 2014-09-01 | 2014-09-05 | yes
Cherryfield Ave - Rear of No.s 15 - 69 | 2014-09-01 | 2014-09-05 | yes
Cromwellsfort Rd - Rear of No.s 124 - 138 | 2014-09-15 | 2014-09-21 | yes
Cromwellsfort Rd - Rear of No.s 18 - 78 (PRIVATE) | 2014-09-15 | 2014-09-21 | yes
Cromwellsfort Rd - Rear of No.s140 - 158 (PRIVATE) | 2014-09-15 | 2014-09-21 | yes
St Anthony's Crescent - Rear of No.s 02 - 46 | 2014-09-01 | 2014-09-05 | yes
St Anthony's crescent - Rear of No.s 65 - 97 | 2014-09-01 | 2014-09-05 | yes
St Brendan's Crescent - Rear of No.s 01 -123 | 2014-09-01 | 2014-09-05 | yes
St Brendan's Crescent - Rear of No.s 02 -98 | 2014-09-01 | 2014-09-05 | yes
St Brigid's Drive - Rear of No.s 01 -10 | 2014-09-01 | 2014-09-05 | yes
St Columbas' Rd - rear of No.s 02 -86 | 2014-09-01 | 2014-09-05 | yes
St Conleth's Rd - Rear of No.s 02 - 88 | 2014-09-01 | 2014-09-05 | yes
St Finbar's Close - Rear of No.s 01 - 29 | 2014-09-01 | 2014-09-05 | yes
St Malachy's Drive - Rear of No.s 02 - 50 | 2014-09-01 | 2014-09-05 | yes
Cherryfield Drive - Rear of No.s 25 - 42 | 2014-09-08 | 2014-09-12 | yes
Cherryfield Rd - Rear No.s 12 - 184 | 2014-09-08 | 2014-09-12 | yes
College Drive to Fortfield Rd - Ped Walkway | 2014-09-08 | 2014-09-12 | yes
St James' Rd - rear of No.s 02 -186A | 2014-09-08 | 2014-09-12 | yes
St James' Rd - rear of No.s 188 -270 | 2014-09-08 | 2014-09-12 | yes
St James' Rd - Rear of No.s 229 - 247 | 2014-09-08 | 2014-09-12 | yes
St James' Rd - Rear of No.s 272 - 308 | 2014-09-08 | 2014-09-12 | yes
St James' Rd - Rear Of No.S 289 - 249 | 2014-09-08 | 2014-09-12 | yes
St James' Rd - Rear of No.s 310 - 324 | 2014-09-08 | 2014-09-12 | yes
St James' Rd - Rear of No.s 326 - 354 | 2014-09-08 | 2014-09-12 | yes
Hillsbrook Ave - rear of No.s 02 - 72 | 2014-09-15 | 2014-09-19 | yes
St Joseph's Rd - Rear of No.s 14 - 44 | 2014-09-15 | 2014-09-19 | yes
St Joseph's Rd - Rear of No.s 64 - 104 | 2014-09-15 | 2014-09-19 | yes
St Killian's Ave - Rear of No.s 01 - 43 | 2014-09-15 | 2014-09-19 | yes
St Killian's Ave - Rear of No.s 02A - 14 | 2014-09-15 | 2014-09-19 | yes
St malachy's drive - Rear of No.s 01 - 56 | 2014-09-15 | 2014-09-19 | yes
St Mel's Ave - Rear of No.s 02 - 16 | 2014-09-15 | 2014-09-19 | yes
St Mel's Avenue - Rear of No.s 01 - 21 | 2014-09-15 | 2014-09-19 | yes
St Patrick's Rd - Rear of No.s 10 - 102 | 2014-09-15 | 2014-09-19 | yes
St Peter's Crescent - Rear of No.s 01 - 83 | 2014-09-22 | 2014-09-26 | yes
St Peter's Crescent - Rear to No.s 02 -72 | 2014-09-22 | 2014-09-26 | yes
St Peter's Rd - Rear of No. 02 - 88 | 2014-09-22 | 2014-09-26 | yes
St Peter's rd - Rear of No.s 90 - 238 | 2014-09-22 | 2014-09-26 | yes
St Peter's Road - Rear of No.s 01 - 107 | 2014-09-22 | 2014-09-26 | yes
St Peter's Road - Rear of No.s 109 - 125 | 2014-09-22 | 2014-09-26 | yes
St Peter's Road - To side of No. 107 - ESB station | 2014-09-22 | 2014-09-26 | yes
St Malachy's Drive - Rear of No.s 02 - 50 | 2014-09-29 | 2014-10-03 | yes
Tibradeen Close - Rear of No.s 06 - 20 | 2014-09-29 | 2014-10-03 | yes
Tibradeen Close - Side of No. 9 | 2014-09-29 | 2014-10-03 | yes
Wainsfort Rd to Wainsfort Park - Ped Walkway | 2014-09-29 | 2014-10-03 | yes
Whitehall Park - Rear of No.s 01 - 14 (PRIVATE) | 2014-09-29 | 2014-10-03 | yes
Whitehall Park - Rear of No.s 15 - 27 (PRIVATE) | 2014-09-29 | 2014-10-03 | yes
Whitehall Rd - Entrance to Badminton Hall | 2014-09-29 | 2014-10-03 | yes
Whitehall Rd West - Rear of No.s 10 - 34 | 2014-09-29 | 2014-10-03 | yes
Whitehall Rd West - Rear of No.s 86 -98 | 2014-09-29 | 2014-10-03 | yes
Whitehall Road West - Rear of No.s 106 - 144 | 2014-09-29 | 2014-10-03 | yes
Whitehall Road West Rear of No.s 146 - 172 (with branch to Muckross Grove) | 2014-09-29 | 2014-10-03 | yes