Billing and Collection Statement

Use of overdraft facility

Approved overdraft facility = €13,000,000

No of days in Overdraft from 1st January to 30th April = 1

SDCC 3-Year Capital Programme Update for Quarter 1 2015

PROGRAMME 1: HOUSING AND BUILDING

Works are on going on the following programmes:

- Electrical Repairs And Rewiring

- Energy Efficiency Programme

- Presale And Prelet Repairs

- Revenue funded Window & Door Replacement Programme R2014

Works are due to start on the following projects this year:

- Belgard Redevelopment

- St Finians Infill – tender approval received from the DECLG

- Suncroft Infill – tender approval received from the DECLG

St Marks Infill – awaiting approval from the DECLG to proceed to tender

Housing adaption grants on Council Houses – works on a priority basis underway

Expanded Social Housing Programme – Target for 2015 to 2017 received in April 2015

PROGRAMME 2: ROAD TRANSPORTATION AND SAFETY

Works are progressing on the Cycle way network in Palmerstown (Old N4) and the link from Tallaght to Templeogue.  Other NTA schemes are progressing in accordance with the funding made available under the 2015 allocation.

Design Work is approaching completion on the R120 (Adamstown Road) and Nangor Road Improvement Schemes and it is anticipated that the CPO Process will be initiated shortly.  The 2015 investment programme in Public Lighting low energy LED retrofit is finalised .

c350 LED’s will be installed in the village centres and over 600 ESB poles through out the County.

PROGRAMME 3: SURFACE WATER AND FLOOD RELIEF WORKS

River Poddle Flood Alleviation Scheme

Contract documents are being finalised to procure a Consultant to carry out preliminary design, detailed design and management of the construction stage in South Dublin and Dublin City Council. The OPW recently approved the design brief and it is planned to have the aforementioned documents completed in the near future at which point we can invite tenders from Consultants on an existing framework agreement. The scheme is estimated to cost in the region of €6million.

Ballycullen Stream Flood Alleviation Scheme

The process of procuring an Engineering Consultant has commenced, detailed surveys will begin as soon as possible to enable the detailed design and contract documents to be completed.

This will enable a construction contract to be entered into.

Dodder Flood Risk Management

The Study is project managed by Dublin City Council and funded by the OPW.

The key outputs from the Study were flood hazard and risk maps and a "Catchment Flood Risk Management Plan". In South Dublin, the Whitechurch Stream Flood Alleviation Scheme has been identified by the OPW in the River Dodder CFRAMS Option Development Process and will progress in 2015/16. The scheme is estimated to cost in the region of €2million.

Minor SW Schemes – 2015

The following minor SW schemes went out to tender in March 2015.

400mm SW upgrade on Church Road, Saggart	  					€125,000

225mm SW installation in New Road, Clondalkin	  					  €50,000

225mm SW upgrade on Monastery Road Clondalkin					€100,000

Progressing the Anti-erosion works on Dodder near Templeogue LTC with the OPW.	  €80,000

PROGRAMME 4: DEVELOPMENT MANAGEMENT

The pilot signs for a County Signage plan are currently being installed.

Investment in Grange Castle Business Park is continuing.

The Tourism Strategy has been launched and the key projects advanced.

PROGRAMME 5: ENVIRONMENTAL SERVICES

Newcastle Burial Grounds Islamic Foundation of Ireland

Construction to commence in Q.3 2015							€150,000

Retaining wall - Saggart Cemetery

Tender process commenced.									  €75,000

PROGRAMME 6: RECREATION AND AMENITY

Play-space Development Programme

Continuation of implementation of play space programme with 6 play spaces completed.  There are 14 proposed sites on the 2015 Playground Construction Programme.  Consultations have commenced on 8 of these sites.

Provision of Allotments & Facilities

Corkagh Allotments Scheme commenced, detailed plans being drawn up.

Dodder Valley Park Development - Firhouse Road Section

Part VIII plans have been prepared. Currently preparing documentation for advertising.

Dodder Valley Park Development – Oldbawn

Design work commencing in Q.2 2015

Sports Pavilions Programme

Meeting held with officials from the DTTAS 14th April, 2015– New composite proposal to be submitted and agreed. Full report and recommendations will be brought to the June Council meeting.

Corkagh Park Improvement Works

Survey work commencing in May 2015 for Tender preparation

Griffeen Valley Park surfacing & marking of Leisure Centre car park

Car park survey completed. Tender being prepared for advertising in June 2015

Dublin Mountains Way Access Improvement (Kiltipper)

Draft plan prepared, consultation to start with residents.

Clondalkin Equine Project

At site selection stage, consultation ongoing with the CEC and other stakeholders.

Public Realm enhancement at Swiftbrook Estate

Design parameters being agreed with residents followed by preparation of tender and advertising.

LEADER Seed Funding

Closing Date for LEADER Programme 15th May - Discussions between SDCC, Fingal and Dunlaoire Rathdown County Council Continuing.

Rathcoole Courthouse

Works required completed.

Jobstown (Kiltalown) All Weather Pitch Refurb

Management Company not in a position to apply for Sports Capital Grant but are preparing for future Scheme.

Libraries

The planned investment programme in the library infrastructure is being advanced.

A tender process is under way in respect of a new mobile library.