COMHAIRLE CHONTAE ÁTHA CLIATH THEAS

SOUTH DUBLIN COUNTY COUNCIL

# MEETING OF TALLAGHT AREA COMMITTEE (1)

Wednesday 7th DECEMBER 2005

H I (2)

## Report on Housing Construction Programme :

The up-to-date position of the construction programme for the Tallaght area is set out in the detail below: -

Completions in 2004 :-

Tallaght Area

| Scheme Name | No. of Units | Completion Dates |
| --- | --- | --- |
| Cushlawn, Phase 1 | 6 | February 2004 |
| Cushlawn, Phase 1 | 5 | March 2004 |
| Cushlawn, Phase 1 | 17 | September 2004 |
| Tymon Park | 2 | April 2004 |
| Bolbrook | 11 | June 2004 |
| Kilcarrig, Phase 2 | 4 | August 2004 |
| Russell Square | 5 | November 2004 |
| Killcarrig Phase 2 | 4 | December 2004 |
| Marlfield (Part V) | 27 | December 2004 |
| Sub Total | 81 |  |

Completions in 2005 :-

| Scheme Name | No. of Units | Completion Dates |
| --- | --- | --- |
| Russell Square | 8 | January 2005 |
| Russell Square | 39 | February 2005 |
| Bawnlea | 7 | March 2005 |
| Jobstown Village Core | 10 | March 2005 |
| Cushlawn, Phase II | 16 | May 2005 |
| Russell Square | 47 | June 2005 |
| Cushlawn Phase 2 | 2 | June 2005 |
| Russell Square | 16 | July 2005 |
| Cushlawn Phase 2 | 5 | September 2005 |
| Daletree, Ballycragh | 8 | September 2005 |
| Fettercairn Village | 7 | October 2005 |
| Fettercairn Village | 6 | November 2005 |
| Cushlawn Phase 2 | 8 | November 2005 |
| Sub Total | 179 |  |

### On Site:-

### Tallaght Area

| Scheme Name | No. of Units on Site | Completion Dates |
| --- | --- | --- |
| Fettercairn Village, Phase 1 Includes extension to creche & community facility | 28 | (In Phases)Nov 05 - Feb 06 |
| Avonbeg, Phase 3 | 47 | In phases early February, 2006 |
| Fortunestown B, Phase 2 | 66 (+52 Vol. Units) | June, 2006 |
| Fortunestown B, Phase 4 | 120 | August, 2006 |
| Fortunestown B, Phase 1 | 110 | May, 2006 |
| Deer Park (Joint Venture) | 119 | (In phases) From DEC 2005 |
| Daletree (Part 5/Joint Venture) | 35 | (In phases ) Dec 2005 |
| Hunterswood (Part V) | 9 | December 2005 |
| Brookfield Village+ Community Facility | 16 | Jan 2006 |
| Deerpark (Part V) | 36 | December 2006 |
| Belfry | 35 | December 2006 |
| Sub.Total | 621 |  |

Tenders Recommended

| Kilcarrig Phase 3 | Tender recommended in the sum of €13,694,394 for the construction of 80 units by D&I Construction Ltd., Tyrell House, Main Street Blessington, Co Wicklow |
| --- | --- |

Tenders being examined

| Scheme Name | No. Of Housing Units |
| --- | --- |
| Castlepark | 9(3 specially adapted units) |
| Cushlawn Phase III | 22 |
| Sub Total | 31 |

Tender Production

| Scheme Name | No. of Housing Units |
| --- | --- |
| Kiltalown Green | 28 |
| Sub Total | 28 |

Part 8 Approved by Council:-

| Scheme Name | No. of Housing Units |
| --- | --- |
| Avonbeg Phase 4 | 7 |
| Sub Total | 7 |

At Concept/Design Stage:-

### Tallaght Area

| ### Scheme Name | ### Approx . No. Of Units |
| --- | --- |
| ### Fortunestown B, Phase3 | ### 120 |
| ### Fettercairn Villlage, Phase2 | ### 10 |
| ### Kilclare, Phase2 | ### 30 (concepts presented to Tallaght Area Committee Meeting 16/06//2003) |
| ### Kilclare Phase3 | ### 15 |
| ### Knockmore House (incl. 15 units for Bernardos) | ### 60 (concepts presented to Tallaght Area Committee Meeting 16/06//2003) |
| Whitestown Stream | - |
| Suncroft | - |
| Whitebrook Park | - (concepts presented to Tallaght Area Committee Meeting 20/09/2004) |
| ### Stocking Lane | -(concept under preparation) |
| ### Swiftbrook | -(concept presented to Tallaght Area Committee Meeting 08/12/04) |
| ### Rossfield Infill |  |
| ### Brookfield 3, 4 & 5 |  |
| ### Fettercairn Phase 2 |  |
| ### Castletymon |  |
| ### Sub Total | 235 |

Other potential sites are also being examined.