Billing and Collection Statement

Use of overdraft facility

Approved overdraft facility = €13,000,000

No of days in Overdraft from 1st January to 30th September = 1

SDCC 3-Year Capital Programme update to August 2015

PROGRAMME 1: HOUSING AND BUILDING

Works are ongoing on the following programmes:

- Electrical Repairs And Rewiring

- Energy Efficiency Programme

- Presale And Prelet Repairs

- Revenue funded Window & Door Replacement Programme R2014

Works have commenced on 3 New Build Projects this year:

- Belgard Redevelopment – Construction commenced May 2015

- St Finians Infill – Contractors appointed in May 2015. Construction to commence Q3 2015

- Suncroft Infill – Contractors appointed in May 2015. Construction to commence Q3 2015

St Marks Infill – awaiting approval from the DECLG to proceed to tender

Dromcarra, Tallaght Infill Part 8 for 14 units was approved by Council in May 2015.

Letts Field, Clondalkin Part 8 consultation commenced 7th May2015 and report due for presentation at September Council meeting.

Housing adaption grants on Council Houses – works on a priority basis underway

Accelerated house purchase programme in place as one element of Social Housing Programme

Expanded Social Housing Programme – Target for 2015 to 2017 received in April 2015

PROGRAMME 2: ROAD TRANSPORTATION AND SAFETY

Works have been completed on the current phase of the Cycle way network in Palmerstown (Old N4).  Works are continuing on the link from Tallaght to Templeogue and is due for completion on 1st quarter 2016.  Monastery Road Walking Scheme, Phase 3 is currently at tender stage.  Work is due to commence end of month and will take approx. 3/4 months to complete.  Other NTA schemes are progressing in accordance with the funding made available under the 2015 allocation.

Design Work is approaching completion on the R120 (Adamstown Road) and Nangor Road Improvement Schemes and it is anticipated that the CPO Process will be initiated shortly.  Funding has recently been announced for this scheme under the Government’s Plan for Capital Investment.

The 2015 investment programme in Public Lighting low energy LED retrofit is finalised and

approx.350 LED’s will be installed in the village centres, 80% of this work will be completed by end of year.  In addition 600 ESB poles will be upgraded to new led standards throughout the county.

PROGRAMME 3: SURFACE WATER AND FLOOD RELIEF WORKS

River Poddle Flood Alleviation Scheme

The OPW has approved the Draft Design Brief for the River Poddle Flood Alleviation Scheme.  As this project straddles both Dublin City and South Dublin areas, DCC have commenced the tender process for procuring consultants using their tender framework on behalf of SDCC. The scheme is estimated to cost in the region of €6million

Ballycullen Stream Flood Alleviation Scheme

Roughan O’Donovan (ROD) have been appointed as consulting engineers to review the Council’s

preliminary design, prepare contract documents and supervise construction of the works.

A draft Preliminary Design Review has just been received and draft contract documents for the

topographical and ground investigation contracts. When these have been reviewed a meeting with representatives of the residents will be set up to brief them on progress and the options being considered. This project will cost approximately €1.6M

Dodder Flood Risk Management

The Study is project managed by Dublin City Council and funded by the OPW.

The key outputs from the Study were flood hazard and risk maps and a "Catchment Flood Risk Management Plan". In South Dublin, the Whitechurch Stream Flood Alleviation Scheme has been identified by the OPW in the River Dodder CFRAMS Option Development Process and will progress in 2015/16. The scheme is estimated to cost in the region of €2million.

Minor SW Schemes – 2015

400mm SW upgrade on Church Road, Saggart                                                  		   €80,000
Scheme completed.

225mm SW installation in New Road, Clondalkin                                                     	 €100,000

At contract stage.

225mm SW upgrade on Monastery Road Clondalkin                                                            €100,000

Archaeology on site currently being addressed

Progressing the Anti-erosion works on Dodder near Templeogue LTC with the OPW.          €80,000

Works on River Dodder bank stabilisation at Templeogue Tennis Club have been completed.

225mm SW installation in Ballycullen Oldcourt Road above Hunters Crescent

Contract €20,000 (excl. V.A.T.) at contract stage.                                                                   €25,000

PROGRAMME 4: DEVELOPMENT MANAGEMENT

The pilot signs for the County Signage plan have been installed and a roll out plan for 2016 agreed at SPC.

Investment in Grange Castle Business Park is continuing with the completion of the central carriageway.

The Tourism Strategy has been launched and the key projects at the Round Tower and the Mountains flagship advanced.

PROGRAMME 5: ENVIRONMENTAL SERVICES

Newcastle Burial Grounds Islamic Foundation of Ireland

Construction to commence in Q.3 2015							€150,000

Retaining wall - Saggart Cemetery

Tender process commenced.									  €75,000

PROGRAMME 6: RECREATION AND AMENITY

Play-space Development Programme

Continuation of implementation of play space programme with 8 play spaces completed.  There are 14 proposed sites on the 2015 Playground Construction Programme: 3 sites are under construction, 2 consultations were unsuccessful and consultations have commenced on 8 of the sites on the 2015 Programme.

Tymon Park Playground Refurbishment

Draft design being finalised. Tender to issue late 2015.

Provision of Allotments & Facilities

Corkagh Allotments Scheme. Draft Design completed for a 100 unit site. Brief for path tender and perimeter railing under preparation.  Tender to issue end of October 2015.

Mt Carmel Park, Dodder Valley Development (Firhouse Road Section)

Draft Part 8 plans have been prepared. An Appropriate Assessment and an Environmental Impact Assessment will be prepared for this draft proposal before going to full Public Consultation under the Part 8 Public Consultation process

Sports Pavilion Programme

Pavilion Strategy and construction programme agreed at July 2015 Council Meeting with design work carried out Q.3 2015.

Design for a modular system for the 3 priority locations at Dodder Valley Old Bawn, Griffeen Valley Park and Corkagh Park are being advanced. It is expected that the Part 8 Process for these pavilions will be initiated at the October Council Meeting.

Corkagh Park Improvement Works

This project is for the improvement of the access road and car park from the Outer Ring Road entrance and for the creation of a new pedestrian and cycle path From the St Johns Road side of the park to separate park users from Depot maintenance traffic.  The tenders for this work will be advertised in October 2015

Griffeen Valley Park surfacing & marking of Leisure Centre car park

Car park survey completed. Draft Design completed. Brief for tender under preparation. Tender to issue October 2015.

Dublin Mountains Way Access Improvement (Kiltipper)

Scoping design completed. Full design brief in preparation. Work can however commence on path improvements and quotation for path improvements to issue October 2015. Consultation with local residents will continue in respect of the Carpark proposal.

Clondalkin Equine Project

Application for funding for an Urban Horse Project has being finalised and a meeting with representatives of the DAFM will be convened to discuss the application. Part 8 drawings have been prepared by the Architectural Services Dept., and it is intended that a report will be presented to the Elected Members of the Clondalkin ACM at an informal meeting prior to going to formal public consultation stage in mid-October for decision of Council in December 2015.

Public Realm enhancement at Swiftbrook Estate

Design parameters have been agreed with residents. Draft Design completed. Quotation request to issue October 2015.

LEADER Seed Funding

Closing Date for LEADER Programme 15th May - Discussions between SDCC, Fingal and Dunlaoire Rathdown County Council Continuing.

Rathcoole Courthouse

Awaiting LEADER call for funding.

Jobstown (Kiltalown) All Weather Pitch Refurb

Management Company not in a position to apply for Sports Capital Grant but are preparing for future Scheme.

Libraries

The planned investment programme in the library infrastructure is being advanced.

A tender process is under way in respect of a new mobile library.