## Sheet1
Property Number | Clerk of Works Report * | EHO Report | Remedial Works Required
1 | Lack of air movement throughout this apartment. | Inspected. Walls dry lined to front of the house, problem cold wall onto shared hallway. Trickle vents into internal window frame
| Install a wall vent in the kitchen as the window trickle vent is not sufficient |  | KITCHEN: Install a wall vent in the kitchen as the window trickle vent is not sufficient
| Install a cooker extractor fan to remove water vapour when cooking. |  | KITCHEN: Install a cooker extractor fan to remove water vapour when cooking.
| Install ducting from the cooker hood to the external air or wall expeller. |  | KITCHEN: Install ducting from the cooker hood to the external air or wall expeller.
| Bedroom No 1- Install insulated plasterboard on the party wall as this wall backs onto an unheated common stairwell. |  | BEDROOM No 1- Install insulated plasterboard on the party wall as this wall backs onto an unheated common stairwell.
| Bedroom No 2- Install insulated plasterboard on the party wall as this wall backs onto an unheated common stairwell. |  | BEDROOM No 2- Install insulated plasterboard on the party wall as this wall backs onto an unheated common stairwell.
| Bathroom – confirm that the current mechanical wall extract ventilator is capable of extracting at a rate of 15 litres per second if it is not replace mechanical fan as there is no window in this bathroom and this will reduce the free moisture in this apartment. |  | BATHROOM – confirm that the current mechanical wall extract ventilator is capable of extracting at a rate of 15 litres per second if it is not replace mechanical fan as there is no window in this bathroom and this will reduce the free moisture in this apartment.
Photographs are available on file. Tal 37/F ber cow/cow reports/Balgaddy 2015
2 | He youngest child in this apartment is nine months old and has a hearth problem which has resulted in two open heart surgeries. | No Access Card Left 15/6/15 | Kitchen- Install a wall vent in the kitchen as the window trickle vent is not sufficient
| Both parents are smokers and the air on the morning of our inspection was filled with smoke. | Trickle vents into internal window frame | Kitchen - Install a cooker extractor fan to remove water vapour when cooking.
| No wall vents were present in the external walls of this unit. |  | Kitchen - Install ducting from the cooker hood to the external air or wall expeller.
| Several window trickle ventilators in the double glazed units were in the closed position during the inspection. |  | Bedroom No 1- Install a non- controllable wall vent.
| All trickle vent in the window were restricted by roller blinds or curtains which has reduced their effectiveness of ventilation. |  | Bedroom No 2- Install a non- controllable wall vent.
Bathroom - Install a non- controllable wall vent.
Bathroom - Install a mechanical wall extract ventilator is capable of extracting at a rate of 15 litres per second as this will reduce the free moisture in this apartment.
Bathroom – remove timber cabinet on bathroom window board to allow window to be opened after showering to reduce the flow of free moisture throughout this apartment.
SDCC Mechanical inspector to investigate the position of the mount mounted gas flue.
3 | No wall vents were present in the external walls of this unit. | Inspected. Problem cold wall onto shared hallway. Trickle vents into internal window frame. Extractor fan not ducted and not working, air circulation issues. | Lack of air movement in the common stairwell.
| Several windows were opened approx 50mm before and during the inspection. |  | Lack of air movement throughout this apartment.
| Several window trickle ventilators in the double glazed units were in the open position during the inspection. |  | Install a wall vent in the kitchen as the window trickle vent is not sufficient
| Mould recorded at interface of wall and ceiling in bedroom No1 (Front) |  | Install ducting from the cooker hood to the external air or wall expeller.
| Mould recorded above the kitchen wall units in kitchen. |  | Bedroom No 1- Install insulated plasterboards on the shared wall between the unheated common stairwell and bedroom no 1.
| Clothes horse located in the bathroom. |  | Bathroom – Install a ceiling mechanical extract ventilator which should be capable of extracting at a rate of 15 litres per second.
No wall vent throughout this unit.
No ducting from the cooker hood to the external air.
No ceiling mechanical extract ventilator present which should be capable of extracting at a rate of 15 litres per second
4 | No wall vents were present in the external walls of this unit. | Inspected. No Extractor fan. Air circulation issues. Maintenance issue ongoing in the bathroom to be completed. Trickle vents into internal window frame. Lead flashing to external stairs missing from bottom half of stairwell. | Kitchen -Install a wall vent in the kitchen/Lounge as the window trickle vent is not sufficient
| Several windows were opened approx 50mm before and during the inspection. |  | Kitchen Install ducting from the cooker hood to the external air.
| Several window trickle ventilators in the double glazed units were in the open position during the inspection. |  | Bedroom No 1- Install insulated plasterboard on walls of the bedroom
| Mould recorded at interface of wardrobe and external wall in bedroom No1 (Front) |  | Install vent in the bedroom walls.
| Mould recorded above the skirting boards in the small bedroom No 2. |  | Bedroom No 2- Install insulated plasterboard on walls of the bedroom
| No ducting from the cooker hood to the external air. |  | Install vent in the bedroom walls.
| Bathroom- No ceiling mechanical extract ventilator present which should be capable of extracting at a rate of 15 litres per second. |  | Bedroom 3 -Fibre cement board which is used on the bedroom walls is loose and rattles in the wind. The tenant stated that the bedroom is extremely cold in winter.
| Kitchen – No cooker extractor fan to extract the air. |  | Bathroom – Install a ceiling mechanical extract ventilator which should be capable of extracting at a rate of 15 litres per second.
Fibre cement board which is used on the bedroom walls is loose and rattles in the wind. The tenant stated that the bedroom is extremely cold in winter.
5 | No wall vents were present in the external walls of this unit. | Inspected. Maintenance issue ongoing at upper floor bedroom which is impacting on the master bedroom, air circulation issues. Trickle vents into internal window frame. | Kitchen -Install a wall vent in the kitchen as the window trickle vent is not sufficient
| Several windows were before and during the inspection. |  | Kitchen - Install ducting from the cooker hood to the external air or wall expeller.
| Several window trickle ventilators in the double glazed units were in the open position during the inspection. |  | Bathroom – Install a ceiling mechanical extract ventilator which should be capable of extracting at a rate of 15 litres per second.
| No extractor fan from the cooker hood to the external air. |  | Bedroom No 3- Install ceiling insulation at the interface of ceiling and external wall.
| No ducting from the cooker hood to the external air. |  | Bedroom 3 - Wall damp under the window board recorded 80 Tramex moisture encounter plus. Note that the audio alert sounds when the relative readings are over 50 on the analog dial, this would indicate high moisture capable of supporting microbial growth on the walls.
| Bathroom- No ceiling mechanical extract ventilator present which should be capable of extracting at a rate of 15 litres per second |  | Bedroom 3- Design problem with the interface of the two widows at a 90º angle.
Bedroom 3- Design problem with the interface of the two concrete cills at a 90º angle.
Bedroom 3- Design problem with the DPC of the two concrete cills at a 90º angle.
6 | No wall vents were present in the external walls of this unit. | EHO recently submitted report to Housing Dept at the request of Deputy Joanne Tuffy TD | Kitchen - Install a wall vent in the kitchen/Lounge as the window trickle vent is not sufficient
| Several windows were opened approx 50mm before and during the inspection. |  | Kitchen -Install ducting from the cooker hood to the external air.
| Several window trickle ventilators in the double glazed units were in the open position during the inspection. |  | Bedroom No 1- Install insulated plasterboard on walls of the bedroom
| Mould recorded above the skirting boards in the small bedroom No 2. |  | Bedroom No 2- Install insulated plasterboard on walls of the bedroom
| No ducting from the cooker hood to the external air. |  | Install vent in the bedroom walls.
| Bathroom- No ceiling mechanical extract ventilator present which should be capable of extracting at a rate of 15 litres per second. |  | Bedroom 3 - Fibre cement board which is used on the bedroom walls is loose and rattles in the wind. The tenant stated that the bedroom is extremely cold in winter.
| Kitchen – No cooker extractor fan to extract the air. |  | Bathroom – Install a ceiling mechanical extract ventilator which should be capable of extracting at a rate of 15 litres per second.
Fibre cement board which is used on the bedroom walls is loose and rattles in the wind. The tenant stated that the bedroom is extremely cold in winter
7 | No wall vents were present in the external walls of this unit. | nspected. No Extractor fan. Air circulation issues. Maintenance issue ongoing in the bathroom to be completed. Trickle vents into internal window frame. Lead flashing to external stairs missing from bottom half of stairwell. | Lack of air movement in the common stairwell.
| Several windows were opened approx 50mm before and during the inspection. |  | Lack of air movement throughout this apartment.
| Several window trickle ventilators in the double glazed units were in the open position during the inspection. |  | Mould above the kitchen wall presses is caused by a cold bridge. The external RWP hopper head is of light steel construction and this is the cause of the cold bridge which can be remedied by installing insulation plasterboard above the wall presses.
| Mould recorded at interface of wall and ceiling in bedroom No1 (Front) |  | Install a wall vent in the kitchen as the window trickle vent is not sufficient
| Mould recorded above the kitchen wall units in kitchen. |  | Install ducting from the cooker hood to the external air or wall expeller.
| Clothes horse located in the bathroom. |  | Bedroom No 1- Install ceiling insulation at the interface of ceiling and external wall.
| No wall vent throughout this unit. |  | Bathroom – Install a ceiling mechanical extract ventilator which should be capable of extracting at a rate of 15 litres per second.
No ducting from the cooker hood to the external air.
No ceiling mechanical extract ventilator present which should be capable of extracting at a rate of 15 litres per second
8 | No wall vents were present in the external walls of this unit. | Inspected. No extractor in kitchen, air circulation issues. Trickle vents to external window frame. | Lack of air movement in the common stairwell.
| Several windows were opened approx 50mm before and during the inspection. |  | Lack of air movement throughout this apartment.
| Several window trickle ventilators in the double glazed units were in the open position during the inspection. |  | Mould above the kitchen wall presses is caused by a cold bridge. The external RWP hopper head is of light steel construction and this is the cause of the cold bridge which can be remedied by installing insulation plasterboard above the wall presses.
| Mould recorded at interface of wall and ceiling in bedroom No1 (Front) |  | Install a wall vent in the kitchen as the window trickle vent is not sufficient
| Mould recorded above the kitchen wall units in kitchen. |  | Install ducting from the cooker hood to the external air or wall expeller.
| Clothes horse located in the bathroom. |  | Bedroom No 1- Install ceiling insulation at the interface of ceiling and external wall.
| No wall vent throughout this unit. |  | Bathroom – Install a ceiling mechanical extract ventilator which should be capable of extracting at a rate of 15 litres per second.
| No ducting from the cooker hood to the external air. |  | Kitchen - Install cooker extractor fan to remove water vapour when cooking
No ceiling mechanical extract ventilator present which should be capable of extracting at a rate of 15 litres per second
9 | No wall vents were present in the external walls of this unit. | No Access Card Left 15/6/15 | Lack of air movement throughout this top floor apartment.
| Several window trickle ventilators in the double glazed units were in the closed position during the inspection. | Trickle vents into internal window frame. | Kitchen- Install a wall vent in the kitchen as the window trickle vent is not sufficient
| All trickle vent in the window were restricted by roller blinds or curtains which has reduced their effectiveness of ventilation. |  | Install a cooker extractor fan to remove water vapour when cooking.
Install ducting from the cooker hood to the external air or wall expeller.
Bedroom No 1- Install a non- controllable wall vent.
Bedroom No 2- Install a non- controllable wall vent.
Bathroom - Install a non- controllable wall vent.
Bathroom - Install a mechanical wall extract ventilator is capable of extracting at a rate of 15 litres per second as this will reduce the free moisture in this apartment
10 | No wall vents were present in the external walls of this unit. | Sick child in the house, Card left to make appointment at a later stage. | Lack of air movement throughout this ground floor apartment.
| Several window trickle ventilators in the double glazed units were in the closed position during the inspection. | Trickle vents to external window frame. | Kitchen- Install a wall vent in the kitchen as the window trickle vent is not sufficient
| All trickle vent in the window were restricted by roller blinds or curtains which has reduced their effectiveness of ventilation |  | Install a cooker extractor fan to remove water vapour when cooking.
Install ducting from the cooker hood to the external air or wall expeller.
Bedroom No 1- Install a non- controllable wall vent.
Bedroom No 2- Install a non- controllable wall vent.
Internal soil stack boxing to be removed and investigated as we recorded high moisture reading at the interface of the stack and the concrete floor.
Bathroom - Install a mechanical wall extract ventilator is capable of extracting at a rate of 15 litres per second as this will reduce the free moisture in this apartment