## Sheet1
2016 - 2018 Capital Programme - Update May 2016
Project Description | Update
Housing Construction Programme | As reported at the April meeting.
Grange Housing Lands | Outline Masterplan to be competed by June for discussion with members.
Tallaght Energy Cluster | EU funding application outcome should be known by late summer 2016.
Villages Programme | Rathcoole , Newcastle, Rathfarnham, Tallaght and Lucan Phase 1 for completion in 2016.
Village Signage | Pilot completed in Tallaght, will be extended to Lucan in 2016
County Signage | A Countywide Tourism And Associated Directional Signage Programme will be devised as part of the Tourism Branding Strategy commissioned in March 2016.
Pavillions Programme | Tender issued 18th April - Oldbawn complete Q4 2016, Griffeen & Corkagh Q1 2017.
Flexible Sports Spaces | Research currently being undertaken by sports officers - pavillion design build exercise will also be informative.
Playspace Programme | As notified, a further 12 at various stages of consultation.
3rd Party Sports Capital Projects | St Judes, Templeogue Utd.,Lucan Harriers and Lucan Utd. - design consultants tenders received and being assessed.
Equine Project Clondalkin | Closing date for tenders 17th May - completed by November 2016.
Dodder Valley\ Mount Carmel | Consultants appointed to prepare an ecological impact assessment.
Roundabout Sponsorship Programme | Phase 1 Tenders now being examined.
N81 Landscape Enhancement | Landscape architects appointed 13/4/16.
Tourism Studies | Camac/Corkagh currently out to tender - Marketing and Branding awarded April 2016. Rathfarnham Castle buildings - conservation study tender just issued.
Annual Roads Programme | Programme agreed by Council in March including parks roads and housing estates.
R120/Nangor Road | Tenders being assessed - to go to construction October 2016.
Greenhills/Ballymount | To be completed October 2016
Dodder Valley Greenway | Part 8 by year end - works Q1 2017
Grange Road Plaza | Completed October 2016.
Access Road Exchange Hall Lands | Part 8 Q3.
Ballycullen Flood Alleviation Scheme | To commence July 2016.
Poddle Scheme | Design to be completed this summer.
Camac Scheme | Design consultants to be appointed 2016.
Grangecastle Business Park | Future expansion in planning - works to Castle and associated Pocket Park at design - expression of interest in office development to be advertised May 2016.
Templeogue House | Cost being independently reassessed - report to members by June 2016.
Rowlagh Library | On site by year end.
Tymon Library | Part 8 june 2016.
Palmerstown Digital Hub | To open Q4.
Lucan Pool | Approved in principle - design consultants to be appointed by June.
Adamstown Community Hall | Detail design consultation underway.
Round Tower Clondalkin | On site - open spring 2017.
Tallaght Stadium - New Stand | Design discussion underway - tender by year end.
Dublin Mountain Gateway | MOU for Phase 2 (EIS) agreed with Coillte - hope to complete planning in 2016.
Heritage Projects €100k | Under consideration by Heritage Forum.