## May 2016
South Dublin Local Economic & Community Plan 2016-2021 - SPC Update May 2016
Infrastructure | Goal 1: Maintain and develop existing enterprise to support and improve the economic infrastructure of South Dublin County
Objective | Action | Timetable | Collaborators | Measurement / Target for 2016 | May 2016 Update (where applicable)
Support the development of development plans for enterprise character areas | Develop a marketing strategy for enterprise character areas | Medium Term | LEO | Develop marketing strategy. | Enterprise Strategy to identify strengths and character areas-conusltant appointed May 2016.
|  |  | South Dublin Chamber | Establish work programme
SDCC
| Develop information material to encourage and support national and local business to locate and grow in the County | Short Term | LEO | Establish and populate database of relevant information. | Planned for Q3/4
South Dublin Chamber
SDCC
Develop and support models of collaboration between existing business | Build and develop the sustaining business programme in conjunction with South Dublin Chamber and LEO | Ongoing | South Dublin Chamber | Maintain programme, focus on exporters | Sustainable Business Programme supported for 2016. Survey of exporters to be undertaken (in Q3/4?)
LEO
SDCC
| Develop an opportunities register for people looking to start and develop small business within the County | Short Term | South Dublin Chamber | Register developed | Will be addressed in Enterprise Strategy – consultant appointed.
LEO
South Dublin County Council
Work with local and regional third level institutes to develop opportunities for company start-ups | Develop an enhanced collaboration between the third level institutes, Synergy centre, South Dublin Chamber and LEO to identify and support a programme for start-up and step up business. | Medium Term | I.T. Tallaght, Ryan Institute, Synergy, South Dublin Chamber, LEO | Develop model for identifying physical locations for start-up, step up facility and suitable tenants. | Microenterprise Development Fund and Microenterprise Start-up Support launched.
Examination of industrial areas underway to target supports
Preliminary discussions with ITT and Synergy Centre about partnering.
Support the development of outdoor and rural enterprise. | Develop a programme to support tourism product development in conjunction with Fáilte Ireland | Ongoing | South Dublin County Council | Identify tourism product within the County and potential for development based on tourism strategy focus. | Consultants appointed for Tourism marketing and branding of County. County Tourism network event held in Tallaght Stadium,
|  |  | LEO | Develop soft business supports for tourism companies in conjunction with Fáilte Ireland
Fáilte Ireland
| Seek to develop links between local food producers and local restaurants and food retailers. | Ongoing | LEO | Identify linkage between food producers and local retailers. | Being explored with Dublin Food Chain/Bord Bia
South Dublin Chamber
Bord Bia
Goal 2: Transform older industrial areas into high quality centres for enterprise
Objective | Action | Timetable | Collaborators | Measurement / Target for 2016 | Update
Develop network of businesses within older industrial areas | Develop network of firms based on the rollout of the Business support grant supports. | Ongoing | LEO | Establish pilot network in Cookstown and JFK areas | Cookstown Area Improvement Scheme approved – opportunity to develop network with roll-out of works
South Dublin Chamber
Identified local businesses
| Identify key issues facing business in older industrial estates | Ongoing | LEO | Identify initial programme based on established BSG programme | Cookstown project will be basis for initial discussions followed by other projects as they emerge
South Dublin Chamber
Identified local businesses
Identify opportunities for the development of start-up/ step up facilities | Develop existing collaboration model between LEO, the Chamber, local third level institutes and South Dublin County Partnership to identify location for start-up/ Step-up facilities | Ongoing | LEO | Identify potential location for initial start-up/ step-facility. | Location(s) to be identified. Promoting ACE start up space via LEO website.
|  |  | South Dublin Chamber | Scope out physical requirements.
|  |  | South Dublin County Partnership | Identify and establish management structure.
Third Level institutes ( ITT, Ryan Institute, Synergy)
Identify specific infrastructural supports for re-development of older industrial areas | Identify key existing infrastructure within Older industrial estates and identify key infrastructure development opportunities particularly power and telecoms facilities | Ongoing | South Dublin County Council | Map existing services within older industrial areas with above average vacancy rates, JFK, Cookstown, Ballymount. | Q3 - 2016 - Examine MV Power, Fibre, Gas, Water and Wastewater Infrastructure deficits in particular
Service Providers
South Dublin Chamber
Encourage and promote programme of physical supports for the improvement of older industrial areas | Build on work carried out for the Business Support Grant and work with local businesses to identify key interventions required | Ongoing | South Dublin County Council | Identify rolling programme of key physical interventions required. | Industrial Area Improvement Scheme launched (under Business Support Fund). From 2015 - JFK Drive Improvement, Cloverhill Ind Estate Improvement, Old Belgard Road Improvement and Ballymount Road Lower Improvement at different stages of planning and development.
South Dublin Chamber
Goal 3: Strengthen the economic fabric of our towns and villages
Objective | Action | Timeline | Collaborators | Measurement / Target for 2016
Develop and maintain communication channels with local retail/ business | Develop a support network for local retailers and identify key supports required by retailers | Ongoing | South Dublin Chamber LEO | Establish pilot programme with the niche retail sector and investigate the development of an online platform for promoting local retail | An online platform for South Dublin County retailers under development. Consultation/testing being organised with representative sample of retailers.
Local retailers
Support the rollout of the South Dublin County Tourism Strategy | Support identified tourist product development: | Ongoing | South Dublin County Council | Establish programme for rollout of village wayfinding signage. Install new signage in villages. | Map design tender prepared for publication for roll-out of next phases of Wayfinding project as agreed with SPC. Action Plan for Tallaght Heritage Trail agreed. Routing, panel locations and features. Public realm and enforcement works ongoing. Industry submission before SPC May 11th for review. Recommendation for industry sub group to be formed to finalise same.
| - Rollout County wayfinding strategy |  | South Dublin Chamber | Develop pilot heritage trail in Tallaght
| - Initiate heritage village trails |  | Fáilte Ireland | Identify and support development of festival with regional draw.
Tourism Implementation Group
Support a marketing strategy for villages within the County | Develop unique character for each village, particularly for niche retailing | Short Term | South Dublin County Council | Identify marketing provider to develop marketing programme | Consultants appointed for Tourism marketing and branding of County.
South Dublin Chamber
| Develop and support village improvements | Short Term | South Dublin County Council | Continue shop front grant | 14 applications for 2016 shop front grant. Construction of Round Tower centre commencing in June 2016. Dublin Mountains Project application being prepared for An
|  |  | South Dublin Chamber | Identify wi-fi improvements
Continue to develop round tower and Dublin Mountain flagship projects.
ENTERPRISE and EMPLOYMENT | Goal 4: Develop new and existing enterprises with significant employment, capital, income or growth potential
Objective | Action | Timetable | Collaborators | Measurement / Target for 2016 | Update
Support initiatives to improve the availability of serviced sites for large inward investment projects | Identify serviced land priorities | Ongoing | South Dublin County Council Industrial Development Agency | Identify priorities for servicing of sites | Ongoing - Improvements to Power network, Water network, Wastewater network, Roads Infrastructure and Fibre capacity are at different stages of planning
| Further develop Grange Castle Business Park | Ongoing | South Dublin County Council Industrial Development Agency | Plan for the continued development of Grange Castle
Continue to develop and improve a dedicated marketing strategy to attract large scale inward investment projects | Build on Grange Castle marketing information | Ongoing | South Dublin County Council Industrial Development Agency | Enhance and expand Council Business pages on Website and related promotional material | Updated material being prepared
Identify and support improved infrastructure required to support large scale inward investment projects | Develop a detailed understanding of infrastructure needs of large inward investment projects. | Ongoing | South Dublin County Council Industrial Development Agency | Support 220kv upgrade. | Ongoing - Improvements to Power network, Water network, Wastewater network, Roads Infrastructure and Fibre capacity are at different stages of planning. Development of Master Plan for lands to the west of Grange Castle
| Work with service providers to meet identified needs. |  | Service Providers | Examine development options for Grange Castle and environs
Support the development of improved links between local third level institutions and large local employers | Develop network between major employers and third level institutions. | Ongoing | South Dublin County Council, South Dublin Chamber, Third level institutions. | Identify participants in network and establish pilot network group. | Planned for Q3/4
Goal 5: Improve the quality and diversity of employment in the County
Objective | Action | Timetable | Collaborators | Measurement / Target for 2016 | Update
Support the development and rollout of a Regional Jobs Strategy for Dublin | Actively support the development of the regional jobs strategy | Ongoing | South Dublin County Council | Provide input and support the development of a regional jobs strategy | Regional Action Plan for Jobs launched and regional co-ordinator appointed. Co-ordinator will work with Enterprise Strategy consultants and 4 Dublin LEOs to progress RAPJ commitments.
LEO
Department of Jobs and Enterprise
Develop a training programme based on the needs of local employers | Identify training needs and develop mechanism for delivery, incorporating certification where possible. | Ongoing | LEO, | Develop and rollout training programme based on 2015 survey results. | Bespoke training programme funded by Business Support Fund for local businesses is ongoing.
South Dublin Chamber
Local business
Develop training supports to enhance and develop exporting companies within the County | Identify supports for exporting companies and develop network to support exporting companies within the County | Ongoing | LEO | Survey exporting companies to identify future training needs | To be organised in conjunction with SD Chamber for (Q3/4?)
South Dublin Chamber
Local Exporters
Work with local stakeholders to promote upskilling of local workforce | Identify particular skill deficits | Ongoing | LEO | Identify programme to tackle skill deficits including existing and emerging apprenticeship opportunities | Enterprise Strategy will address current and future skills gap together with actions to meet these.
South Dublin Chamber I.T. Tallaght
Solas
Social Enterprise centres
Goal 6: Actively engage with other Authorities and Agencies in the continued economic development of the Dublin region
Objective | Action | Timetable | Collaborators | Measurement / Target for 2016 | Update
Support the continued collaboration with other agencies and authorities to develop and support economic enterprise | Continue to develop and deepen collaboration with the Industrial Development Agency | Ongoing | Industrial Development Agency | Develop protocols for identifying key inward development site size and location | Marketingreviewed and update-kept under constant review
Continue to develop and enhance the marketing of Grange Castle Business Park to prospective clients
| Continue to develop and deepen collaboration with Enterprise Ireland | Ongoing | Enterprise Ireland | Develop and expand models of collaboration with Enterprise Ireland | Ongoign liaison with agencies.
Support the identification and development of Key regional infrastructure provision | Work with state agencies to support business case for delivery of key infrastructure | Ongoing | Irish Water | Identify key regional infrastructure requirements | Master Plan for lands to West of Grange Castle Business Park - Tender Q3
Eirgrid
Dublin Local Authorities
National Transport Agency
National Roads Authority
Goal 7: Develop micro enterprise, community economic development and start-ups
Objective | Action | Timetable | Collaborators | Measurement / Target for 2016 | Update
Support the ongoing development of the South Dublin LEO as a first stop shop for the development of enterprise within the County. | To support the development of start-up and small business expansion in the County and to maximise the development of enterprise in South Dublin | Ongoing | Enterprise Ireland | Develop a County Enterprise strategy for South Dublin County. | Consultant appointed in May 2016 to develop Enterprise Strategy.
|  |  | South Dublin Chamber | Develop a training support programme based on the 2015 business survey. | Bespoke training programme funded by Business Support Fund for local businesses is ongoing (76 participants in Q1 2016)
|  |  | LEO | Maximise the take up of allocated funding measures under measure one and two programmes | Ongoing delivery of M1 & M2 programmes by LEO. €188,700 approved for 13 projects in Q1 2016.
Support a network for the development of community economic development within the County | Identify key actors to be included in network and develop programme of work | Short Term | LCDC | Establish a network and develop programme of work to identify existing factors most inhibiting community economic development | Planned for Q3/4
LEO
Social Enterprise Centres South Dublin Chamber
Support the development of a network for the promotion of social entrepreneurship in the County | Identify key actors to be included in network. | Short Term | LCDC, LEO, Social enterprise centres, Chamber, Social Entrepreneurs | Establish network of stakeholders to identify existing factors most inhibiting to the development of social enterprises | Planned for Q3/4