COMHAIRLE CHONTAE ÁTHA CLIATH THEAS

SOUTH DUBLIN COUNTY COUNCIL

# MEETING OF TALLAGHT AREA COMMITTEE (1)

Monday 16TH January 2006

H I (13)

## Report on Housing Construction Programme:

The up-to-date position of the construction programme for the County area is set out in the detail below: -

Completions in 2004 :-

Tallaght Area

| Scheme Name | No. of Units | Completion Dates |
| --- | --- | --- |
| Cushlawn, Phase 1 | 6 | February 2004 |
| Cushlawn, Phase 1 | 5 | March 2004 |
| Cushlawn, Phase 1 | 17 | September 2004 |
| Tymon Park | 2 | April 2004 |
| Bolbrook | 11 | June 2004 |
| Kilcarrig, Phase 2 | 4 | August 2004 |
| Russell Square | 5 | November 2004 |
| Killcarrig Phase 2 | 4 | December 2004 |
| Marlfield (Part V) | 27 | December 2004 |
| Sub Total | 81 |  |

Lucan/ Clondalkin Area

| Scheme Name | No. Of Units | Completion Dates |
| --- | --- | --- |
| Oldchurch | 4 | February 2004 |
| Balgaddy “A” | 84 | February 2004 |
| Balgaddy "B" | 44 + (24 Voluntary Units) | March 2004 |
| ### Sub Total | 132 (+24) |  |

Terenure/Rathfarnham Area

| Scheme Name | No. Of Units | Completion |
| --- | --- | --- |
| Whitechurch Phase 3 | 7 | September, 2004 |
| Whitechurch Phase 3 | 2 | December, 2004 |
| ### Sub Total | 9 |  |

Completions in 2005 :-

Tallaght Area

| Scheme Name | No. of Units | Completion Dates |
| --- | --- | --- |
| Russell Square | 8 | January 2005 |
| Russell Square | 39 | February 2005 |
| Bawnlea | 7 | March 2005 |
| Jobstown Village Core | 10 | March 2005 |
| Cushlawn, Phase II | 16 | May 2005 |
| Russell Square | 47 | June 2005 |
| Cushlawn Phase 2 | 2 | June 2005 |
| Russell Square | 16 | July 2005 |
| Cushlawn Phase 2 | 5 | September 2005 |
| Daletree, Ballycragh | 8 | September 2005 |
| Fettercairn Village | 7 | October 2005 |
| Fettercairn Village | 6 | November 2005 |
| Cushlawn Phase 2 | 8 | November 2005 |
| Fettercairn Village | 14 | December 2005 |
| Sub Total | 193 |  |

Lucan / Clondalkin Area

| Scheme Name | No. Of Units | Completion |
| --- | --- | --- |
| Harelawn (SH 235) | 10 | December 2005 |
| Moorfield (SH220) | 14 | December 2005 |
| Liscarne (SH 188) | 38 | December 2005 |
| Sub Total | 62 |  |

Terenure/Rathfarnham

| Scheme | No. Of Units | Completion |
| --- | --- | --- |
| Whitechurch Phase 3 | 4 | April, 2005 |
| Whitechurch Phase 3 | 4 | May, 2005 |
| ### Whitechurch Phase 3 | 2 | July 2005 |
| ### Sub Total | 10 |  |

### On Site:-

### Tallaght Area

| Scheme Name | No. of Units on Site | Completion Dates |
| --- | --- | --- |
| Fettercairn Village, Phase 1 Includes extension to creche & community facility | 14 | (In Phases)Nov 05 - Feb 06 |
| Avonbeg, Phase 3 | 47 | In phases early February, 2006 |
| Fortunestown B, Phase 2 | 66 (+52 Vol. Units) | June, 2006 |
| Fortunestown B, Phase 4 | 120 | January 06 , August, 2006 |
| Fortunestown B, Phase 1 | 110 | May, 2006 |
| Deer Park (Joint Venture) | 119 | (In phases) From February 2006 |
| Daletree (Part 5/Joint Venture) | 27 | Late 2006 |
| Hunterswood (Part V) | 9 | Late 2006 |
| Brookfield Village+ Community Facility | 16 | May 2006 |
| Deerpark (Part V) | 36 | February 2006 |
| Belfry | 35 | December 2006 |
| Belgard Square | 44 |  |
| Sub.Total | 643 |  |

Lucan / Clondalkin Area

| Scheme Name | No. Of Units | Completion |
| --- | --- | --- |
| Moorfield (SH 220) | 30 | January / February 2006 |
| Shancastle Ph,1(SH 243) | 26 | January/February 2006 |
| Balgaddy “C” (SH 161) | 85 + (65 Voluntary Units) | September 2006 |
| Balgaddy “D” (SH 209) | 65 | Mid – End 2007 |
| Balgaddy “E” (SH 210) | 100 | May 2006 |
| Mayfield (SH 244) | 36 | February 2006 |
| Ballyowen Part V | 12 | Awaiting contracts |
| Sub Total 354 (+65 Voluntary Units) |  |  |

Tenders Recommended

Tallaght Area

| Scheme Name | No of Units |
| --- | --- |
| Kilcarrig Phase 3 (SH274) | Tender recommendation in the sum of €13,694,394 for the construction of 80 units by D&I Construction Ltd., Tyrell House, Main Street Blessington, Co Wicklow |
| Cushlawn Phase 3 (SH278) | Tender recommendation in the sum of €4,148,160 for the construction of 22 units by Owenbee Group, Unit 4, Fairways Mall, Donnabate, Co. Dublin |
| Sub Total | 102 |

Lucan / Clondalkin Area

| Scheme Name | No of Units |
| --- | --- |
| Kilcronan (SH 182) | Tender recommendation in the sum of €9,593,479 for the construction of 21 social housing units, 32 voluntary housing units (including Community Centre) by William F. Rowley ltd., 4A Villa Park Road, Blackhorse Avenue, Dublin 7. |
| ## St Finian’s ( SH 293) | Tender recommended in the sum of €578,896 for the construction of 4 housing units by Alan Doyle, 511 Orwell Park, Templeogue, Dublin 6W |
| ## Sub Total | 57 |

Terenure/Rathfarnham

| Scheme Name | No of Units |
| --- | --- |
| ## Whitechurch Phase 4 (SH242) | Tender recommended in the sum of €5,989,252 for the construction of 29 units and a Community Facility by Dunne Contracting Ltd., Unit 6A Block H, Centrepoint Business Park, Oak Road, Dublin 12 |
| ## Sub Total | 29 & Community facility |

Tenders being examined

Tallaght Area

| Scheme Name | No. Of Housing Units |
| --- | --- |
| Castlepark | 9(3 specially adapted units) |
| Sub Total | 9 |

Tender Production

Tallaght Area

| Scheme Name | No. of Housing Units |
| --- | --- |
| Kiltalown Green | 28 |
| Sub Total | 28 |

Lucan / Clondalkin Area

| Scheme | No. of Units |
| --- | --- |
| Rowlagh (SH 165) | 23 |
| ### Sub Total | 23 |

Part 8 Approved by Council:-

Tallaght Area

| Scheme Name | No. of Housing Units |
| --- | --- |
| Avonbeg Phase 4 (SH252) | 7 & St Muirins House |
| Sub Total | 7 |

Lucan / Clondalkin Area

| ### Scheme | No of Units |
| --- | --- |
| ## New Road Clondalkin ( SH 286) | 9(Part V option being considered) |
| Lindisfarne (SH 297) | 5 |
| Lealand (SH 279) | 7 |
| ## Sub Total | 21 |

At Concept/Design Stage:-

### Tallaght Area

| ### Scheme Name | ### Approx . No. Of Units |
| --- | --- |
| ### Fortunestown B, Phase3 | ### 120 |
| ### Fettercairn Villlage, Phase2 | ### 10 |
| ### Kilclare, Phase2 | ### 30 (concepts presented to Tallaght Area Committee Meeting 16/06//2003) |
| ### Kilclare Phase3 | ### 15 |
| ### Knockmore House (incl. 15 units for Bernardos) | ### 60 (concepts presented to Tallaght Area Committee Meeting 16/06//2003) |
| Whitestown Stream | - |
| Suncroft | - |
| Whitebrook Park | - (concepts presented to Tallaght Area Committee Meeting 20/09/2004) |
| ### Stocking Lane | -(concept under preparation) |
| ### Swiftbrook | -(concept presented to Tallaght Area Committee Meeting 08/12/04) |
| ### Rossfield Infill | Concepts being prepared |
| ### Fettercairn Phase 2 | Concept presented to Tallaght Area Committee 7th December 2005 |
| ### Castletymon | Concept presented to Tallaght Area Committee 7th December 2005 |
| ### Sub Total | 235 |

Lucan / Clondalkin Area

| Scheme | No. of Units |
| --- | --- |
| Nangor | 160 |
| Balgaddy B1 + Community Centre | 14 |
| ### Airlie Heights | 6 |
| ### Tony Kearns Motors Site, Palmerstown | Concept to be prepared |
| ### Balgaddy F | Approved plan under review |
| ### Sub Total | 180 |

Terenure / Rathfarnham

| Scheme | No. of Units |
| --- | --- |
| Whitechurch Avenue | Layout being prepared |
| Palmer Park | Preliminary concept to be prepared |

Other potential sites are also being examined.