COMHAIRLE CHONTAE ÁTHA CLIATH THEAS
SOUTH DUBLIN COUNTY COUNCIL

MEETING OF TALLAGHT AREA COMMITTEE 2

Monday, 23rd January  2006

QUESTION NO. 11

QUESTION: Councillor M. Daly

"To ask the Manager what progress has been made on the redevelopment of Tallaght Village?"

REPLY

There has been a considerable amount of development in the Village in Tallaght in the recent past. Most of the developments have been driven by the Urban Renewal Tax Incentive Integrated Area Plan (IAP). In the IAP, twenty vacant, derelict or underused sites were designated in the Town Centre for a range of tax incentives. Eight of those sites were located in the Tallaght Village/High Street area. The development on these sites has been as follows;

IAP Site No 1 Former Iceland site at the Tallaght Road: The construction of a 4-6 storey mixed commercial/residential development (27974 sq.m.) comprising 204 apartments, 6 retail units, a restaurant and a new pedestrian bridge. This development has recently started.

IAP Site No 2 and 4:  At the Greenhills Road Extension and the Tallaght Bypass: The 3-6 storey development consists of a mixed residential, office and retail development on a 1.8 ha. Site. Residential (85 apartments), Office 3,373 sq.m. retail 3824sq.m. with a new pedestrian street connecting the Village Green with the Greenhills Road Extension. Development has recently commenced.

IAP Site No3: Greenhills Road Extension north of the Main St: Mainly residential development ranging from 2 to 4 storeys over basement car parking containing 88 no. spaces.  The proposed development will consist of 1 no. Crèche, 2 no. retail units and 90 no. apartments. Development on the east side is almost complete and is due to commence on the east side shortly.

IAP Site No 4 (part of): The Laurels, Main St.: The development consists of a mixed-use commercial/residential development comprising 18 no. apartments and 2 no. retail units in two blocks as follows - front block with street frontage to be 3 storeys high plus penthouse level and rear block to be 4 storeys high plus penthouse level, all over a basement level car park. This development is at an advanced stage.

IAP Site No 6: There are a series of developments that have been completed in and around the Courthouse Square and the Old Blessington Road. These are;

- Brian O’Reilly Solicitors:  2-storey extension towards Courthouse Square with 2 shops on ground floor and offices on first floor and a first floor office extension at side facing Old Bawn Road. This development is completed.

- Hannah Homes: A two-storey shop with residential overhead has been constructed.

- The Probation Service: Construction of a new three storey office building for use by the Probation Service, over new 26 car basement car park with first floor link to existing Probation Service office building. This building is under construction.

- Irish Nationwide A two storey commercial extension has been constructed.

- Macari: 3-storey restaurant, office and residential development has been constructed.

All of the above developments will also have access from the Courthouse Square. When all of the developments are finished, the Council will undertake a new landscape and parking layout in Courthouse Square.

IAP Site No 8: This development consists of a 4 storey apartment block with a setback penthouse storey providing 106 apartments over the existing ground floor retail units, 157sq.m crèche at penthouse level, 3 new retail units,  (805 sq.m.  702 sq.m. and 584 sq.m. respectively)  to the rear of the existing retail centre over the remodelled 93 space basement car park and a new 5 level 369 space multi - storey car park above.

In addition to the above developments, the Council have a number of environmental improvements planned for Tallaght Village as part of the Urban and Village Renewal Scheme 2005-2006. The improvements the major refurbishment of the village core and the provision of new plazas and some further improvements at junction of Main St. and Old Bawn Road and the Zip Project which involves the creation of a dedicated pedestrian / cycle corridor linking the Luas Interchange to the Institute of Technology and Tallaght Village. The Zip project comprises of a high-quality hard and soft landscaped strip featuring assistive technology for orientation and information, particularly for the disabled.

The Tallaght Village area is also part of the Tallaght Masterplan area (The Master-plan is required to guide the future development of the Town Centre as the County Town and to facilitate the development of the extended and newly zoned Town Centre area following the recent adoption of the County Development Plan 2004 – 2010). The Masterplan process has involved two major consultation exercises and it is expected that the Draft Masterplan will go on display over the coming weeks.