## May 2016
South Dublin Local Economic & Community Plan 2016-2021 - SPC Update May 2017 (Economic Elements)
Infrastructure | Goal 1: Maintain and develop existing enterprise to support and improve the economic infrastructure of South Dublin County
Objective | Action | Timetable | Partners | 2017 Measurement / Target | Update
Support the development of development plans for enterprise character areas | Develop a marketing strategy for enterprise character areas | Medium Term | LEO | Develop & enhance local strengths and sectors identified in Dublin Regional Enterprise Strategy | 2017 Local Implementation Plan to build on Enterprise Strategy actions approved by SPC in Feb 2017.
South Dublin Chamber
SDCC
| Develop information material to encourage and support national and local business to locate and grow in the County | Short Term | LEO | Marketing material for business location in the County developed. | Development of updated promotional material included in work plan for 2017 Sustainable Business Programme.
South Dublin Chamber
SDCC
Develop and support models of collaboration between existing business | Build and develop the sustaining business programme in conjunction with South Dublin Chamber and LEO | Ongoing | South Dublin Chamber | Maintain programme, focus on exporters | Sustainable Business Programme supported for 2017. Exporting survey launched and exporting event held in March in conjunction with SD Chamber, IEA, BoI & LEO. Additional events, including Brexit specific event, being planned.
LEO
SDCC
| Develop an opportunities register for people looking to start and develop small business within the County | Short Term | South Dublin Chamber | Progress Business Opportunities Register with other DLAs | Business Opportunities Register model proposed in Enterprise Strategy - to be progressed with Dublin City Council under dublin.ie platform for the region.
LEO
South Dublin County Council
Work with local and regional third level institutes to develop opportunities for company start-ups | Develop an enhanced collaboration between the third level institutes, Synergy centre, South Dublin Chamber and LEO to identify and support a programme for start-up and step up business. | Medium Term | I.T. Tallaght Ryan Institute Synergy South Dublin Chamber LEO | Develop model for identifying physical locations for start-up, step up facility and suitable tenants. | Survey of vacant areas and engagement with owners ongoing in Cookstown & Ballymount. Tender on assessment of enterprise space provision in the County being prepared (proposed to get IT Tallaght in put once drafted). 11 Mircoenterprise Development Fund applications approved to date (potential invetsment of up to €750k).
Support the development of outdoor and rural enterprise. | Develop a programme to support tourism product development in conjunction with Fáilte Ireland | Ongoing | South Dublin County Council LEO Failte Ireland | Continue to develop the tourism product within the County and use tourism strategy to shape future development. Develop soft business supports for tourism companies in conjunction with Fáilte Ireland & other agencies. | Marketing Plan, tourism videos, website and social media launched. Contract to manage social media accounts being procured. Final Liffey Blueway Report due by end June 2017. Corkagh Report - Implementation Plan under development.
Establishment of tourism network for businesses being progressed throuh LEO to build on the three network events for tourism held by the County Promotion Unit in the last year.
| Seek to develop links between local food producers and local restaurants and food retailers. | Ongoing | LEO | Identify linkage between food producers and local retailers. | Dublin Food Chain & Food Academy programmes ongoing.
South Dublin Chamber
Bord Bia
Goal 2: Transform older industrial areas into high quality centres for enterprise
Objective | Action | Timetable | Partners | 2017 Measurement / Target | Update
Develop network of businesses within older industrial areas | Develop network of firms based on the rollout of the Business support grant supports. | Ongoing | LEO; South Dublin Chamber; Local Businesses; | Generate additiontal Area Improvement Scheme applications from business clusters in the County | Continued engagement with businesses to promote scheme with applications being progressed in Cherry Orchard IE, Avonbeg IE, Greenhills IE.
| Identify key issues facing business in older industrial estates | Ongoing | LEO; South Dublin Chamber; Local Businesses; | Identify initial programme based on established BSG programme | Survey of vacant areas and engagement with owners ongoing in Cookstown & Ballymount with a view to developing a position paper on required interventions.
Identify opportunities for the development of start-up/ step up facilities | Develop existing collaboration model between LEO, the Chamber, local third level institutes and South Dublin County Partnership to identify location for start-up/ Step-up facilities | Ongoing | LEO; South Dublin Chamber; South Dublin County Partnership; Third Level institutes (ITT, Ryan Academy; Synergy) | Identify potential location for initial start-up/ step-facility. | To be informed by tender on assessment of enterprise space provision in the County.
Scope out physical requirements.
Identify and establish management structure.
Identify specific infrastructural supports for re-development of older industrial areas | Identify key existing infrastructure within Older industrial estates and identify key infrastructure development opportunities particularly power and telecoms facilities | Ongoing | South Dublin County Council; Service Providers; | Examine MV Power, Fibre, Gas, Water and Wastewater Infrastructure deficits in particular | JFK - Proposed footpath extension works under consideration
Encourage and promote programme of physical supports for the improvement of older industrial areas | Build on work carried out for the Business Support Grant and work with local businesses to identify key interventions required. | Ongoing | South Dublin County Council; South Dublin Chamber; | Identify rolling programme of key physical interventions required. | Survey of vacant areas and engagement with owners ongoing in Cookstown & Ballymount with a view to developing a position paper on required interventions.
Goal 3: Strengthen the economic fabric of our towns and villages
Objective | Action | Timeline | Partners | 2017 Measurement / Target | Update
Develop and maintain communication channels with local retail/ business | Develop a support network for local retailers and identify key supports required by retailers | Ongoing | South Dublin Chamber LEO | Establish pilot programme with the niche retail sector and investigate the development of an online platform for promoting local retail | Discussions with Retail Excellence Ireland to develop retail support programme in South Dublin.
Local retailers
Support the rollout of the South Dublin County Tourism Strategy | Support identified tourist product development: | Ongoing | South Dublin County Council; South Dublin Chamber; Failte Ireland; Tourism Implementation Group; | Establish programme for rollout of village wayfinding signage. Install new signage in villages. Develop pilot heritage trail in Tallaght; Examine festival & event options for the County; | Current Failte Ireland audit will inform procurement for design and installation of visitor wayfinding and directional signage to attractions and Villages around County Dublin. Its recommendations are awaited before continuing with delivery of the South Dublin Village Wayfinding Programme and local attractions signage (including heritage trails). Gael Force held on Feb 18th 2017; Additional event options being explored.
- Rollout County wayfinding strategy
- Initiate heritage village trails
Support a marketing strategy for villages within the County | Develop unique character for each village, particularly for niche retailing | Short Term | South Dublin County Council; South Dublin Chamber; | Develop proposals for each village/town in conjunction with marketing consultants. | To form part of County Promotion Unit work programme for H2 2017 subject to resources,
| Develop and support village improvements | Short Term | South Dublin County Council; South Dublin Chamber; | Enhanced promotion of Shop Front Grant Scheme; Promotion of Town & Village Renewal Scheme; Progress identified tourism initiatives; | 30 shop front gtants received in 2017 (up >200% on 2016). Applicatoions being assessed. EOIs for Town & Village Renewal Scheme to be advertised in May 2017; Round Tower centre scheduled to open in June 2016 with Happy Pear engaged for managment of commercial aspects. Dublin Mtns: An Bord Pleanala determination awaited regarding planning process. Likely planning submission in July. Extensive information/engagement completed over Q1 and Q2. Project website established with updates published. Failte Ireland development stage grant awarded to Project.
ENTERPRISE and EMPLOYMENT: Goal 4: Develop new and existing enterprises with significant employment, capital, income or growth potential
Objective | Action | Timetable | Partners | 2017 Measurement / Target | Update
Support initiatives to improve the availability of serviced sites for large inward investment projects | Identify serviced land priorities | Ongoing | South Dublin County Council Industrial Development Agency | Identify priorities for servicing of sites | Eirgrid Plans for Grange Castle South now to progress as the parties involved in the judicial review finally made a settlement – S183 report to be presented at May Council Meeting. SDCC taking part in the National Braodband Plan Co development subgroup, meetings held every 2 months
| Further develop Grange Castle Business Park | Ongoing | South Dublin County Council Industrial Development Agency | Plan for the continued development of Grange Castle | Tender for Professional Services published on 27/03/2017, Submissions due back on 19/05/2017. Infrastructure Wireframe expected in Q3 2017
Continue to develop and improve a dedicated marketing strategy to attract large scale inward investment projects | Build on Grange Castle marketing information | Ongoing | South Dublin County Council Industrial Development Agency | Enhance and expand Council Business pages on Website and related promotional material | Material will be finalised to conincide with new design of Council website.
Identify and support improved infrastructure required to support large scale inward investment projects | Develop a detailed understanding of infrastructure needs of large inward investment projects. | Ongoing | South Dublin County Council Industrial Development Agency | Support 220kv upgrade. | Eirgrid project now progressing therefore Power upgrade expected in 2019. Publication of Construction Tender for R120/R136 Road Improvement Scheme Imminent . Tender for Professional Services published on 27/03/2017, Submissions due back on 19/05/2017. Infrastructure Wireframe expected in Q3 2017. Constant liaison with Fibre providers with regard to current and future provision of services.
| Work with service providers to meet identified needs. |  | Service Providers | Examine development options for Grange Castle and environs
Support the development of improved links between local third level institutions and large local employers | Develop network between major employers and third level institutions. | Ongoing | South Dublin County Council, South Dublin Chamber, Third level institutions. | Identify participants in network and establish pilot network group. | Not progressed yet.
Goal 5: Improve the quality and diversity of employment in the County
Objective | Action | Timetable | Partners | 2017 Measurement / Target | Update
Support the development and rollout of a Regional Jobs Strategy for Dublin | Actively support the development of the regional jobs strategy | Ongoing | South Dublin County Council; LEO: DJEI | Provide input and support the development of a regional jobs strategy | Next meeting of Implementation Committee for Dublin RAPJ is scheduled for 27th June in Dublin City Council. SDCC have participated in working group progressing all relevant SDCC/LEO 2016 & 2017 RAPJ actions & commitments.
Develop a training programme based on the needs of local employers | Identify training needs and develop mechanism for delivery, incorporating certification where possible. | Ongoing | LEO, | Continue delivery training through LEO & South Duvblin Chamber based on identified and emerging needs. | Ongoing delivery of Business Support Fund training programme by SD Chamber. New tender for training programmes advertised by LEO.
South Dublin Chamber
Local business
Develop training supports to enhance and develop exporting companies within the County | Identify supports for exporting companies and develop network to support exporting companies within the County | Ongoing | LEO | Development of Export Network and delivery fo supports and events. | Export event held in March & Brexit Event being arranged by LEO for June 2017.
South Dublin Chamber
Local Exporters
Work with local stakeholders to promote upskilling of local workforce | Identify particular skill deficits | Ongoing | LEO | Engage with Regional Skills forum to tackle skill deficits including existing and emerging apprenticeship opportunities | LEO represented on Regional Skills Forum with various initiatives being progressed through the forum, see http://www.regionalskills.ie/Regions/dublin/
South Dublin Chamber I.T. Tallaght
Solas
Social Enterprise centres
Goal 6: Actively engage with other Authorities and Agencies in the continued economic development of the Dublin region
Objective | Action | Timetable | Partners | 2017 Measurement / Target | Update
Support the continued collaboration with other agencies and authorities to develop and support economic enterprise | Continue to develop and deepen collaboration with the Industrial Development Agency | Ongoing | Industrial Development Agency | Develop protocols for identifying key inward development site size and location | Marketing plan research ongoing. Continuted liaison with IDA.
Continue to develop and enhance the marketing of Grange Castle Business Park to prospective clients
| Continue to develop and deepen collaboration with Enterprise Ireland | Ongoing | Enterprise Ireland | Develop and expand models of collaboration with Enterprise Ireland | Protocol on engagement with Enterprise Ireland continues to ensure client focus and support.
Support the identification and development of Key regional infrastructure provision | Work with state agencies to support business case for delivery of key infrastructure | Ongoing | Irish Water | Identify key regional infrastructure requirements | Tender for Professional Services published on 27/03/2017, Submissions due back on 19/05/2017. Infrastructure Wireframe expected in Q3 2017
Eirgrid
Dublin Local Authorities
National Transport Agency
National Roads Authority
Goal 7: Develop micro enterprise, community economic development and start-ups
Objective | Action | Timetable | Partners | 2017 Measurement / Target | Update
Support the ongoing development of the South Dublin LEO as a first stop shop for the development of enterprise within the County. | To support the development of start-up and small business expansion in the County and to maximise the development of enterprise in South Dublin | Ongoing | Enterprise Ireland; Various sectoral businesses; | Implementation of Regional Enterprise Strategy | Local Implementation Plan agreed by SPC.
|  |  | LEO; South Dublin Chamber; Training Providers; | Delivery of training and other supports to local businesses. | 108 participants in Business Support Fund training in 2017 (to end March).
|  |  | LEO | Maximise the take up of allocated funding measures under measure one and two programmes | Ongoing delivery of M1 & M2 programmes by LEO. €298,989 approved for 12 projects creating 23 new jobs under M1 in 2017 (as at 30th April 2017).
Support a network for the development of community economic development within the County | Identify key actors to be included in network and develop programme of work | Short Term | LCDC | Establish a network and develop programme of work to identify existing factors most inhibiting community economic development | Noit progressed yet / to be considered by LCDC.
LEO
Social Enterprise Centres South Dublin Chamber
Support the development of a network for the promotion of social entrepreneurship in the County | Identify key actors to be included in network. | Short Term | LCDC, LEO, Social enterprise centres, Chamber, Social Entrepreneurs | Establish network of stakeholders to identify existing factors most inhibiting to the development of social enterprises | Social Engterprise Conference planned for 2nd June (hosted by Partas). Preparations for establishment of South Dublin Social Enterprise Committee ongoing.