**LMP Implementation/Action Plan Q2 2017**

|  |  |  |  |
| --- | --- | --- | --- |
|  | **Actions** | **Responsibility** | **Time Frame** |
| **1** | **Raise awareness of roles and responsibility of various stakeholder relating to litter management** | **Enforcement & Licensing** | **Ongoing** |
| **2** | **Implement all relevant legislation, regulations and bye-laws** | **Enforcement & Licensing** | Ongoing active enforcement of all provisions of the Litter Pollution Act 1997, as amended, Waste Management Acts & associated regulations, Control of Dogs – dog fouling  **Legal Proceedings**  **April to May**  **22** cases referred for prosecution  **7** cases listed for court hearing  **0** appeals listed for Court Hearing |
| **3** | **Continue to operate the Customer Relations Management Systems (MembersNet, FYS, Customer Contact System, Environmental Complaints System) to track complaints/reports from initial contact to resolution** | **Enforcement & Licensing** | Ongoing. |
| **4** | **Investigate incidents of littering and illegal dumping** | **Enforcement & Licensing** | Ongoing foot patrols by Litter Warden service, with particular emphasis on county towns and villages**.** All incidents reported investigated for evidence |
| **5** | **Maintain high profile targeted warden service with foot and drive by patrols as appropriate in towns, villages, cemeteries and allotments** | **Enforcement & Licensing** | **Fixed Payments Notices issued**  Illegal dumping/Litter **56**  Unauthorised Signage **20**  Dog Fouling **0** |
| **6** | **Examine alternative Warden Service uniform** | **Enforcement & Licensing** | **Ongoing** |
| **7** | **Use overt and covert CCTV cameras and technologies to monitor areas prone to illegal dumping and to support enforcement action** | **Enforcement & Licensing** | CCTV/ Rapid Deployment Cameras & Audio devises provided at various locations. |
| **8** | **Engage on a regional basis to develop solutions to tackle dumping in the Dublin region (Smart Dublin)** | **Enforcement & Licensing** | **Ongoing** |
| **9** | **Manage and maintain Memorandums of Understanding with utility companies in relation to graffiti removal** | **Enforcement & Licensing** | Ongoing  MOU review  Meetings with utility providers scheduled for end of Q2 |
| **10** | **Operation of village cleaning programme including weekend service** | **Public Realm** | Ongoing Village cleansing in all town and village centres daily (Monday to Friday) and also on Sundays.  Continuous village maintenance work in Tallaght, Clondalkin, and Lucan and it’s proposed to now extend this service to other town/ village locations around the County.  Litter bin and cleaning service carried out various parks on bank holiday weekends (Sean Walsh, Tymon, Corkagh, and Griffeen Valley). |
| **11** | **Planned and scheduled clean-ups of identified litter blackspots in the county** | **Public Realm** | Continuous clean-ups of blackspots (scheduled & planned)  Successful applications made under the national Anti - Dumping Initiative for cleanup projects at Rossfield, Piperstown and Sean Walsh Park. Tranche 2 applications being prepared. |
| **12** | **Servicing and maintenance of Bring Banks to ensure that they are litter free** | **Public Realm** | Ongoing service of textile facilities being carried out by three service providers (74 recycling/ bring centres)  Regional contract in place for the servicing (emptying) of the glass/ can recycling banks. |
| **13** | **Conclude review litter bin provision in Public Realm having regard to Litter Bin Placement Protocol** | **Public Realm** | Litter Bin Review complete, report to come to ACMs.  Solar(Big Belly)street pilot agreed for Rathfarnham - 5 in total inc I in park |
| **14** | **Enforce litter control measures in Conditions of Allocation for Playing Fields** | **Public Realm** | Ongoing |
| **15** | **Targeted inspection of playing pitches with high litter issues** | **Public Realm** | Ongoing |
| **16** | **Use of internal systems to track and manage the removal graffiti from public property.** | **Public Realm** | Reported Graffiti being tracked on CC system.  All reports forwarded to the relevant bodies for scheduled removal. |
| **17** | **Targeted programme to remove bonfire material from public places in advance of Halloween** | **Public Realm** | Q4 |
| **18** | **Mapping of Halloween bonfires to identify trends and inform planned interventions (talk to Teresa/Leo/IT)** | **Public Realm** | Q4 |
| **19** | **Clean up and removal of Halloween bonfire material in timely manner** | **Public Realm** | Q4 |
| **20** | **Operate Laneway Maintenance programme at identified locations across the county and continue to seek solutions to issue** | **Public Realm** | Ongoing |
| **21** | **Provide scheduled waste removal for registered local community groups engaged in community clean ups** | **Public Realm** | 52 weekly scheduled clean up pickups.  444 clean up pickups were carried out for the Months of April and May, incl NSCW see below |
| **22** | **Participation and support for National Spring Clean events** | **Public Realm** | Q2. (April)  High level of activity maintained during SCW 2017. See above. |
| **23** | **Promote Anti-Litter & Anti-graffiti (dog fouling, anti-litter, illegal dumping, anti-graffiti etc ) radio and cinema advertisement campaign** | **Communication & Awareness** | The tackle litter and anti-dog fouling adverts are running in the cinema in Tallaght and Liffey Valley and also on the radio in the square Tallaght. |
| **24** | **Continue to examine the potential for Street Art Graffiti Scheme** | **Communication & Awareness** | Ongoing |
| **25** | **Administer Anti Litter and Anti Graffiti Awareness Grant** | **Communication & Awareness** | 2017 ALAG grant is currently being advertised and administered. Deadline for submissions is Thursday 29th June. This tranche includes for proposals for tackling dog litter |
| **26** | **Promote environmental schools poster and slogan competition** | **Communication & Awareness** | The poster competition for 2017-2018 school year will be advertised on the schools page and also in the September issue of the Green times newsletter. |
| **27** | **Promote the Green Dog Walkers initiative and responsible dog ownership** | **Communication & Awareness** | GDW initiative and responsible dog ownership continue to be promoted eg, dog licences and social media.  Dog Poo video / advertisement developed and being filmed end of June |
| **28** | **Promote National Gum Litter Task Force** | **Communication & Awareness** | The Gum Litter Task Force was launched in SDCC on Tuesday 30th May with the Deputy Mayor in Clondalkin Village. |
| **29** | **Promote and support National Spring Clean** | **Communication & Awareness** | National Spring Clean was launch by the Mayor in Lucan. It was promoted on an ongoing basis throughout the month via social media. 197 clean ups were carried out during the month of April |
| **30** | **Promote and support the PURE Initiative** | **Communication & Awareness** | Glenasmole National school took part in a PURE event on Wednesday 31st May – this was promoted on SDCCs social media accounts. |
| **31** | **Promote and support Tidy Towns Initiative through grant schemes eg LA21, Anti Litter and Anti Graffiti Awareness** | **Communication & Awareness** | “Adopt a Bring Bank” continues to be promoted through the PPN, Tidy Towns and social credits groups |
| **32** | **Review and promote Social Credit Scheme** | **Communication & Awareness** | The newly developed Social credits newsletter <http://www.sdcc.ie/news/social-credits-scheme-newsletter-june-2017> |
| **33** | **Support community groups through Social Credit Scheme** | **Communication & Awareness** | 100 registered groups , c 50% of these groups active on regular basis. |
| **34** | **Provide support and administer the Green Schools Programme** | **Communication & Awareness** | The National Green flag awards ceremony took place in the Helix on Wednesday 24th May. 39 schools in the SDCC area received green flags on the day, with two new schools receiving their first flag for Litter and waste |
| **35** | **Promote Seasonal Campaigns** | **Communication & Awareness** | The month of April was National Spring Clean month and was launch by the Mayor in Lucan. It was promoted on an ongoing basis throughout the month via social media  National Gum Litter Task force was launched in May in by the Deputy Mayor in Clondalkin |