- COMHAIRLE CHONTAE ÁTHA CLIATH THEAS

- SOUTH DUBLIN COUNTY COUNCIL

### MEETING OF SOUTH DUBLIN COUNTY COUNCIL

MONDAY 13th FEBRUARY 2006

QUESTION No. 40

Traffic calming programme

QUESTION: Cllr. Eamonn Tuffy

To ask the Manager for a progress report on the Council's current programme of traffic calming projects and if he will consider proposals from Councillors for specific traffic calming measures where there is a demonstrated need on safety grounds, before the completion of the proposed review and evaluation of the current programme?

REPLY:

The Lucan/Clondalkin Area Committee approved the installation of traffic calming measures in 4 Residential Cells and 4 Roads in both Clondalkin and Lucan Electoral Areas.

The present position in relation to these schemes is as follows:

Clondalkin Residential Cells

St. Johns						Construction Complete

Woodford/Monksfield//Monastery Gate		Construction Complete

Cherrywood/Oldchurch				Construction Complete

Rowlagh						Scheme drawings will be					         			                   available shortly.

Roads:

Aylmer Road						Construction Complete

Oatfield Avenue/Wheatfield Avenue		Construction Complete

St Ronans Avenue					Construction Complete

Palmerstown Woods                                      Construction to commence

in March 06.

Lucan Residential Cells

Hillcrest				                   Construction Complete

Arthur Griffith/Canonbrook/Esker Drive/           Ramps installed on Esker

St. Finian’s	Drive in August. Pedestrian crossing currently being installed. Construction scheduled to commence in March 06

Palmerstown	Alternative options being

examined.

Lucan Heights					Design to be prepared

Roads:

Ballyowen Road					Construction Complete

Coppice/Dingle					Construction Complete

Ballyowen Lane					Under construction

Esker Lane			Construction scheduled for

March 06

The current Traffic Calming Programme provides for the installation of Traffic Calming measures in 40 separate locations across the council’s administrative area. 22 of these schemes have been constructed to date and a further 4 schemes are due to commence shortly.  The Council will shortly be carrying out a review of the schemes constructed to date and a report on this matter together with future proposals will be brought to the elected members in mid-2006.