COMHAIRLE CHONTAE ÁTHA CLIATH THEAS

SOUTH DUBLIN COUNTY COUNCIL

MEETING OF TERENURE RATHFARNHAM AREA COMMITTEE (2)

Tuesday 14th February 2006

Headed Item No. 10

Report on Implementation of Traveller Accommodation Programme 2005 – 2008

The assessment of Traveller accommodation needs conducted in association with the process leading to the adoption of the Traveller Accommodation Programme 2005 - 2008 indicated that there is a need to provide 215 units of Traveller-specific accommodation throughout the County during the course of the programme.  This accommodation is to cater for both immediate requirements and future family formations.

The Council adopted the Traveller Accommodation Programme 2005 – 2008 unanimously on 9th May 2005.

The incomplete elements of the previous accommodation programme form the first phase of the current accommodation programme.

The following is the current position on developments in the 2005 – 2008 programme at various stages of delivery under the Programme:

| Traveller Accommodation Programme 2005 - 2008 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Scheme |  | Type and No. of Units | Part X/8 Advertised |  | Architect |  | Comments |  |
| Belgard Park |  | R.C.P. – 10 Bays |  |  |  |  | Residents moved into RCP on 5th May 2005. |  |
| Daletree Place |  | 10 Group Houses |  |  |  |  | Residents moved into houses in August 2005. |  |
| St. Aidan’s Close Brookfield |  | Group Houses – 5. | 22/04/03 |  | G.A.P. |  | Under construction. Scheduled to be completed by Spring 2006. |  |
| Hazel Hill, Killinardin |  | Group Houses – 5 R.C.P. – 5 Bays | Completed |  | M.V. Cullinan |  | Currently on site |  |
| Fortunestown |  | 10 Group Houses – |  |  | SAB |  | On site since December 2005. Scheduled to be completed in 2006. |  |
| Hayden's Lane |  | 8 Group Houses | 22/04/2003 |  | G.A.P. |  | On site. To be completed this year. |  |
| Kishogue |  | Group Houses – 10 R.C.P. – 10 Bays | Completed. |  | M.V. Cullinan |  | Advert for re-tendering of construction of permanent site to be advertised 27/1/06. |  |
| Stocking Lane |  | R.C.P. – 10 Bays | Completed |  | G.A.P. |  | DoE,H&LG approval of. cost plan awaited. |  |
| Lynch's Lane | Group Houses – 10 R.C.P. – 10 Bays |  |  | ------ |  | M.V. Cullinan |  | DoE,H&LG approval of. cost plan awaited. |
| Tay Lane | 7 Group Houses |  |  |  |  |  |  | Part 8 report noted by SDCC on 9th of January 2006. Cost plan to be prepared. |
| Fonthill Road | 3 Group Houses 3 Bays |  |  | 16/05/05 |  |  |  | Being provided through Part V mechanism. Part 8 report noted at July 2005 Council meeting. |
| Coldcut Road | R.C.P. – 8 Bays |  |  | 16/05/05 |  | ------ |  | Part 8 reports for 8-bay RCP noted at July 2005 Council meeting. |
| Ballyowen Lane | 5/6 Group Houses |  |  | ------ |  | G.A.P. |  | On hold. No progress. |
| Rathcoole | 10 group houses |  |  | Part X completed |  | Arch Services Dept |  | On hold awaiting resolution of access road issue. |
| Lock Road Emergency Site | 7 bays |  |  | ___ |  | Arch Services Dept. |  | Site completed by contractor; awaiting completion of ESB works. |

The remaining developments, listed below, are at site identification stage:

Adamstown – 3 developments, 30 units

Brittas - 	10 units

Blackchurch -	10 units

Bustyhill - 	8 units

Newcastle - 	10 units