COMHAIRLE CHONTAE ÁTHA CLIATH THEAS

SOUTH DUBLIN COUNTY COUNCIL

# MEETING OF TALLAGHT AREA COMMITTEE (1)

Monday 20th February, 2006

H I – (11)

## Report on Housing Construction Programme:

The up-to-date position of the construction programme for the County area is set out in the detail below: -

Completions in 2004 :-

| Total | No. of Units | 81 |
| --- | --- | --- |

Completions in 2005 :-

| Scheme Name | No. of Units | Completion Dates |
| --- | --- | --- |
| Russell Square | 110 | 2005 |
| Bawnlea | 7 | March 2005 |
| Jobstown Village Core | 10 | March 2005 |
| Cushlawn, Phase II | 31 | 2005 |
| Daletree, Ballycragh | 8 | September 2005 |
| Fettercairn Village | 22 | 2005 |
| Sub Total | 188 |  |

### On Site:-

| Scheme Name | No. of Units on Site | Completion Dates |
| --- | --- | --- |
| Fettercairn Village, Phase 1 Includes extension to creche & community facility | 14 | (In Phases) Feb 06 – Mar 06 |
| Avonbeg, Phase 3 | 47 | In phases September, 2006 |
| Fortunestown B, Phase 2 | 66 (+52 Vol. Units) | March 2006- June 2006 |
| Fortunestown B, Phase 4 | 120 | April 06 - August, 2006 |
| Fortunestown B, Phase 1 | 110 | May, 2006 |
| Deer Park (Joint Venture) | 119 | (In phases) February 2006 – April 2006 |
| Daletree (Part 5/Joint Venture) | 27 | Late 2006 |
| Hunterswood (Part V) | 9 | Late 2006 |
| Brookfield Village+ Community Facility | 16 | May 2006 |
| Deerpark (Part V) | 36 | February – April 2006 |
| Belfry | 35 | December 2006 |
| Belgard Square | 44 | Late 2006 |
| Sub.Total | 643 |  |

Tenders Recommended

| Scheme Name | No of Units |
| --- | --- |
| Kilcarrig Phase 3 (SH274) | Tender recommendation in the sum of €13,694,394 for the construction of 80 units by D&I Construction Ltd., Tyrell House, Main Street Blessington, Co Wicklow |
| Cushlawn Phase 3 (SH278) | Tender recommendation in the sum of €4,148,160 for the construction of 22 units by Owenbee Group, Unit 4, Fairways Mall, Donnabate, Co. Dublin |
| Sub Total | 102 |

Tenders being examined

| Scheme Name | No. Of Housing Units |
| --- | --- |
| Castlepark | 9(3 specially adapted units) |
| Sub Total | 9 |

Tender Production

| Scheme Name | No. of Housing Units |
| --- | --- |
| Kiltalown Green | 28 |
| Sub Total | 28 |

Part 8 Approved by Council:-

| Scheme Name | No. of Housing Units |
| --- | --- |
| Avonbeg Phase 4 (SH252) | 7 & St Muirins House |
| Sub Total | 7 |

At Concept/Design Stage:-

| ### Scheme Name | ### Approx . No. Of Units |
| --- | --- |
| ### Fortunestown B, Phase3 | ### 120 |
| ### Fettercairn Villlage, Phase2 | ### 10 |
| ### Kilclare, Phase2 | ### 30 (concepts presented to Tallaght Area Committee Meeting 16/06//2003) |
| ### Kilclare Phase3 | ### 15 |
| ### Knockmore House (incl. 15 units for Bernardos) | ### 60 (concepts presented to Tallaght Area Committee Meeting 16/06//2003) |
| Whitestown Stream | - |
| Suncroft | - |
| Whitebrook Park | - (concepts presented to Tallaght Area Committee Meeting 20/09/2004) |
| ### Stocking Lane | -(concept under preparation) |
| ### Swiftbrook | -(concept presented to Tallaght Area Committee Meeting 08/12/04) |
| ### Rossfield Infill | Concepts being prepared |
| ### Fettercairn Phase 2 | Concept presented to Tallaght Area Committee 7th December 2005 |
| ### Castletymon | Concept presented to Tallaght Area Committee 7th December 2005 |
| ### Sub Total | 235 |

Other potential sites are also being examined.