COMHAIRLE CONTAE ÁTHA CLIATH THEAS
SOUTH DUBLIN COUNTY COUNCIL

Minutes of Environment Public Realm & Climate Change SPC Meeting held on 6th February 2018 in IT Conference Room

In attendance

Elected Members

Councillor Pamela Kearns (Chair)

Councillor Francis Timmons

Councillor Danny O’Brien

Councillor Ed O’Brien

Councillor Rob Russell

Sectoral  Members

Connie Kiernan

Donie Anderson

Officials

Teresa Walsh, Director of Service

Chris Galvin, Senior Engineer

Michael McAdam, Senior Engineer

Mary Maguire, Senior Executive Officer

Sorcha O’Brien, Environmental Awareness Officer

Mary Keenan, Senior Executive Parks Superintendent

Apology

Councillor Brian Lawlor

Item 1: Minutes of Environment SPC meeting held on 7th November  2017

The Minutes of Environment SPC meeting held on 7th November 2017, were proposed by Councillor F. Timmons, seconded by Councillor D. O’Brien

Item 2:  SDCC Climate Change Action Plan

A presentation on progress on the development of the Council’s Climate Change Action Plans was delivered by Declan McCormack, CODEMA which focused on the following:

- About CODEMA

- Dublin Region Strategy for Climate Change Action Plans

- Baseline Emissions

- SDCC baseline statistics and targets

- 5 Milestones in plan development

- Workshops – objectives

- Draft Plan – outline of chapters

- Next Steps – workshops for peer review/ pubic engagement/impact of proposed actions

Queries raised related to performance against other LAs, actions to minimise eg PL LED/ fleet replacement/ solar farm / green / energy masterplan solutions for Clonburris SDZ

Item 3:  Interim review of Living with Trees

The following report as circulated was noted:

Review of Tree Management Policy 2015-2020 ‘Living With Trees’

The Council's Tree Management Policy 2015-2020 'Living With Trees' was adopted at a meeting of the Council on July 13, 2015.

The policy was developed by the Council’s Public Realm section having regard to best practice within the wider local authority and arboricultural sectors on both national and international levels.  The process involved the support and active input of a dedicated working group comprising members of the Environment, Water & Climate Change Strategic Policy Committee.  A draft policy document was published to coincide with a period of public consultation enabling the public to submit comments and observations which were considered by the working group and addressed in the adopted policy.

The Tree Management Policy provides a framework to inform and support decisions made by the Council on the management and development of a sustainable tree population in the County. The Policy acts as a point of reference for the public, Councillors, Council staff and professionally interested people to enable informed discussion and to establish a clearer, consistent and a structured approach to the issues affecting trees.

The objectives of the policy are:

- Improve tree management and create a safer, healthier tree population

- Implement a proactive, planned programme of cyclical tree maintenance

- Maximise the use of the Council’s resources to provide a better service and give better value for money.

Interim Review

This is a 5-Year management policy which is now into its third year and is scheduled for an interim review in accordance with the relevant specific action listed in the Action Plan which accompanies and supports the Tree Management Policy. It is intended to carry out this interim review during 2018.

The aim of the review is to:

- Review and assess progress to date on the implementation of the Action Plan

- Confirm whether the vision established by the policy is the right focus

- Provide an updated snapshot of our current tree stock and how the Council manages them

- Reassess aspects of the policy on particular issues that continue to generate ambiguity

- Look at emerging issues

- Assess consistency of relevant policies and actions of the Tree Management Policy with the Council’s Climate Change Action Plan

- Make new policy recommendations as necessary from review process

Since the Tree Management Policy was adopted in 2015, there are a number of policy issues which continue to generate ambiguity.  These issues are reflected through:

- analysis of tree-related enquiries received via the Council’s Customer Contact System

- emerging policies on climate change action

- increasing housing densities

- ongoing conflict between trees and services

- public concerns arising from extreme weather events

In order to provide further clarity, specific policy issues proposed for review include:

- Trees in conflict with built structures – a clear, corporate protocol is required for resolving issues where tree roots are in conflict with the built environment.  Specific locations include public footpaths, private boundary walls and driveways.

- Guidelines and options for implementation of alternative engineering solutions in order to minimise removal of healthy trees

- Review policy on removal of trees in proximity to public lighting columns in order to minimise loss of healthy trees and address public resistance to current practice

- Trees along riverbanks & watercourses – clarify procedure for resolving issues

- Trees and utilities - procedures and protocols for planning, installation and maintenance of utility apparatus in proximity to trees to be formalised with internal Council Departments and external agencies

- Irish Water Infrastructure Standards – restrictions on tree/shrub planting adjacent to water mains

- Tree root pruning – requirement for policy and guidelines

- Tree planting systems and use of rootbarriers – requirement for policy and guidelines

- Resistance to tree planting in residential streets and open spaces

- Disposal and recycling of timber and green waste

- Dublin Tree Canopy Study published March 2017 – review findings and implications for tree management in South Dublin

- SDCC Climate Change Action Plan

- Unauthorised removal of trees

- Tree risk management – identifying, prioritising and undertaking tree works according to categorised level of risk

Action Plan Update

The Tree Management Policy incorporates an Action Plan to support and deliver progress against policy’s the vision and aims.  The plan identifies a number of key actions, responsibilities and timescales for delivery over the period 2015-2020.  The current status for actions identified for delivery in the period 2015-2017 is as follows:

| Objective 1 - To establish the current position with regard to street trees in the County |  |  |  |  |
| --- | --- | --- | --- | --- |
| Ref | Action | Measurement | Timeframe | Status |
| 1.1 | Evaluate and purchase a tree management system | Purchase and use of system | 2015 | Procurement process complete and contract for supply of system has been awarded. |
| 1.2 | Survey all street trees in County and collate all data on computerised tree management system | Number of trees surveyed | 2015-2020 | Survey commenced in March 2015. Over 13,000 trees surveyed to date |
| 1.3 | Prepare a system for the ongoing update of street trees data in a spatial format | Real time availability of information on street tree location, number, condition and maintenance history | 2020 |  |
| 1.4 | Use the CAVAT system to value all Council street trees and use this information to assist in the management of the tree stock | All trees have accurate CAVAT value | 2020 |  |
| 1.5 | Review existing Tree Preservation Orders in the county | Annual Review | Ongoing | Ongoing as part of the planning process by Public Realm in conjunction with Planning Section |

| Objective 2 - To implement a proactive tree management programme |  |  |  |  |
| --- | --- | --- | --- | --- |
| Ref | Action | Measurement | Timeframe | Status |
| 2.1 | Ensure tree maintenance is completed in a safe manner in accordance with recognised standards and best practice | Ongoing development and training of all Council staff involved in tree work Employment of qualified, trained, competent contractors | Ongoing | Training and upskilling of staff ongoing Suitably qualified external contractors engaged as necessary |
| 2.2 | Use the Council’s planning powers to retain and protect trees on development sites and enforce as necessary | Annual review | Ongoing | Ongoing as part of the planning process by Public Realm in conjunction with Planning Section |
| 2.3 | Maximise the recycling of tree related green waste generated by the Council’s own tree management. | Annual review | Ongoing | Ongoing |
| 2.4 | Establish guidelines to prioritise maintenance work on street trees | Guidelines in place and used | 2015 | Guidelines set out and in use as per Tree Management Policy ‘Living With Trees’ |
| 2.5 | Develop a 5 year cyclical tree maintenance programme for street trees | Publish programme on Council’s website | 2015 | 3 year rolling tree maintenance programme for 2017-2019 in operation |
| 2.6 | Develop best practice protocol for tree maintenance works and nesting birds | Protocol agreed and in practice | 2015 | Draft document prepared |
| 2.7 | Provide staff training in tree survey and inspection | Training completed | 2015 | Training completed |
| 2.8 | Develop a quality standard specification for assessment of tree maintenance works post completion | Quality standard completed and in use | 2016 |  |
| 2.9 | Develop an annual tree planting programme | Number of trees planted | 2016 | 300 new trees planted in winter 2016. Approx. 1,500 new trees planted in winter 2017/spring 2018. |
| 2.10 | Develop tree planting and management guidelines | Guidelines in place | 2016 |  |
| 2.11 | Monitor the removal of street trees and ensure that new trees are proposed. | Annual review | 2016 | Statistics for tree removal and tree planting reported and monitored on a monthly basis |
| 2.12 | Work with a range of partners agree procedures and develop protocols to secure active protection of Council-owned trees from avoidable damage caused by the activities of other agencies. | Procedures and protocols agreed and in practice with internal Council Departments and external agencies | 2016 |  |
| 2.13 | Develop a protocol for resolving issues where tree roots are in conflict with the built environment | Procedures and protocols developed and in practice | 2016 |  |
| 2.14 | Develop a protocol for maintenance and management of trees along riverbanks & watercourses | Procedures and protocols developed and in practice | 2016 |  |
| 2.15 | Develop protocols for dealing with trees and utilities in consultation with the main utility providers | Procedures and protocols agreed and in practice with utility providers | 2016 |  |
| 2.16 | Pilot a community based leaf composting project | Project in place | 2016 | Information provided and discussion with community groups in Clondalkin and Rathfarnham |
| 2.17 | Pilot a tree replacement programme in an urban street setting | Agree area and complete | 2017 | Draft proposals in preparation for St. Joseph’s Road |
| 2.18 | Document a list of the significant trees of South Dublin | List established | 2017 |  |
| 2.19 | Develop a tree risk management system | System developed and in place | 2018 |  |
| 2.20 | Present annual review of Tree Management Policy Action Plan | Annual Review completed | Annually 2016-2020 | Updates on 2016 Tree Management presented to ACMs in March 2017. Updates on 2017 Tree Management presented to ACMs in December 2017 |
| 2.21 | Undertake a mid-term review of the Tree Management Policy | Mid-term review completed | 2017 | Review commencing February 2018 |
| 2.22 | Undertake review of Tree Management Policy 2015-2020 and draft new 5 year Tree Management Policy | 5 Year Review completed | 2020 |  |

| Objective 3 - Prepare and implement a public awareness and education tree programme |  |  |  |  |
| --- | --- | --- | --- | --- |
| Ref | Action | Measurement | Timeframe | Status |
| 3.1 | Develop a ‘Trees’ webpage on the Council’s website www.sdcc.ie | Webpage in place and maintained | 2015 | http://www.sdcc.ie/services/parks-and-recreation/tree-management in place and maintained |
| 3.2 | Make tree maintenance programme available on website | Information available on website | 2015 | Information available on website |
| 3.3 | Promote Tree week and Tree day in association with the Tree Council of Ireland | No. of Tree week & Tree Day activities organised each year | ongoing | Programme of activities arranged annually |
| 3.4 | Prepare feasibility study for sponsored tree planting | Plan completed | 2017 |  |
| 3.5 | Develop tree trails in each of the regional parks | Tree trails in parks | 2017 | Development of tree trails in progress for Dodder Valley Park and Sean Walsh Park |

Next Step

In order to progress the review of the Tree Management Policy, as a next step, it is proposed to organise a workshop for key representatives of internal Council departments to discuss issues proposed for review.

A discussion ensued with focus on public resistance to activity and the need to demonstrate “better reasoning” for decisions made / optimising public space for tree planting instead of kerbside.   Original internal groups / workgroup(s) of the SPC to be revisited as part of the review.

Item 4 Prelim Report on Street Canvas (Anti-Graffiti Initiative

The following report as circulated was noted:

As part of the SDCC Litter Management Plan 2015 -2019 / Annual Plans, actions are continuously reviewed with a view to eliminating/ minimising litter which includes visual litter. The issue of graffiti (visual litter) remains high on the agenda. As such the concept of placing art on traffic light boxes in South Dublin County has been extensively explored. This included liaison with Dublin City Council (who have already engaged in such an initiative). Based on this liaison, it was established that the project necessitates the consideration of a multiplicity of issues including suitability of locations, budgetary requirements, planning requirements, insurance requirements, cross departmental liaison and external stakeholder collaboration.

Dublin Canvas project

Dublin Canvas is a community art platform intended to bring flashes of colour and creativity to everyday objects in the County. The platform takes previously unused public spaces and transforms them into canvases to help brighten up the County.

This platform is an inclusive public art project that acts as a deterrent to visual litter. As of December 2017, the project was in its third year and had completed over 200 pieces of original artwork within the five main Dublin City Council areas.

Dublin Canvas uses traffic light control boxes to exhibit high quality, creative artwork to the public. Traffic light control boxes make perfect canvases to showcase community art as they are always naturally located in high footfall – high traffic areas. The artwork can be enjoyed by pedestrians, cyclist and motorists as they wait for the traffic light to turn green.

Dublin Canvas will begin as a pilot project in the South Dublin County Council area with 48 boxes spread evenly over the six electoral areas. An open call for submissions will be carried out inviting local community groups and artists to submit artwork in line with the application process. The Dublin Canvas Creative Producer has been engaged to co-ordinate the project and the estimated project cost for 2018 is approximately €22,000.

Proposed 2018 Timeline

Stage 1: January – February

- Assess suitable traffic light control boxes for artwork

- Agree selected locations

- Photograph and add GPS data to website ready for callout to artists.

Stage 2: March - April

- Callout Commences

- Selection process

- Artists notified of outcome

Stage 3: May

- Artwork begins

Stage 3: September

- Artwork Completed

Proposed Traffic box locations -To be confirmed subject to health and safety inspection and suitability

Lucan

- T143 Lucan Main St /Adamstown Rd

- T167 Lucan Rd/ Chapel Hill

- T555 Lucan Rd/ Grange Castle

- T312 R148 Kennelsfort Rd

- T311 R148 The Oval

- T571 R120/N4 (Newcastle Interchange)

- T549 ORR/ Willsbrook Rd

- T553 ORR/ Hermitage

Clondalkin

- T598 Newcastle main St. / Aylmer Rd

- T359 Tower Rd / Main St/ Convent Rd

- T379 Tower Rd/ Ninth Lock Rd/ Orchard Lane

- T364 Fonthill Rd South/ New Rd

- T502 New Nangor Rd/ Bawnogue Rd

- T535 New Nangor Rd/ Grange Castle Rd

- T590 Saggart Village Cross Roads

- T169 Ninth Lock Rd/ New Nangor rd

Tallaght Central

- T138 N81-Old Bawn Road

- T140A Tallaght Village

- T141 Belgard Rd- Old Blessington Road

- T176 N81-Belgard Road

- T179 Belgard Road- Mayberry Road

- T303 Greenhills Road-Mayberry Road

- T530 Tallaght Main Street- Greenhills Road

- T568 Belgard Square East – Belgard Square

Tallaght South

- T395 N81 Jobstown

- T569 N81 Cheeverstown Rd

- T550 Fortunstown Rd/ Jobstown Rd

- T564 ORR/ Fortunstown

- T527 Killinarden Heights

- P667 Fortunstown lane

- T580 Bóthar Katherine Tynan/ Fettercairn

- T569 Bóthar Katherine Tynan/ ORR

Templeogue/ Terenure

- T136 Crumlin Cross

- T198 St. Peters Rd St. James

- T501 Kimmage manor

- T199 Templeville / Glendown

- T342 Templeogue Templeville,

- T508 Templeogue Rd/ Templeogue Bridge

- T505 Templeville Rd/ Fortfield

- T521 Firhouse Rd / Spawell Bridge

Rathfarnham

- T341 Rathfarnham Rd/ dodder Rd

- T376 Rathfarnham Rd/ Butterfield

- T380 Rathfarnham Main St/ Butterfield Ave

- T337B Rathfarnham by Pass/ Willsbrook Rd

- T333 Butterfield / Marian/ fairways

- T160 Dodder Rd/ Fairways

- T132 Ballyboden / Ballyroan

- T598 Taylors Lane / Whitechurch Rd

A discussion ensued and Sorcha O’Brien, and she responded to questions arising focused on the process, timelines for the project, costs, locations and the methodology for selecting the appropriate art for these locations.

Item 5 Update on Flood Alleviation Schemes and Surface Water Schemes

The following report as circulated was noted:

The update on the flood alleviation schemes and the surface water schemes is as follows:

Ballycullen Stream Flood Alleviation Scheme

Following a number of flooding events in the Castlefield area, the Drainage Section of the Council has examined the flooding problem and after reviewing various options it has concluded that a duplication of the existing culvert is the preferred solution to alleviate flooding in the area.

The contract for the construction of this scheme was awarded to Clonmel Enterprises Ltd. in February. Works on site are now complete 2 months ahead of schedule. We have now entered the 12 month defects period.

River Poddle Flood Alleviation Scheme

Following the severe flooding event of 24/25th October 2011 the OPW agreed and provided the extra funding to undertake the Catchment Flood Risk Assessment & Management Study (CFRAMS) of the Poddle. The final report on these was forwarded to the OPW who has since approved the Draft Design Brief for the River Poddle Flood Alleviation Scheme. The appointment of consultants is expected in early September. The letter of intent and the letters to the unsuccessful tenderers have been issued. There was an objection from one of the eliminated tenderers. Dublin City Council forwarded the appeal to Engineers Ireland to make an adjudication. Engineers Ireland have upheld the decision of the Tender Assessment Board and the appointment of the consultant is now proceeding. Consultants will be appointed in early February.

In order to progress the environmental assessment for the works at Tymon Park SDCC engaged Roughan & ODonovan following a competition in December. Work on a Winter Habitiat Survey is currently progressing in Tymon Park and the results of this will feed into the Environment Assessment for the project.

Camac Flood Alleviation Scheme

The overall scheme for the Camac did not meet the OPW cost benefit criteria to progress work on the river in its entirety. A steering group has been set up to consider works at specific locations on the Camac River, SDCC and the OPW have met on site and walked the Camac. The OPW have drafted a brief for the appointment of Consultants to carry out the design of flood alleviation measures at these specific locations and this is currently being reviewed by SDCC and DCC.

Whitechurch Stream Flood Alleviation Scheme

As part of the Dodder CFRAMS there is a proposed scheme for the Whitechurch Stream. The OPW have confirmed funding for the procurement of a consultant engineer for the scheme. We are currently drafting a design brief for this and will submit the brief when complete to the OPW prior to engaging the consultant through the DCC framework.

2018 SURFACE WATER MINOR WORKS PROGRAMME:

1 Surface Water Sewer Systems;

| Location | Project | Update on Project |
| --- | --- | --- |
| Tay Lane, Rathcoole | Flood attenuation | Next phase. Continued from 2017 |
| Glenmaroon | Localised surface water improvement – to address a Surface Water issue on Glenmaroon Road. | In Planning. |
| Main Street, Peamount Road, Newcastle. | Localised surface water improvement | Carried over from 2017 |
| Celbridge Road | Surface water improvement scheme – collapsed culvert restoration. | Works complete. |
| Ballyowen Lane, Lucan. | Surface water improvement scheme – to assist Public Realm where necessary to complete pitch works | Next phase. Continued from 2017 |
| Templeogue Village | Initial assessment and feasibility study. | Phase 1. Carried over from 2017 |
| Stocking Lane, Rathfarnham. | Culvert upgrade | Phase 1. Carried over from 2017 |
| Old Lucan Road near village | Localised surface water improvement | Multi annual scheme in conjunction with Roads |
| Butterfield Park | Localised surface water improvement | In planning. |
| Nangor Road/Ninth Lock Road Junction, Clondalkin. | Localised surface water improvement | In planning. Carried over from 2017 |
| The majority of the above schemes are at preliminary stage and are subject to detailed design and full budgetary estimates. |  |  |

2 Flood Alleviation Minor Capital Works – Rivers & Streams

| Location | Project | Update on Project |
| --- | --- | --- |
| Camac River | Clearing and regrading | In planning |
| Poddle River | Clearing and regrading | In planning |
| Jobstown stream | Regrading, dredging and cleaning. Provision of a better aesthetic area to discourage illegal dumping into the stream. | In planning |
| River CCTV & Telemetry | 2 sites; Camac at Toyota and Tallaght Stream at Sean Walsh Park | In planning |
| Rain Gauge Upgrade | 5 sites | In planning |
| Owendoher Stream | Clearing and regrading | In planning |

Chris Galvin and Micheal McAdam responded to queries raised

Item 6 2018 Draft Work Programme

The following draft work programme as circulated was agreed and will be considered at the next CPG meeting:

- CFRAMS - Flood Alleviation and Surface Water Schemes – ongoing

- Climate Change -  Mitigation / Adaptation Plan

- Review of Living With Trees

- Litter Management Action Plan – 2017 Summary

- Teen Space –  Report on public consultation

- Update on Waste Management Plan / WERLA Update

- Update on examination of Reuse / recycling – Coffee Cups

- Update on Recycling Strategy (Following ACM updates)

- Update on Scramblers & Quads

- Parks & Open Spaces Strategy Update

- Revised Tree Management Plan

- Initiate Review of Bye Laws ( Parks Op Spaces / Horses - Depending on outcome of working groups)

- Biodiversity Plan *

Item 7 2017 – Item referred by Council – Scramblers

The following report as circulated was noted :

The following item was referred to the November 2017 Council Meeting having initially been considerd and  referred from  October 2017 Clondalkin ACM.

''That this committee asks for a task force to be convened to look at what can be done to combat the issue of Scramblers and Quads, the behaviour is causing ongoing distress to many residents, it is both anti-social and a dangerous behaviour, The Task force should include Elected Reps, Guards, Safety Forums reps, Council Reps (Particularly Anti-social unit), Crosscare rep and any other required member ''

REPORT:

The Council is acutely aware of long and on-going problems associated with scramblers and has been in liaison with An Garda Síochána in relation to this issue.

Public Realm works have been initiated in attempts to combat the problem e.g. run of 1.2 metre high fencing along the side of the green space areas, provision of bollards etc.,

Similarly, An Garda Síochána, South Dublin County Council and Motorcycling Ireland launched an awareness campaign about the correct use of quads bikes and scramblers in advance of Christmas 2016. This campaign requested parents who were considering buying these bikes as a Christmas present for their child to make sure that they were informed as to the legal requirements around these bikes and the use of them.

It is considered that the Council's parks and Open Spaces Byelaws are sufficiently strong to enable enforcement by AGS within the Council’s parks and open spaces and Claude 3.1 h refers as follows "....... save with the permission of the Council, no person shall bring into a Park any Mechanically Propelled Vehicle which includes for the avoidance of doubt motorcycles, motor-cross / quad bikes or other powered vehicles. Such vehicles may be removed from the park / open space by An Garda Síochána".

While it is acknowledged that there may be / is difficulty in bringing successful prosecutions, the Council passed a motion at the January 2017 Council meeting calling for the introduction of primary legislation to regulate ownership and use of vehicles. The Minister for Justice’s reply at that time indicated that such legislation would require a review of road traffic legislation and the communication had been referred to that Department.  As no response was received from the Minister for Transport, Tourism and Sport, a reminder was recently issued to his office.

As the problem is not limited to the Clondalkin area, it may be appropriate that the potential establishment of a county wide task force be considered jointly by the Environment Public Realm and Climate Change and Land Use Planning & Transportation SPC.

It was agreed that this item be considered by this and the Land Use Planning & Transportation SPCs. End of Report to SPC

Cllr Francis Timmons was nominated from the EPR&CC membership and the item will be considered by the Land Use & Transportation SPC at the next meeting.

It was acknowledged that given the regional aspect of the problem that the task Force would  require a regional dimension and will be forwarded to the DLAs for consideration.

Item 8 Litter Management Plan – 2017 Action Plan summary

The following 2017 summary report as circulated was noted:

|  | Actions | Responsibility | Time Frame |
| --- | --- | --- | --- |
| 1 | Raise awareness of roles and responsibility of various stakeholder relating to litter management | Enforcement & Licensing | Ongoing |
| 2 | Implement all relevant legislation, regulations and bye-laws | Enforcement & Licensing | Ongoing active enforcement of all provisions of the Litter Pollution Act 1997, as amended, Waste Management Acts & associated regulations |
| 3 | Continue to operate the Customer Relations Management Systems (MembersNet, FYS, Customer Contact System, Environmental Complaints System) to track complaints/reports from initial contact to resolution | Enforcement & Licensing | January - December 2017 6,723 complaints received and logged. Members Net – 830 Fix your Street – 1,132 Environmental Complaints System - 4,761 |
| 4 | Maintain high profile targeted warden service with foot and drive by patrols as appropriate in towns, villages, cemeteries and allotments | Enforcement & Licensing | Increased monitoring of known litter generator areas by the Litter Warden service. Continued investigation of litter for evidence of prepatrators. Heightened visibility / branded vehicles |
| 5 | Examine alternative Warden Service uniform | Enforcement & Licensing | Ongoing |
| 6 | Use overt and covert CCTV cameras and technologies to monitor areas prone to illegal dumping and to support enforcement action | Enforcement & Licensing | Installation of Fixed/Rapid Deployment Cameras for 2017: - Ballyowen SC Bring Banks - Kiltalown - Lynch’s Lane - Tandy’s Lane - Lennox Laboratries - JFK Industrial Estate - Estate - Back lands at St. Aidans/Brookfield Installation of Audio Device technology at the following location in 2017: - Bring Banks at Sean Walsh Pk - Bring Banks at Ballyowen SC |
| 7 | Engage on a regional basis to develop solutions to tackle dumping in the Dublin region (Smart Dublin) | Enforcement & Licensing | Smart Dublin – SBIR - Seeking low cost, innovative, technological solutions in the form of products, services or applications to tackle illegal dumping in the Dublin region Phase 1 nearing conclusion. Competition from within existing Phase 1 participants to select participants for Phase 2 funding to be finalised in January 2018. |
| 8 | Manage and maintain Memorandums of Understanding with utility companies in relation to graffiti removal | Enforcement & Licensing | Regular Meetings with Utility Providers. 3 x MOUs renewed with Virgin Media, ESB and Eir (Sept 2017) |
| 9 | Operation of village cleaning programme including weekend service | Public Realm | Village cleansing programme ongoing in all town and village centres on a daily basis Monday to Friday and also on Sundays. Continous village maintenance work in Tallaght, Clondalkin, and Lucan and its proposed to now extend this service to other town / village locations around the County Litter bin and cleaning service in some parks on bank holiday weekends (Sean Walsh, Tymon, Corkagh, and Griffeen Valley). very positive results for Tallaght in IBAL Anti Litter 2017 results- Now ranked 5th overall "Cleaner than European Norms" |
| 10 | Planned and scheduled clean-ups of identified litter blackspots in the county | Public Realm | Planned and scheduled clean- ups of blackspots are ongoing. Successful applications made under the national Anti-Dumping Initiative for clean up projects at Rossfiedl, Piperstown and Sean Walsh Park. |
| 11 | Servicing and maintenance of Bring Banks to ensure that they are litter free | Public Realm | 74 recycling/ bring centres. Textile facilities serviced by three service providers. Regional contract in place for the servicing (emptying) of the glass/ can recycling banks. Tender process underway to put new contract in place. |
| 12 | Conclude review litter bin provision in Public Realm having regard to Litter Bin Placement Protocol | Public Realm | Litter Bin Review were completed and presented to ACMs Arrangements being made for procurement of Solar (Big Belly) street pilot agreed for Rathfarmham |
| 13 | Enforce litter control measures in Conditions of Allocation for Playing Fields | Public Realm | Weekly notice issued to clubs regarding clean-up post matches. |
| 14 | Targeted inspection of playing pitches with high litter issues | Public Realm | Ongoing |
| 15 | Use of internal systems to track and manage the removal graffiti from public property. | Public Realm | Reported graffiti being tracked on CC System. All reports forwarded to the relevant Body for scheduled removal. MoUs in place and working well |
| 16 | Targeted programme to remove bonfire material from public places in advance of Halloween | Public Realm | Pre-Halloween Bonfire commenced early October. c 300 locations (excluding duplicate locations) advised of stockpiling. 211 tonnes of bonfire materials was collected by SDCC in the two weeks prior to the Bank Holiday weekend and over the Bank Holiday weekend including Tuesday 31st October 2017. 201 tonnes of Post Halloween waste was also removed. |
| 17 | Mapping of Halloween bonfires to identify trends and inform planned interventions | Public Realm | 388 bonfires were mapped |
| 18 | Clean up and removal of Halloween bonfire material in timely manner | Public Realm | 388 locations were cleared |
| 19 | Operate Laneway Maintenance programme at identified locations across the county and continue to seek solutions to issue | Public Realm |  |
| 20 | Provide scheduled waste removal for registered local community groups engaged in community clean ups | Public Realm | 52 weekly scheduled clean up pickups. 1665 clean up pickups were carried out in 2017 including NSCW. |
| 21 | Participation and support for National Spring Clean events | Public Realm | High level of activity maintained during SCW 2017; see above. |
| 22 | Promote Anti-Litter & Anti-graffiti (dog fouling, anti-litter, illegal dumping, anti-graffiti etc ) radio and cinema advertisement campaign | Communication & Awareness | Jan – Dec 2017 24 Cinema adverts (dog fouling, takle litter & illegal dumping) Ongoing radio adverts in the square (dog fouling & tackle litter) 2 Targeted radio adverts on dog fouling with 98fm & Q102 for 52 spots Till Receipts with SuperValu for 28 weeks in Lucan & knocklyon |
| 23 | Administer Anti-Litter and Anti-Graffiti Awareness Grant | Communication & Awareness | 2017 AL/AG grant has been administrated with 18 applicants receiving funding |
| 24 | Promote environmental schools poster and slogan competition | Communication & Awareness | There were a total of 134 enteries for the Poster competition that was advertised through email, Green Times newsletter, SDCC site and social media. Presentation ceremony by Mary at launch of Eco Week |
| 25 | Promote the Green Dog Walkers initiative and responsible dog ownership | Communication & Awareness | GDW initiative and responsible dog ownership continue to be promoted eg, dog licences and social media. The new Anti Dog Fouling advert has been advertised in the cinema 9 times through 2017. A GDW competition was held in March 2017 to promote responsioble dog owners. |
| 26 | Promote National Gum Litter Task Force | Communication & Awareness | The Gum Litter Task Force was promoted through the cinema over the year as part of national campaign. An advert was also placed on the square radio for the summer months. Regional GLT initiative was launched by Deputy Mayor in Clondalkin |
| 27 | Promote and support the PURE Initiative | Communication & Awareness | Annual Contribution made. Pure awards took place on the 03rd October. |
| 28 | Promote and support Tidy Towns Initiative through grant schemes eg LA21, Anti Litter and Anti Graffiti Awareness | Communication & Awareness | LA21 and Al/AG grants promoted to all Tidy Town groups via all communication channels – social media, email, sdcc site and PPN. In addition supports provided on an ongoing basis through the Social credit scheme |
| 29 | Review and promote Social Credit Scheme | Communication & Awareness | Review of the Social Credit Scheme was carried out with full report going to EWCC SPC 2 Newsletters were issued via email, social media and sdcc website New Community minor landscaping scheme was launched involving 9 groups New materials provided – gloves, paint and brushes |
| 30 | Support community groups through Social Credit Scheme | Communication & Awareness | Support was provided to 2600 Community clean-ups through out 2017 |
| 31 | Provide support and administer the Green Schools Programme | Communication & Awareness | Green School Participation is reviewed on an ongoing basis. Currently there are 99 primary and 35 secondary schools registered. Green School Seminar held in September for all schools Assessments carried out throughout the year for schools wishing to participate in the flag process Workshops and visits offered to all schools through out the year promoting all environmental issues 2 Green School Times newsletters issued The Recycled decoration competition and Environmental poster competition was held for all schools to participate in. Schools from across the county assisted the Council with the launch of Eco Week, National Spring Clean and also Gum Litter Task Force |
| 32 | Promote Seasonal Campaigns | Communication & Awareness | Main Events for 2017 - Green Dog Walker competition - Adopt a bring bank launched - Environmental Poster competition - ECO week - National Spring Clean - Gum Litter Task Force - Green School Seminar - ReUse month - Halloween Campaign - EWWR - Christmas recycled decoration competition - Christmas campaign - 2 Green Schools newsletters - 2 Social credit scheme newsletters - Community minor landscaping campaign As well as Yearly campaigns for 2017 - Cinema adverts – 24 - Radio adverts - 2 - Till receipts – 28 weeks - Distribution of EA materials - GDW - LA21 Grant - Anti-litter & Anti-graffiti grant |

There being no further business the meeting concluded at 7.15 pm