Housing Construction Programme Update

Tallaght Area Committee September 2018

There are 4 housing construction projects on site in the Tallaght Area totalling 158 units which will be delivered in 2018. The schedule for completions is as follows:

| Local Electoral Area | Schemes | No. of Units | Status | Scheduled for Completion |
| --- | --- | --- | --- | --- |
| Tallaght South | Mac Uilliam (Fortunestown) | 28 | Under construction | Quarter 4 2018 |
| Tallaght South | Dromcarra, Tallaght | 14 | Under construction | Quarter 4 2018 |
| Tallaght South | Sheehy Skeffington Meadows (Social + TAP) | 90 | 69 units handed over between May and August 2018. Final phase of 16 social + 5 TAP for completion October 2018. | Quarter 4 2018 |
| Tallaght South | Killinarden, Tallaght | 26 | Under construction | End 2018 |
|  |  | 158 |  |  |

The next tranche of social housing build projects are currently at feasibility stage with a number of projects being brought to Council through Part 8 of the Planning and Development Act 2000 (as amended). There is currently 1 scheme which has been progressed within the Tallaght area for Part 8 consideration.

| Schemes | No. of Units | Status |
| --- | --- | --- |
| St. Catherine’s, Tallaght | 13 | Part 8 approved September 2018. Pre-Tender design and costs to be prepared to advance the Department of Housing funding approval. |

The proposed Older Persons schemes at Fernwood and Maplewood will be brought to Council in October for consideration. The proposed Whitestown Way scheme is currently on display for Part 8 consultation. The consultation period is open on this proposed scheme up to the 9th of November 2018.

PART V AND APPROVED HOUSING BODY DELIVERY PROGRAMME UPDATE

TALLAGHT AREA

Part V negotiations are ongoing with developers to deliver the 10% social requirement on private schemes within the county. There are currently 4 schemes within the Tallaght area delivering a total of 42 units by the end of 2018.

| Part V Update |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Area | Delivered Q1 2018 | Delivered Q2 2018 | Expected Q3 2018 | Expected Q4 2018 | Expected 2019 |
| Tallaght Central |  |  | 1 |  | 30 |
| Tallaght South | 32 | 8 | 1 |  |  |
| Grand Total | 32 | 8 | 2 | 0 | 30 |

The Approved Housing Body sector has an active acquisition programme of turnkey developments within the county. There are a total of 31 units projected for delivery in the Tallaght area over quarter 3 and quarter 4 in 2018.

| Approved Housing Body Delivery Programme Update |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Delivered Q1 2018 | Delivered Q2 2018 | Q3 2018 | Q4 2018 | 2019 |
| Tallaght | 1 | 0 | 3 | 28 | 56 |