## Slide 1: A More Inclusive County: South Dublin County Integration Strategy 2019-2023

## Slide 2: Consultation Process
A review of the actions identified under the Council's previous Integration Strategy was undertaken to determine where there was successful delivery of actions, and also to examine what actions were not delivered and the reasons for non-delivery. This review has informed the development and direction of proposed actions for the new Strategy.
The National Migrant Integration Strategy and a discussion document produced by the Immigrant Council of Ireland ‘Keeping it Local: Discussion document and proposed actions for Local Authorities on developing local migrant integration strategies’ have both significantly informed the new draft Strategy as well as providing guidance in determining possible actions for inclusion;
South Dublin County Partnership developed a questionnaire to gather feedback from key stakeholders in this area - the questionnaire was published on www.sdcc.ie and was also distributed to South Dublin Migrant Integration Forum, local Elected Representatives, the Local Community Development Committee, the Public Participation Network and others to ensure as wide a response as possible;
Direct consultation was undertaken with South Dublin Migrant Integration Forum to gather their input on the proposed actions for the draft Strategy;
Internal consultation across relevant sections and departments of the Council has also been undertaken to identify possible actions to support migrant integration in the various work streams of the Council.
A consultant was engaged to carry out a research piece to profile South Dublin County; to investigate best practice for developing a integration strategy and to examine the EU, national and local context required for the strategy

## Slide 3: The Strategy
The strategy is being developed to be specific in a local context and with the Council being the main driving force behind the actions whilst working with other agencies to ensure that all the relevant stakeholders in the integration process contribute to the delivery of the strategy.
5 thematic areas have been identified under the strategy:
Theme 1: Inclusive Communities
Theme 2: Lifelong Learning
Theme 3: Enterprise and Employment
Theme 4: Health and Wellbeing
Theme 5: Inclusive Service Delivery
A full list of the actions is set out in the draft, in the next slides some notable actions have been extracted.

## Slide 4: Theme 1: Inclusive Communities
Action | Section | SDCC/ Outside Agency Partner | Success Indicators
Promote the portrayal of positive contribution made by migrant communities in SDCC | 1. Social Inclusion Unit | 1. South Dublin Migrant Integration Forum (SDMIF) 2. Intercultural Centres | 1. Positive awareness of migrant communities and the benefits of diversity promoted 2. Awards at intercultural Food and Craft Festival and Social Inclusion Week
Facilitate communication between South Dublin Migrant Integration Forum (SDMIF) and new communities in the County (Open forums held annually at minimum) | 1. Social Inclusion Unit | 1. South Dublin County Partnership | 1. Increased membership of South Dublin Migrant Integration Forum (SDMIF)
 |  | 2. Intercultural Centres | 2. SDMIF hold an open night during Social Inclusion Week
 |  | 3. The Towers Residents Association | 
 |  | 4. Community Centres/ Family Resource Centres 5. New Communities Partnership | 
Ensure the South Dublin County Council public offices display anti-racism information | 1. Corporate Services | 1. Council Community Centres | 1. Anti-racism information displayed in public offices, libraries and community centres
 | 2. Community Development Team |  | 
 | 3. Libraries |  | 
 | 4. Social Inclusion Unit |  | 
Initiatives will be undertaken aimed at increasing the number of migrant representatives in local authority fora, like Public Participation Networks (PPNs), and other representative fora | 1. Social Inclusion Unit | 1. PPN | 1. Increased number of migrant groups registered with the PPN
 |  | 2. SDMIF | 2. Number of migrant representatives elected to decision making structures
 |  | 3. JPC | 
 |  | 4. Sports Partnership | 

## Slide 5: Theme 2: Lifelong Learning
Action | Section | SDCC/ Outside Agency Partner | Success Indicators
Development of Migrant Awareness Programme in Schools | 1. Social Inclusion Unit | 1. Department of Justice | 1. Number of schools participating in programme
Promote the informal adult education programmes delivered locally amongst migrant communities | 1. Libraries 2. Social Inclusion Unit | 1. Aontas | 1. Increase in number of migrants communities participating
 |  | 2. SDCP | 
 |  | 3. ETB | 

## Slide 6: Theme 3: Enterprise and Employment
Action | Section | SDCC/ Outside Agency Partner | Success Indicators
Research the possible provision of an "English for Business" language course to improve the linguistic proficiency of migrants | 1. Local Enterprise Office |  | 1. Research piece undertaken
 | 2. Libraries |  | 
Explore the development and implementation of specific courses and training for ethnic entrepreneurs to address specific needs as identified | 1. Local Enterprise Office |  | 1. Development of specific courses and training for ethnic entrepreneurs where a need is identified

## Slide 7: Theme 4: Health and Wellbeing
Action | Section | SDCC/ Outside Agency Partner | Success Indicators
Hold a dedicated event during Health and Wellbeing Week for migrant integration | 1. Social Inclusion Unit | 1. Sports Development Officers | 1. Integration event held
 | 2. Sports & Recreation Section | 2. National Governing Bodies 3. HSE | 
 | 3. South Dublin Sports Partnership | 4. South Dublin Migrant Information Forum (SDMIF) | 
Research into encouraging Health & Wellbeing programmes for those placed in direct provision | 1. Social Inclusion Unit |  | 1. Research piece undertaken
 | 2. Interagency Section |  | 
 | 3. Sports & Recreation Section |  | 
 | 4. Sports Partnership |  | 

## Slide 8: Theme 5: Inclusive Service Delivery
Action | Section | SDCC/ Outside Agency Partner | Success Indicators
Further develop the project identifying language skills of Council staff | 1. Customer Care Section |  | 1. List of Council staff available to deal with non-English speaking customers
 | 2. Learning & Development Unit |  | 
Diversity awareness training for all Council staff | 1. HR Training |  | 1. Number of Council staff completed training
Formation of a co-ordination group among the Dublin Local Authorities | 1. Social Inclusion Unit | 1. Dublin City Council; Fingal County Council, Dun Laoghaire - Rathdown County Council | Group formed and meeting on a quarterly basis
Establish a monitoring group comprised of relevant Council Officials to update the progress on strategies actions | 1. Social Inclusion Unit | 1. South Dublin Council Departments | 1. Monitoring Group set up
Registration/Political Awareness Programme in migrant communities (voters registration, Council Chamber tour etc.) | 1. Corporate Services 2. Social Inclusion Unit 3. Community Development Team 4. Libraries | 1. SDMIF SDCP Immigrant Council of Ireland | 1. Increased participation by eligible and future migrant in democratic processes

## Slide 9: Next steps:
Input from the members of the SPC
Endorsement of draft strategy by SPC members
Proof reading by consultant
Plain English proofing carried out by Council’s Access Officer
Final draft strategy to the March Council meeting
Strategy to go to graphic design company
Strategy circulated after April Council meeting