Rathfarnham Templeogue Terenure Area

Housing Capital Programme Quarterly Report

Q1 2019

| 2019 Capital Housing Supply Programme |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| LA Build | AHB Build | Part V | Total Build | LA Acquisitions | AHB Acquisitions | Total Acquisitions | Voids | Total 2019 Capital Supply |
| 112 | 111 | 125 | 348 | 37 | 9 | 46 | 21 | 415 |

| Rathfarnham Templeogue Terenure Area Committee Report |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Programme for 2019 |  |  |  |  |  |  |
| Local Electoral Area | Local Authority Build | Part V | AHB Build | LA Acquisition | AHB Acquisition | Grand Total |
| Rathfarnham | 40 | 4 | 9 |  |  | 53 |  |  |
| Templeogue/Terenure |  | 21 |  | 1 |  | 22 |  |  |
|  | 40 | 25 | 9 | 1 | 0 | 75 |  |  |
| Completions to date | No deliveries to date within this LEA 2019 |  |  |  |  |  |  |  |

| Construction Programme 2019-2021 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Construction Projects on Site |  |  |  |  |  |  |
| Local Electoral Area | Project Name | Part 8 Approved Date | No. of Units | Current Status |  |  |
| Rathfarnham | Owendoher | Oct-15 | 40 | Contract due for completion and handover in May 2019 |  |  |
| Projects with Part 8 Planning Approval |  |  |  |  |  |  |
| Local Electoral Area | Project Name | Part 8 Approved Date | No. of Units Approved @ Part 8 | Current Status |  |  |
| Templeogue-Terenure | Homeville | 10/09/2018 | 16 | Plans currently being prepared to bring the project to tender for contractor in Q3 2019. |  |  |
| Templeogue-Terenure | Templegoue Village | 01/10/2018 | 11 | Plans currently being prepared to bring the project to tender for contractor in Q3 2019. |  |  |
|  |  |  | 27 |  |  |  |
| Projects Pre-Part 8 Stage |  |  |  |  |  |  |
|  | Project Name | Part 8 publication target | Indicative No. of Units | Current Status |  |  |
| Rathfarnham | Stocking Lane | April 2019 | 52 | Designs currently being prepared for Part 8 publication. |  |  |
| Rathfarnham | Knocklyon | April 2019 | 31 | Designs currently being prepared for Part 8 publication. |  |  |
|  |  |  | 83 |  |  |  |

| Part V Delivery Programme for 2019 |  |  |  |
| --- | --- | --- | --- |
| Scheme Name | Rathfarnham | Templeogue/Terenure | Status of Part V Agreement |
| Ashfield College |  | 1 | Offsite unit being secured in lieu of unit within the scheme. |
| Ballycullen Green | 3 |  | Units agreed and Part V costs under negotiation. |
| Corrybeg |  | 1 | Units agreed and Part V costs under negotiation. |
| Dodderbrook |  | 13 | Units agreed and Part V costs under negotiation. |
| St. Johns Old Court | 1 |  | Part V agreement in place |
| Wilkins Court |  | 6 | Part V agreement in place |
| Grand Total | 4 | 21 |  |