Tallaght Local Electoral Area

Housing Capital Programme Quarterly Report

Q1 2019

| 2019 Capital Housing Supply Programme |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| LA Build | AHB Build | Part V | Total Build | LA Acquisitions | AHB Acquisitions | Total Acquisitions | Voids | Total 2019 Capital Supply |
| 112 | 111 | 125 | 348 | 37 | 9 | 46 | 21 | 415 |

| Tallaght Area Committee Report |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Programme for 2019 |  |  |  |  |  |  |
| Local Electoral Area | Local Authority Build | Part V | AHB Build | LA Acquisition | AHB Acquisition | Grand Total |
| Tallaght South | 9 | 38 | 67 | 3 | 3 | 120 |  |  |
| Tallaght Central | 0 | 7 | 12 | 2 | 2 | 23 |  |  |
| Total | 9 | 45 | 79 | 5 | 5 | 143 |  |  |
| Delivered units to date |  |  |  |  |  |  |  |  |

| Local Electoral Area | LA Build | AHB Acquisition | Grand Total |
| --- | --- | --- | --- |
| Tallaght South | 9 | 1 | 10 |

| Construction Programme 2019-2021 |  |  |  |  |
| --- | --- | --- | --- | --- |
| Projects with Part 8 Planning Approval |  |  |  |  |
| Local Electoral Area | Project Name | Part 8 Approved Date | No. of Units Approved @ Part 8 | Current Status |
| Tallaght | St. Catherine’s | September 2018 | 13 | Plans currently being prepared to bring the project to tender for contractor in Q4 2019. |
| Tallaght | Fernwood & Maplewood (Clúid Housing) | October 2018 | 40 | Clúid Housing preparing to go to tender. Department of Housing funding approval granted. |
| Tallaght | Whitestown Way (Clúid Housing) | December 2018 | 81 | Clúid Housing preparing to go to tender. Department of Housing funding approval granted. |
|  |  |  | 134 |  |
| Projects Pre-Part 8 Stage |  |  |  |  |
|  | Project Name | Part 8 publication target | Indicative No. of Units | Current Status |
| Tallaght South | Rossfield | To Be Confirmed | 2 | Department of Housing capital appraisal (stage 1) submission to be prepared. Target Q4 2019 to publish Part 8 plans. |
|  |  |  | 2 |  |

| Part V Delivery Programme for 2019 |  |  |
| --- | --- | --- |
| Scheme Name | No. of Units Being Delivered | Status of Part V Agreement |
| Balrothery (Kingswood) | 1 | Part V agreement finalised with developer. Units due for delivery in Q4 2019. |
| Citywest Village | 13 | Part V agreement finalised with developer. Units due for delivery in Q2 2019. |
| Cuil Duin, Harcourt Developments | 24 | Part V agreement finalised with developer. Units due for delivery in Q3 2019. |
| Elder Heath | 6 | Part V agreement finalised with developer. Units due for delivery in Q3 2019. |
| Stonemason Court | 1 | Part V agreement finalised with developer. Units due for delivery in Q3 2019. |
| Total | 45 |  |

| AHB Build Programme |  |  |
| --- | --- | --- |
| Scheme Name | Unit Numbers Being Delivered | Details |
| Balrothery (Kingswood) | 12 | Respond! Housing supported to acquire 13 units (includes 1 Part V unit) |
| Stonemason Court | 11 | Clúid Housing supported to acquire 12 units (includes 1 Part V unit) |
| Westpark | 56 | Clúid Housing purchasing supported to acquire newly renovated units in Westpark, Saggart, Co. Dublin |
| Grand Total | 79 |  |