**Clondalkin Local Electoral Area**

**Housing Capital Programme Quarterly Report**

**Q1 2019**

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **2019 Capital Housing Supply Programme** | | | | | | | | |
| LA Build | AHB Build | Part V | ***Total Build*** | LA Acquisitions | AHB Acquisitions | **Total Acquisitions** | **Voids** | **Total 2019 Capital Supply** |
| 112 | 111 | 125 | ***348*** | 37 | 9 | **46** | **21** | **415** |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Clondalkin Area Committee Report** | | | | | | |
| **Programme for 2019** | | | | | | |
| **Local Electoral Area** | **Local Authority Build** | **Part V** | **AHB Build** | **LA Acquisition** | **AHB Acquisition** | **Grand Total** |
| Clondalkin | 63 | 19 | 10 | 11 | 16 | 119 |  |  |
|  |  |  |  |  |  |  |  |  |

|  |  |  |  |
| --- | --- | --- | --- |
| **Local Electoral Area** | **LA Acquisition** | **AHB Acquisition** | **Grand Total** |
| Clondalkin | 1 | 1 | 2 |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Construction Programme 2019-2021** | | | | | | |
| **Construction Projects on Site** | | | | | | |
| **Local Electoral Area** | **Project Name** | **No. of Units** | **Current Status** | | | |
| Clondalkin | Collinstown Grove (CAS Build Project) | 4 | Túath Housing CAS Construction Project. Contractor appointed and was commencing on site 11/03/2019. | | | |
| Clondalkin | St. Cuthberts | 63 | Construction commenced in 2018. Scheme progressing which is due for completion in Q3 2019 | | | |
|  |  | 67 |  | | | |
|  |  |  |  |  |  |  |
| **Projects with Part 8 Planning Approval** | | | | | | |
| **Local Electoral Area** | **Project Name** | **Part 8 Approved Date** | **No. of Units Approved @ Part 8** | **Current Status** | | |
| Clondalkin | Riversdale, Clondalkin | October 2018 | 44 | Plans currently being prepared to bring the project to tender for contractor in Q2 2019. | | |
| Clondalkin | Nangor Road (Dublin Simon Community CAS Project) | P.P. Approved 2017 (SD16A/0450) | 10 | DSC preparing final stage budget for Department of Housing Approval. Estimate site start Q2 2019. | | |
|  |  |  | 54 | | | |
| **Projects Pre-Part 8 Stage** | | | | | | |
|  | **Project Name** | **Part 8 publication target** | **Indicative No. of Units** | **Current Status** | | |
| Clondalkin | Balgaddy | April 2019 | 74 | Currently at Part 8 consultation stage closing on the 22nd of March. Part 8 will be brought to April Council meeting. | | |
| Clondalkin | Greenfort Gardens | April 2019 | 2 | Currently at Part 8 consultation stage closing on the 22nd of March. Part 8 will be brought to April Council meeting. | | |
| Clondalkin | Eircom Site (Nangor Road) | To Be Confirmed | 92 | Cost Benefit Analysis currently being prepared for Department of Housing funding consideration– project will be in excess of €20m. Scheme will progress to Part 8 following completion of CBA. | | |
| Clondalkin | St. Mark Avenue | To Be Confirmed | 32 | Plans being prepared for Part 8.Target April to publish Part 8 plans. | | |
| Clondalkin | 2 AHB Sites at Collinstown Grove | To Be Confirmed | 10 | Schemes being designed by Túath Housing for Part 8 publication. | | |
|  |  |  | **210** |  | | |

|  |  |  |
| --- | --- | --- |
| **Part V Delivery Programme for 2019** | | |
| **Scheme Name** | **No. of Units Being Delivered** | **Status of Part V Agreement** |
| Broadfield, Rathcoole | 11 | Part V costs currently being negotiated with developer. |
| Corner Park (Newcastle) | 5 | Part V agreement finalised with developer. Units due for delivery in Q2 2019. |
| Windmill, Rathcoole | 3 | Part V agreement finalised with developer. Units due for delivery in Q2 2019. |
| **Grand Total** | 19 |  |