Clondalkin Local Electoral Area

Housing Capital Programme Quarterly Report

Q1 2019

| 2019 Capital Housing Supply Programme |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| LA Build | AHB Build | Part V | Total Build | LA Acquisitions | AHB Acquisitions | Total Acquisitions | Voids | Total 2019 Capital Supply |
| 112 | 111 | 125 | 348 | 37 | 9 | 46 | 21 | 415 |

| Clondalkin Area Committee Report |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Programme for 2019 |  |  |  |  |  |  |
| Local Electoral Area | Local Authority Build | Part V | AHB Build | LA Acquisition | AHB Acquisition | Grand Total |
| Clondalkin | 63 | 19 | 10 | 11 | 16 | 119 |  |  |

| Local Electoral Area | LA Acquisition | AHB Acquisition | Grand Total |
| --- | --- | --- | --- |
| Clondalkin | 1 | 1 | 2 |

| Construction Programme 2019-2021 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Construction Projects on Site |  |  |  |  |  |  |
| Local Electoral Area | Project Name | No. of Units | Current Status |  |  |  |
| Clondalkin | Collinstown Grove (CAS Build Project) | 4 | Túath Housing CAS Construction Project. Contractor appointed and was commencing on site 11/03/2019. |  |  |  |
| Clondalkin | St. Cuthberts | 63 | Construction commenced in 2018. Scheme progressing which is due for completion in Q3 2019 |  |  |  |
|  |  | 67 |  |  |  |  |
| Projects with Part 8 Planning Approval |  |  |  |  |  |  |
| Local Electoral Area | Project Name | Part 8 Approved Date | No. of Units Approved @ Part 8 | Current Status |  |  |
| Clondalkin | Riversdale, Clondalkin | October 2018 | 44 | Plans currently being prepared to bring the project to tender for contractor in Q2 2019. |  |  |
| Clondalkin | Nangor Road (Dublin Simon Community CAS Project) | P.P. Approved 2017 (SD16A/0450) | 10 | DSC preparing final stage budget for Department of Housing Approval. Estimate site start Q2 2019. |  |  |
|  |  |  | 54 |  |  |  |
| Projects Pre-Part 8 Stage |  |  |  |  |  |  |
|  | Project Name | Part 8 publication target | Indicative No. of Units | Current Status |  |  |
| Clondalkin | Balgaddy | April 2019 | 74 | Currently at Part 8 consultation stage closing on the 22nd of March. Part 8 will be brought to April Council meeting. |  |  |
| Clondalkin | Greenfort Gardens | April 2019 | 2 | Currently at Part 8 consultation stage closing on the 22nd of March. Part 8 will be brought to April Council meeting. |  |  |
| Clondalkin | Eircom Site (Nangor Road) | To Be Confirmed | 92 | Cost Benefit Analysis currently being prepared for Department of Housing funding consideration– project will be in excess of €20m. Scheme will progress to Part 8 following completion of CBA. |  |  |
| Clondalkin | St. Mark Avenue | To Be Confirmed | 32 | Plans being prepared for Part 8.Target April to publish Part 8 plans. |  |  |
| Clondalkin | 2 AHB Sites at Collinstown Grove | To Be Confirmed | 10 | Schemes being designed by Túath Housing for Part 8 publication. |  |  |
|  |  |  | 210 |  |  |  |

| Part V Delivery Programme for 2019 |  |  |
| --- | --- | --- |
| Scheme Name | No. of Units Being Delivered | Status of Part V Agreement |
| Broadfield, Rathcoole | 11 | Part V costs currently being negotiated with developer. |
| Corner Park (Newcastle) | 5 | Part V agreement finalised with developer. Units due for delivery in Q2 2019. |
| Windmill, Rathcoole | 3 | Part V agreement finalised with developer. Units due for delivery in Q2 2019. |
| Grand Total | 19 |  |