Clondalkin Local Electoral Area

Housing Capital Programme Quarterly Report

Q3 2019

| Department of Housing Targets for South Dublin County Council 2019 |  |  |  |
| --- | --- | --- | --- |
|  | Build | Acquisitions | Total |
| Target | 435 | 76 | 511 |

| Capital Housing Delivered to End August 2019 Clondalkin Area |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Clondalkin LEA | Local Authority Build | AHB Build | Part V | Total Build | LA Acquisition | AHB Acquisition | Total Acquisitions | Grand Total |
| Grand Total | 0 | 4 | 7 | 11 | 4 | 13 | 17 | 28 |

| Construction Programme 2019-2021 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Construction Projects on Site |  |  |  |  |  |  |
| Local Electoral Area | Project Name | No. of Units | Current Status |  |  |  |
| Clondalkin | Collinstown Grove | 4 | Túath Housing CAS Construction Project. Contractor appointed and commenced on site 11/03/2019 |  |  |  |
| Clondalkin | St. Cuthberts | 63 | On site. Completion Quarter 4. |  |  |  |
| Projects with Part 8 Planning Approval |  |  |  |  |  |  |
| Local Electoral Area | Project Name | Part 8 Approved Date | No. of Units Approved @ Part 8 | Current Status |  |  |
| Clondalkin | Riversdale, Clondalkin | October 2018 | 44 | Project out to tender for contractor end August 2019. |  |  |
| Clondalkin | Nangor Road (Dublin Simon Community CAS Project) | P.P. Approved 2017 (SD16A/0450) | 10 | Department of Housing budget approval received August 2019. Construction to commence Sept/October 2019. |  |  |
|  |  |  | 54 |  |  |  |
| Projects Pre-Part 8 Stage at the end of August 2019 |  |  |  |  |  |  |
|  | Project Name | Part 8 publication target | Indicative No. of Units | Current Status |  |  |
| Clondalkin | Eircom Site (Nangor Road) | 11/07/2019 | 92 | Cost Benefit Analysis currently being prepared for Department of Housing funding consideration– project will be in excess of €20m. Part 8 report being presented to Council on the 9th of September. |  |  |
|  |  |  | 92 |  |  |  |

| Part V Agreements in Place |  |  |
| --- | --- | --- |
| Scheme Name | No. of Units Being Delivered | Status of Part V Agreement |
| Windmill, Rathcoole | 3 | Part V agreement finalised with developer. Two units delivered in Q2 2019 with final unit to deliver in Q3 2019. |
| Grand Total | 3 |  |