## Ph 1-4
Figure 4.13 INFRASTRUCTURE, SERVICES, FACILITIES AND AMENITIES - Phases 1-4 | Phase | 1A | 1B | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 to 13
| DWELLING No. | 0-500 | 501- 1,000 | 1,001- 1,800 | 1,801- 2,600 | 2,601- 3,400 | 3,401- 4,200 | 4,201- 5,000 | 5,001- 5,800 | 5,801- 6,600 | 6,601- 7,400 | 7,401- 8,200 | 8905
Upgrade R120 Newcastle Road / Footpath |  | 1A: Complete
One side of Adamstown Link Road (Adamstown Avenue) as a haul road |  | 1A: Complete
New junction on the R120 Newcastle Road at Adamstown Castle |  | 1A: Complete
Initial section of Adamstown Station Road |  | 1A: Complete
Initial northern section of Loop Road #1 |  | 1A: Complete
The Lucan - Palmerstown High Level Water Supply Scheme |  | 1A: Complete
Pro-rata childcare provision as per Planning Scheme |  | 1A: Complete
The Outer Ring Road (ORR) between the N4 and the N7 |  | 1B: Complete
One side of the Adamstown Link Road as a two-way single carriageway road |  | 1B: Complete
The Main Adamstown Station Road |  | 1B: Complete
Adamstown Railway Station and surface park and ride car park |  | 1B: Complete
The remaining parts of Loop Road #1 as a haul road |  | 1B: Complete
Surface water works for northeast/southeast drainage catchments |  | 1B: Complete
Pro-rata childcare provision as per the Planning Scheme |  | 1B: Complete
Adamstown Station access road as a haul road |  | 2: Complete
Upgrade existing Lucan-Esker and Lucan Low-Level pump stations |  | 2: Complete
Construction of Primary Schools Nos. 1 & 2 and / or Secondary School |  | 2: Complete
Community Centre: Option 1 or Option 2 |  | 2: SDZ16A/001
All Weather Pitch |  | 2: Complete
Loop Road #1 and alternative access for eastern section of Tandy’s Lane |  | 2: Complete
Surface water drainage on a pro-rata basis |  | 2: Complete
Completion of R120 Newcastle Road study as part of Lucan Movement Framework Plan |  | 2: Complete
Both sides of Adamstown Link Road (Adamstown Avenue) to provide 2 way QBC and carriageways |  | 3: Complete
Adamstown Station Road |  | 3: Complete
Northern section of Loop Road #3 as a haul road |  | 3: Complete
Tobermaclugg pump station and associated works |  | 3: Complete
Upgrade Tobermaclugg Stream between SDZ lands and N4 |  | 3: Complete
QBC busway on Adamstown Avenue (from junction with ORR to Adamstown Park) |  | 3: Complete
Northern section of Loop Road #2 |  | 3: Complete
Commencement of Tandy’s Lane Park or Airlie Park |  | 3: Commenced
Minimum floor space at Tandy’s Lane village or Tobermaclugg Local Centre OR minimum floorspace at Adamstown District Centre of 1,800 sq.m |  | 3: Under construction
Eastern section of Loop Road around Adamstown District Centre |  | 3: Complete
District Centre busway loop road adjoining Adamstown Station |  | 3: Complete; 4: see also Phases 5 & 7
Minimum of 65 no. full time childcare spaces |  | 3: Complete
Surface water drainage on a pro-rata basis |  | 3: Complete
Any necessary improvement works to the R120 Newcastle Road arising from the Newcastle Road Study |  | 3: Complete
Construction of Primary Schools Nos. 1 & 2 and / or Secondary School |  | 4: Complete
Completion of Tandy’s Lane Park or Airlie Park, either of which commenced in Phase 3
Link Road to rear of existing Lucan District Centre
Northern, central and southern sections of the central spine of Loop Road #2 (Adamstown Boulevard) and QBC Busway
Part of the northern section of Loop Road #3
Two cross links between Loop Roads #1 and #2 (one of which comprises north eastern section of Loop Road around Adamstown Distirct Centre)
Surface water drainage on a pro-rata basis

## Ph 5-13
Figure 4.3 Infrastructure, Services, Facilities and Amenities - Phases 5-13 | Phase | 1A | 1B | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 to 13
| DWELLING No. | 0-500 | 501- 1,000 | 1,001- 1,800 | 1,801- 2,600 | 2,601- 3,400 | 3,401- 4,200 | 4,201- 5,000 | 5,001- 5,800 | 5,801- 6,600 | 6,601- 7,400 | 7,401- 8,200 | 8905
Health Centre | bar: 5
Commencement of Tandy’s Lane Park or Airlie Park (whichever has not been provided in Phases 3-4) | bar: 5
Minimum floor space at Tandy’s Lane village or Tobermaclugg Local Centre OR minimum floorspace at Adamstown District Centre of 3,600 sq.m | bar: 5
North western section of Loop Road around Adamstown District Centre | bar: 5
District Centre busway loop road adjoining Adamstown Station | bar: 5
Minimum of 65 no. full time childcare spaces | bar: 5
Site made available for Primary School No. 3 | bar: 5
Doubling of the Dublin - Kildare suburban railway |  | 5: Complete
Adamstown Railway Station |  | 5: Complete
Further assessment of sewerage works and works to upgrade the 9B sewer if required | bar: 5
Surface water drainage on a pro-rata basis | bar: 5
New junction on the R403 Celbridge Road | bar: 5
Celbridge Link Road and remaining section of northern part of Loop Road #3 as haul roads (see Figure 4.7a) | bar: 5
A further cross link road between Loop Roads #1 and #2
Opening of Primary School No. 3
Provision of Civic Centre / Library Building
Completion of Tandy’s Lane Park or Airlie Park (whichever commenced in Phase 5)
Surface water drainage on a pro-rata basis
Celbridge Link Road and remaining section of northern part of Loop Road #3 as haul roads
Minimum floor space at Tandy’s Lane village or Tobermaclugg Local Centre OR minimum floorspace at Adamstown District Centre of 7,200 sq.m | bar: 7
Western section of Loop Road around Adamstown District Centre | bar: 7
District Centre busway loop road adjoining Adamstown Station (if not yet provided) | bar: 7
Minimum of 100 no. full time childcare spaces | bar: 7
Permanent Railway Park and Ride | bar: 7
Construction of a Leisure Centre with a swimming pool | bar: 7
Link road south from Loop Road around Adamstown District Centre to the west of Adamstown Station | bar: 7
Commencement of the Central Boulevard Urban Park | bar: 7
Site made available for Primary School No. 4 | bar: 7
All but the southernmost section of Loop Road #3 | bar: 7
Surface water drainage on a pro-rata basis | bar: 7
The Celbridge Link Road | bar: 7
The southernmost section of Loop Road #3
A cross link road between Loop Roads #2 and #3 to the south of Airlie Park
Local Centre 1: Tandy’s Lane OR Tobermaclugg Local Centre (if not already provided)
Minimum of 100 no. full time childcare spaces
Link road south from the northern section of Loop Road #3 to intersect with cross link south of Airlie Park
Opening of Primary School No. 4
Completion of Central Boulevard Urban Park
Provision of an Enterprise Centre
A central north-south link between the two cross links joining Loop Roads #2 and #3 | bar: 9
Local Centre 2: Tandy’s Lane OR Tobermaclugg Local Centre (if not already provided) | bar: 9
Minimum of 100 no. full time childcare spaces | bar: 9
Commencement of Tobermaclugg Park | bar: 9
Adamstown District Centre to provide the remainder of the minimum retail and retail services requirement
Minimum of 70 no. full time childcare spaces
Completion of Tobermaclugg Park
Further intensification of development up to the maximum number of dwellings permissible