|  |  |  |
| --- | --- | --- |
| **Actions** | **Responsibility** | **Time Frame** |
| **Raise awareness of roles and responsibility of various stakeholder relating to litter management** | **Enforcement & Licensing** | Ongoing |
| **Implement all relevant legislation, regulations and byelaws** | **Enforcement & Licensing** | Ongoing active enforcement of all provisions of the Litter Pollution Act 1997, as amended, Waste Management Acts & Associated regulations, Control of Dogs – dog fouling  **Legal Proceedings**  **July – Sept ‘19**  **12** cases referred prosecution  **8** cases listed for court hearing  **0** appeal listed for court hearing |
| **Continue to operate the Customer Relations Management Systems (MembersNet, FYS, Customer Contact System, Environmental Complaints System) to track complaints/reports from initial contact to resolution** | **Enforcement & Licensing** | **July – Sept 2019**  **Total 969**  Members Net: **126**  Fix your street: **240**  ECS: **603**  No. of reports of Drug Paraphernalia: **0** |
| **Investigate incidents of littering and illegal dumping** | **Enforcement & Licensing** | Ongoing foot patrols by Litter Warden service, with emphasis on county towns and villages. All incidents reported investigated for evidence  **Fixed Payments Notices issued** July – Sept 2019  **Total 136**  Illegal dumping and litter: 105  Failing to keep public place litter free: **1**  Dog Fouling**: 1**  Unauthorised signs: **29** |
| **Maintain high profile targeted warden service with foot and drive by patrols as appropriate in towns, villages, cemeteries and allotments** | **Enforcement & Licensing** | Ongoing |
| **Use overt and covert CCTV cameras and technologies to monitor areas prone to illegal dumping and to support enforcement action** | **Enforcement & Licensing** | CCTV/ Rapid Deployment Cameras installed  Audio devices at Ballyowen Bottle Banks and Sean Walsh Park Bottle Banks, Killinarden Bring Bank and Griffeen Road Bring Bank. |
| **Engage on a regional basis to develop solutions to tackle dumping in the Dublin region (Smart Dublin)** | **Enforcement & Licensing** | Ongoing |
| **Manage and maintain Memorandums of Understanding with utility companies in relation to graffiti removal** | **Enforcement & Licensing** | Ongoing |
| **Operation of village cleaning programme including weekend service** | **Public Realm** | Daily village cleansing in all town and village centres (Monday to Friday and Sundays) was undertaken throughout Q3 2019  Continuous village maintenance work in Tallaght, Clondalkin and Lucan undertaken throughout Q3 2019  Litter bin and cleaning service carried out in various parks on bank holiday weekends (Sean Walsh, Tymon, Corkagh and Griffeen Valley) throughout Q3 2019 |
| **Planned and scheduled clean-ups of identified litter blackspots in the county** | **Public Realm** | Continuous clean ups of areas prone to repetitive instances of illegal dumping (Scheduled and planned) |
| **Servicing and maintenance of Bring Banks to ensure that they are litter free** | **Public Realm** | Ongoing service of facilities by three service providers (69 recycling / bring centres). |
| **Conclude review litter bin provision in Public Realm having regard to Litter Bin Placement Protocol** | **Public Realm** | Ongoing |
| **Enforce litter control measures in Conditions of Allocation for Playing Fields** | **Public Realm** | On going |
| **Targeted inspection of playing pitches with high litter issues** | **Public Realm** | On going |
| **Use of internal systems to track and manage the removal graffiti from public property.** | **Public Realm** | On going |
| **Targeted programme to remove bonfire material from public places in advance of Halloween** | **Public Realm** | Completed |
| **Mapping of Halloween bonfires to identify trends and inform planned interventions** | **Public Realm** | Underway at the time of this report |
| **Clean up and removal of Halloween bonfire material in timely manner** | **Public Realm** | Underway at the time of this report |
| **Operate Laneway Maintenance programme at identified locations across the county and continue to seek solutions to issue** | **Public Realm** | Ongoing |
| **Provide scheduled waste removal for registered local community groups engaged in community clean ups** | **Public Realm** | Ongoing |
| **Participation and support for National Spring Clean events** | **Public Realm** | Completed in Q2; support provided to 82 events |
| **Promote Anti-Litter & Anti-graffiti promotional/media awareness schedule (dog fouling, anti-litter, illegal dumping, anti-graffiti radio and cinema advertisement campaigns)** | **Communication & Awareness** | Campaigns ongoing on radio and in cinema to promote this initiative. Awaiting Anti-Litter Grant income to commence new advertising campaigns. |
| **Implement pilot South Dublin Canvas pilot project** | **Communication & Awareness** | This is now completed for 2019.  23 boxes done from 2019 selection, also 12 boxes carried forward from 2018 scheme completed. |
| **Administer Anti-Litter and Anti-Graffiti Awareness Grant** | **Communication & Awareness** | AL/AG Grant 2019 advertised out / scored (12 applicants) awaiting funding from department to issue out PO’s to all applicants. LA21 Grant2019 was advertised out 5th Sept. 63 applicants in total. Awaiting departments decision on the funding for projects put forward. |
| **Promote environmental schools’ poster and slogan competition** | **Communication & Awareness** | Completed Q2. All posters put up outside the winning school and surrounding areas of St. Bernadette’s NS. |
| **Promote the Green Dog Walkers initiative and responsible dog ownership** | **Communication & Awareness** | Promoted out through social media also out through the Tidy Towns groups. Stand available for any groups to promote. |
| **Promote National Gum Litter Task Force** | **Communication & Awareness** | Advertised out through social media in April. |
| **Promote and support National Spring Clean** | **Communication & Awareness** | Completed in Q2. 82 groups in total signed up. Photo call to launch event with Mayor on 20th March. Dublin clean-up day April 27th 13 sign ups in total. |
| **Promote and support the PURE Initiative** | **Communication & Awareness** | Env Awareness continue to support Pure initiative. |
| **Promote and support Tidy Towns Initiative** | **Communication & Awareness** | This is on- going for Green Dog Walkers and Stop Food Waste initiatives. Bulbs not Bonfires advertised out as part of Halloween campaign. |
| **Review and promote Social Credit Scheme** | **Communication & Awareness** | Env Awareness continues to promote SCS. Minor landscaping and paint enhancement scheme advertised out again on all social media platforms. Application ongoing for both schemes. |
| **Support community groups through Social Credit Scheme** | **Communication & Awareness** | Minor landscaping and the paint scheme are now available to all groups under this scheme.  Allotments were supplied with over 100 Hessian bags for composting.  Bulbs not Bonfires advertised out and completed. WEEE recycling in county hall and libraries, Ballymount passes for SCS groups.  Figures for SCS  July: 231  August: 188  September: 233 |
| **Provide support and administer the Green Schools Programme** | **Communication & Awareness** | Green school’s newsletter sent out to all schools at start of seminar. Green school’s seminar took place 24th Sept in Tallaght library. |
| **Promote Seasonal Campaigns** | **Communication & Awareness** | **July:**  Pooper scoopers ongoing campaigns.  Dublin Art Canvas selection process complete boxes started and put out on social media.  Dashboard dining campaign being developed.  Trifocal food waste seminar.  Hessian bags given to allotments 65 in total so far. extra bio-degradable bags given out to libraries with stands.  Water bottles given out to all who took part in bike week.  Paint enhancement scheme advertised out again.  Plastic free July advertised out on all social media platforms.  **August:**  Mattress Amnesty advertised out took place 10th August.  Green school newsletter designed and sent to print.  **September:**  Green school’s newsletter sent out to all schools.  Green school’s seminar took place Sept 25th in Tallaght library. Over 18 different schools took part.  Launch of reuse month also took place this day with the Mayor.  Bulbs ordered for Halloween campaign.  Extra Hessian bags ordered for Halloween Campaign.  Ballymount passes designed and sent for print. |