SOUTH DUBLIN COUNTY COUNCIL

COMHAIRLE CHONTAE ÁTHA CLIATH THEAS

# MEETING OF TALLAGHT AREA COMMITTEE (1)

Monday 20th March, 2006

Item H-I (12)

Report on Implementation of Traveller Accommodation Programme 2005 - 2008

The assessment of Traveller accommodation needs conducted in association with the process leading to the adoption of the Traveller Accommodation Programme 2005 - 2008 indicated that there is a need to provide 215 units of Traveller-specific accommodation throughout the County during the course of the programme.  This accommodation is to cater for both immediate requirements and future family formations.

To date, twenty units of Traveller-specific permanent accommodation have been delivered under the 2005 – 2008 programme and it is anticipated that 40 units of permanent and emergency accommodation will be completed in 2006.

The Council adopted the Traveller Accommodation Programme 2005 – 2008 unanimously on 9th May 2005.

The incomplete elements of the previous accommodation programme form the first phase of the current accommodation programme.

The following is the current position on developments at various stages of delivery in this Area Committee’s jurisdiction.

| Traveller Accommodation Programme 2005 - 2008 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Scheme |  | Type and No. of Units | Part X/8 Advertised |  | Architect |  | Comments |  |
| Belgard Park |  | R.C.P. – 10 Bays |  |  |  |  | Residents moved into RCP on 5th May 2005. |  |
| Daletree Place |  | 10 Group Houses |  |  |  |  | Residents moved into houses in August 2005. |  |
| St. Aidan’s Close Brookfield |  | Group Houses – 5. | 22/04/03 |  | G.A.P. |  | Under construction. Scheduled to be completed by Spring 2006. |  |
| Hazel Hill, Killinardin |  | Group Houses – 5 R.C.P. – 5 Bays | Completed |  | M.V. Cullinan |  | Currently on site |  |
| Fortunestown |  | 10 Group Houses – |  |  | SAB |  | On site since December 2005. Scheduled to be completed in 2006. |  |
| Rathcoole | 10 group houses |  |  | Part X completed |  | Arch Services Dept |  | On hold awaiting resolution of access road issue. |
| Stocking Lane | 10-bay RCP |  |  | December 2004 |  | GAP Architects |  | Awaiting cost plan approval from Department of the Environment, Heritage and Local Government |

Belgard Road Re-development - Scheduled to start construction in 2008.  Further progress on this scheme dependent on TT Master Plan and current planning permission application