|  |
| --- |
| **South Dublin Development Plan 2022-2028** |
| **Stage** | **Process** | **Timeframe[[1]](#endnote-1)** | **Dates** |
| **Pre-Draft**  | Pre-draft **Notice** Public Consultation  | Not less than 8 Weeks Commencing 31st July 2020  | 31st July - 28th September |
| Prepare Chief Executives Report on Pre-Draft Submissions  | Not later than 16 weeks from date of Notice | 29th September to 19th November prepare CE Report |
| Issue CE Report to Cllrs |  | 19th November 2020 Issue CE report |
| Councillors Consider Chief Executive’s Report on Submissions and make directions  | Not later than 10 weeks from date CE Report submitted.**Additional 9 days added to timeframe as per S.251 of the Act** | 20th November 2020 to 4th February 2021 By 4th February 2021 Issue Directions |
| **Chief Executive’s Draft Plan** | Preparation of Chief Executive’s Draft Plan and its submission to the members  | Not later than 12 weeks following receipt of Directions from members | 4th February to 28th AprilCE Draft Plan submitted to members by 28th April |
| Councillors Consider Chief Executive’s Draft Plan and deem it to be the Draft Plan unless amended  | Within 8 Weeks of the submission of the Draft to members | 28th April to 22nd June |
| **Draft Plan**  | Preparation of Draft County Development Plan and issuing of **notice** | Prepare and issue within 2 weeks of date of resolution | 22nd June to **5th July** |
| Draft Plan Public Consultation  | Not less than 10 Weeks  | 5th July to 14th September  |
| Chief Executive’s Report on Draft Plan submissions submitted to members. | Not later than 22 weeks from the date of issuing notice | 15th September to 3rd December 2021Issued by 3rd December |
| Councillors consider Draft Plan and CE Report. Councillor’s now ADOPT or AMEND Draft Plan  | Within 12 weeks of submission of CE Report **Additional 9 days added to timeframe as per S.251 of the Act** | 3rd December 2021 to 3rd March 2022 **If Plan adopted it will come into effect on the 13th April 2022** |
| **Amendments to Draft Plan** | Preparation of Amendments to Draft Plan  | Not later than 3 weeks from resolution.(or more if required by AA or SEA) | 3rd March to 23rd March |
| Public Consultation on Amendments to Draft Plan  | Not less than 4 Weeks | If no AA/SEA issues consultation runs from the 23rd March until the 20th April 2022 |
| **Preparation of Chief Executives Report on Submissions**  | CE Report prepared and submitted to members not later than 8 weeks from date of notice  | CE Report to Councillors by 17th May 2022 |
| Councillors consider Amendments and Chief Executive’s Report. Plan must now be MADE  | Within 6 weeks from submission of report | 17th May to 27th June 2022Development Plan is made. |
| **Adopted Plan**  | South Dublin County Development Plan comes into effect | 6 weeks after the Plan is made | 8th August County Development Plan comes into effect |

1. Exact dates may be subject to change over the course of the process. [↑](#endnote-ref-1)