| South Dublin Development Plan 2022-2028 |  |  |  |
| --- | --- | --- | --- |
| Stage | Process | Timeframe | Dates |
| Pre-Draft | Pre-draft Notice Public Consultation | Not less than 8 Weeks Commencing 31st July 2020 | 31st July - 28th September |
|  | Prepare Chief Executives Report on Pre-Draft Submissions | Not later than 16 weeks from date of Notice | 29th September to 19th November prepare CE Report |
|  | Issue CE Report to Cllrs |  | 19th November 2020 Issue CE report |
|  | Councillors Consider Chief Executive’s Report on Submissions and make directions | Not later than 10 weeks from date CE Report submitted. Additional 9 days added to timeframe as per S.251 of the Act | 20th November 2020 to 4th February 2021 By 4th February 2021 Issue Directions |
| Chief Executive’s Draft Plan | Preparation of Chief Executive’s Draft Plan and its submission to the members | Not later than 12 weeks following receipt of Directions from members | 4th February to 28th April CE Draft Plan submitted to members by 28th April |
|  | Councillors Consider Chief Executive’s Draft Plan and deem it to be the Draft Plan unless amended | Within 8 Weeks of the submission of the Draft to members | 28th April to 22nd June |
| Draft Plan | Preparation of Draft County Development Plan and issuing of notice | Prepare and issue within 2 weeks of date of resolution | 22nd June to 5th July |
|  | Draft Plan Public Consultation | Not less than 10 Weeks | 5th July to 14th September |
|  | Chief Executive’s Report on Draft Plan submissions submitted to members. | Not later than 22 weeks from the date of issuing notice | 15th September to 3rd December 2021 Issued by 3rd December |
|  | Councillors consider Draft Plan and CE Report. Councillor’s now ADOPT or AMEND Draft Plan | Within 12 weeks of submission of CE Report Additional 9 days added to timeframe as per S.251 of the Act | 3rd December 2021 to 3rd March 2022 If Plan adopted it will come into effect on the 13th April 2022 |
| Amendments to Draft Plan | Preparation of Amendments to Draft Plan | Not later than 3 weeks from resolution. (or more if required by AA or SEA) | 3rd March to 23rd March |
|  | Public Consultation on Amendments to Draft Plan | Not less than 4 Weeks | If no AA/SEA issues consultation runs from the 23rd March until the 20th April 2022 |
|  | Preparation of Chief Executives Report on Submissions | CE Report prepared and submitted to members not later than 8 weeks from date of notice | CE Report to Councillors by 17th May 2022 |
|  | Councillors consider Amendments and Chief Executive’s Report. Plan must now be MADE | Within 6 weeks from submission of report | 17th May to 27th June 2022 Development Plan is made. |
| Adopted Plan | South Dublin County Development Plan comes into effect | 6 weeks after the Plan is made | 8th August County Development Plan comes into effect |

Exact dates may be subject to change over the course of the process.