COMHAIRLE CONTAE ÁTHA CLIATH THEAS
SOUTH DUBLIN COUNTY COUNCIL

MEETING OF LUCAN-PALMERSTOWN-FONTHILL AREA COMMITTEE

Tuesday, 26 May 2020

HEADED ITEM NO.9

Q1 2020 Housing Supply Programme Quarterly Report

| 2019 Total Housing Delivered |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Build | Acquisition | Leasing | HAP & RAS | Total |
| Department of Housing, Planning and Local Government Targets | 435 | 76 | 150 | 1,053 | 1,704 |
| Actual 2019 Output | 449 | 93 | 49 | 956 | 1,547 |
| % | 103% | 122% | 33% | 91% | 91% |

| Housing Delivered 2019 Lucan-Palmerstown-Fonthill Area |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Local Electoral Area | Build | Part V | Total Build | Total Acquisitions | Total Leasing | Grand Total |
| Lucan | 34 | 56 | 90 | 13 | 11 | 114 |
| Palmerstown- Fonthill | 0 | 0 | 0 | 7 | 0 | 7 |
|  | 34 | 56 | 90 | 20 | 11 | 121 |

| Total Projected Housing Delivery 2020 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Build | Part V | Total Build | Total Acquisitions | Total Voids | Total Leasing | RAS & HAP | Grant Total Projected Delivery |
| 309 | 94 | 403 | 30 | 21 | 90 | 1,000 | 1, 544 |

| Projected Housing Delivery Programme 2020 Lucan-Palmerstown-Fonthill Area |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Local Electoral Area | Build | Part V | Total Build | Total Leasing | Grand Total |
| Lucan | 7 | 9 | 7 | 0 | 7 |
| Palmerstown- Fonthill | 40 | 0 | 40 | 0 | 40 |
| Grand Total | 47 | 0 | 47 | 0 | 47 |

| Construction Programme 2020-2021 |  |  |  |  |
| --- | --- | --- | --- | --- |
| Projects with Part 8 Planning Approval |  |  |  |  |
| Local Electoral Area | Project Name | Part 8 Approved Date | No. of Units Approved @ Part 8 | Current Status |
| Fonthill/ Palmerstown | Balgaddy | 08/04/2019 | 69 | Stage 1 budget approval received from Department of Housing, Planning and Local Government. |
| Fonthill/ Palmerstown | Greenfort Gardens | 08/04/2019 | 2 | Tender complete and assessment of submissions currently underway. |
| Fonthill/ Palmerstown | St. Mark’s Avenue | 08/07/2019 | 41 | Stage 4 final budget approval received from the Department of Housing, Planning and Local Government. |
|  |  |  | 112 |  |

| Part V Agreements in place |  |  |
| --- | --- | --- |
| Scheme Name | Number of Part V Units | Details |
| Lock Road/Newcastle Road, Finnstown | 9 | Part V agreement in place. Total Scheme of 94 units. Respond! Housing association to acquire all of the units. |
| Total | 9 |  |