## Slide 1: South Dublin School Street – project update.

## Slide 2: What is a School Street?
A school street is a road outside a school, or schools, with a temporary restriction on motorised traffic during school drop-off and pick-up times. The restriction, generally, applies to school related traffic and through traffic.
Grove Road, Malahide. Photo courtesy of Fingal County Council.

## Slide 3: Rational for School Streets
Road Safety - reducing motorised traffic around the school environment makes it safer to cycle, walk and scoot.
Environmental - reducing dependence on the motorised car reduces CO2 emissions, noise pollution and improves air quality.
Health - traffic free environments encourage more people to walk and cycle which improves our physical and mental health.
Grove Road, Malahide. Photo courtesy of Fingal County Council.

## Slide 4: South Dublin School Street - Assessment
Primary schools evaluated against following selection criteria:
Presence of School Warden,
Road category: Regional, Local, Residential etc.,
Presence of public transport outside school,
Green-Schools Ireland, Active Schools etc.,
Potential for improved connectivity between school and pupil catchment,
Known traffic related issues outside school.

## Slide 5
School Street/Zone* Proposed Project Timeline:
ACM agreement 13th October,
Council agreement 9th November,
Initial School engagement to gauge and agree participation by December,
Procurement of supporting consultants by January 2021,
Survey and analysis February – March 2021,
Design work April – May 2021,
Scheme implementation by September 2021.
*school street/zone

## Slide 6: Possible interventions:
Signing and lining,
Barriers to restrict traffic access,
Road realignment,
Improved pedestrian/cycling facilities,
Improved street design.

## Slide 7: RTFB ACM
Holy Spirit Schools, Limekiln Lane
Has a School Warden operating outside the school,
Local Access,
No bus route outside school, but PT nearby on St. Peter’s Road,
Both schools involved with Green-Schools and Senior School Awarded Green-Schools Travel,
Connectivity potential exists but to explored at a greater level during engagement/design phase,
Parking/congestion outside the school.

## Slide 8: RTFB ACM - Holy Spirit Schools, Limekiln Lane

## Slide 9: RTFB ACM - Holy Spirit Schools, Limekiln Lane

## Slide 10: RTFB ACM
Bishop Galvin/Shanahan Schools
Has 2 School Wardens operating outside the school,
Local Access,
Bus route on Rossmore Road, but not Templeogue Wood,
Bishop Shanahan is working on Green-Schools Travel,
Connectivity potential exists but to explored at a greater level during engagement/design phase,
Parking/congestion issues outside the school.

## Slide 11: RTFB ACM – Bishop Galvin/Shanahan Schools

## Slide 12: RTFB ACM – Bishop Galvin/Shanahan Schools

## Slide 13
THANK YOU
Q&A