COMHAIRLE CONTAE ÁTHA CLIATH THEAS
SOUTH DUBLIN COUNTY COUNCIL

Clondalkin Area Committee Meeting

17th February 2021

HEADED ITEM NO.15

Q1 2021 Housing Supply Programme Quarterly Report

|  | Capital Housing Delivered 2020 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Local Authority Build (Including PPP) |  | AHB Build | Part V | Total Build | LA Acquisition | AHB Acquisition | Total Acquisitions | Total Leasing | Voids | Grand Total |
| 109 |  | 156 | 105 | 370 | 12 | 21 | 33 | 123 | 10 | 536 |

| Housing Projected Delivery 2021 |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| LA Build | AHB Build | Part V | Total Build | LA Acquisitions | AHB Acquisitions |  | Total Acquisitions | Total Voids |  | Total Leasing |  | Total 2021 Projected Delivery |
| 63 | 198 | 107 | 368 | 13 | 17 |  | 30 | 10 |  | 150 |  | 558 |
| Department of Housing Build Target for 2021 |  |  | 408 |  |  | Department of Housing Leasing Target for 2021 |  |  | 190 |  | 598 |  |

| Housing Delivered 2020 Clondalkin Area |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Local Electoral Area | Local Authority Build Including PPP | AHB Build | Part V | Total Build | LA Acquisition | AHB Acquisition | Total Acquisitions | Total Leasing | Grand Total |
| Clondalkin | 109 | 148 | 24 | 281 | 4 | 3 | 7 | 47 | 335 |

| Housing Build Pipeline for 2021 Clondalkin Area |  |  |  |  |
| --- | --- | --- | --- | --- |
| Local Electoral Area | LA Build | AHB Build | Part V | Total |
| Clondalkin | 22 | 26 | 5 | 53 |

| Construction Programme 2021 |  |  |  |  |
| --- | --- | --- | --- | --- |
| Projects with Part 8 Planning Approval |  |  |  |  |
| Local Electoral Area | Project Name | Part 8 Approved Date | No. of Units Approved @ Part 8 | Current Status |
| Clondalkin | Riversdale | 08/10/2018 | 44 | Contractor commenced December 2020 on Phase 1 of 22 units. Off site during level 5 restrictions. |
| Clondalkin | Nangor Road (Eircom Site) | 14/10/2019 | 93 | Project progressing to tender Q2 2021. |
| Clondalkin | Lindisfarne, Clondalkin | 11/01/2021 | 19 | Part 8 approved January 2021. Project to progress to detailed design for tender. |
|  |  |  | 156 |  |

| Part V Delivery Programme for 2021 |  |  |
| --- | --- | --- |
| Scheme Name | No. of Units | Status of Part V Agreement |  |
| Aylmer Heath, Newcastle | 4 | Part V agreed on Phase 2 Aylmer Heath. Total of 17 units in Phase 2 being delivered by Respond Housing in 2021. |  |
| St. Finians Way, (Pavement Homes), Main St. Saggart | 1 | Part V being finalised for delivery in 2021. |  |
| Grand Total | 5 |  |  |