COMHAIRLE CONTAE ÁTHA CLIATH THEAS
SOUTH DUBLIN COUNTY COUNCIL

Tallaght Area Committee Meeting

22nd February 2021

HEADED ITEM NO.14

Q1 2021 Housing Supply Programme Quarterly Report

|  | Capital Housing Delivered 2020 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Local Authority Build (Including PPP) |  | AHB Build | Part V | Total Build | LA Acquisition | AHB Acquisition | Total Acquisitions | Total Leasing | Voids | Grand Total |
| 109 |  | 156 | 105 | 370 | 12 | 21 | 33 | 123 | 10 | 536 |

| Housing Projected Delivery 2021 |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| LA Build | AHB Build | Part V | Total Build | LA Acquisitions | AHB Acquisitions |  | Total Acquisitions | Total Voids |  | Total Leasing |  | Total 2021 Projected Delivery |
| 63 | 198 | 107 | 368 | 13 | 17 |  | 30 | 10 |  | 150 |  | 558 |
| Department of Housing Build Target for 2021 |  |  | 408 |  |  | Department of Housing Leasing Target for 2021 |  |  | 190 |  | 598 |  |

| Housing Delivered 2020 Tallaght Area |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Local Electoral Area | Local Authority Build Including PPP | AHB Build | Part V | Total Build | LA Acquisition | AHB Acquisition | Total Acquisitions | Total Leasing | Grand Total |
| Tallaght Central | 0 | 0 | 0 | 0 | 1 | 6 | 7 | 1 | 8 |
| Tallaght South | 0 | 1 | 46 | 47 | 3 | 4 | 7 | 22 | 76 |
| Total | 0 | 1 | 46 | 47 | 4 | 10 | 14 | 23 | 84 |

| Housing Build Pipeline for 2021 Tallaght Area |  |  |  |  |
| --- | --- | --- | --- | --- |
| Local Electoral Area | LA Build | AHB Build | Part V | Total |
| Tallaght Central | 0 | 40 | 0 | 40 |
| Tallaght South | 12 | 36 | 27 | 75 |
| Total | 12 | 76 | 27 | 115 |

| Construction Programme 2020-2021 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Projects with Part 8 Planning Approval |  |  |  |  |  |
| Local Electoral Area | Project Name | Part 8 Approved Date | No. of Units | Current Status |
| Tallaght South | St. Catherine's | 10/09/2018 | 12 | Construction commenced Q4 2020. Offsite January 2021 due to Level 5 Public Health Measures. |
| Tallaght Central | Fernwood & Maplewood | 08/10/2018 | 40 | Contractor commenced on site July 2020. Offsite January 2021 due to Level 5 Public Health Measures. |
| Tallaght Central | Whitestown Way | 10/12/2018 | 81 | Contractor appointed Q4 2020 and will commence on site once Public Health Measures permit. |
| Tallaght Central | Old Bawn (Brady's Field) | 11/02/2020 | 12 | Detailed design for tender underway. |
|  |  |  | 145 |  |

| Part V Agreements in Place |  |  |  |
| --- | --- | --- | --- |
| Electoral Area | Scheme Name | Number | Status |
| Tallaght South | City West Village Apartments | 24 | Part V Agreed. Units will be delivered in 2021. |
| Tallaght Central | Kingswood Castle, Tallaght | 2 | Part V agreed. Project under construction for delivery in 2021. The total scheme of 24 units is being acquired for social housing provision by Respond! Housing. |
| Tallaght South | The Mews, Kingswood, Tallaght | 1 | Part V agreed. For delivery 2021. |
| Tallaght South | Mountain Gate, Kiltipper. | 7 | Part V Agreed. Projected delivery 2022. |
|  |  | 34 |  |