COMHAIRLE CONTAE ÁTHA CLIATH THEAS
SOUTH DUBLIN COUNTY COUNCIL

MEETING OF RATHFARNHAM/TEMPLEOGUE/FIRHOUSE/BOHERNABREENA AREA COMMITTEE

Tuesday,11th May 2021

HEADED ITEM NO.4

Q2 2021 Housing Supply Programme Quarterly Report

|  | Housing Projected Delivery 2021 |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | LA Build | AHB Build | Part V | Total Build | LA Acquisitions | AHB Acquisitions |  | Total Acquisitions | Total Leasing |  | Voids |  | Total 2021 Projected Delivery |
| Pre-COVID Pipeline | 63 | 198 | 107 | 368 | 13 | 17 |  | 30 | 150 |  | 10 |  | 558 |
| Revised Pipeline 2021 | 2 | 146 | 97 | 245 | 13 | 17 |  | 30 | 150 |  | 0 |  | 425* |
|  | Department of Housing Build Target for 2021 |  |  | 408 |  |  | Department of Housing Leasing Target for 2021 |  |  | 190 |  | 598 |  |

* 2021 pipeline revised due to impact on programme of delivery during Level 5 restrictions.

| Housing Build Pipeline for 2021 Rathfarnham – Templeogue – Firhouse - Bohernabreena Area |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | LA Build | AHB Build | Part V | Total |
| Rathfarnham-Templeogue | 0 | 11 | 1 | 12 |
| Firhouse- Bohernabreena | 0 | 0 | 9 | 9 |
| Grand Total | 0 | 11 | 10 | 21 |

| Capital Housing Delivered 2021 to end April 2021 Rathfarnham – Templeogue – Firhouse - Bohernabreena Area |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Local Electoral Area | Local Authority Build | AHB Build | Part V | Total Build | LA Acquisition | AHB Acquisition | Total Acquisitions | Total Leasing | Grand Total |
| Rathfarnham- Templeogue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Firhouse- Bohernabreena | 0 | 0 | 9 | 9 | 1 | 0 | 1 | 1 | 11 |
| Grand Total | 0 | 0 | 9 | 9 | 1 | 0 | 1 | 1 | 11 |

| Construction Programme 2021 |  |  |  |  |
| --- | --- | --- | --- | --- |
| Projects with Part 8 Planning Approval |  |  |  |  |
| Local Electoral Area | Project Name | Part 8 Approved Date | No. of Units Approved @ Part 8 | Current Status |
| Firhouse/ Bohernabreena | Homeville | 10/09/2018 | 16 | Project on site with projection completion Q2 2022. |
| Rathfarnham/ Templeogue | Templeogue Village | 01/10/2018 | 11 | Tender complete and Stage 4 final budget application being submitted to Department of Housing to appoint contractor. |
|  |  |  | 27 |  |

| Next tranche of Proposed Part 8’s |  |  |
| --- | --- | --- |
| Scheme Location | Proposed no. of Units | Status |
| Pearse Brothers Park Rathfarnham | 10 | Proposed Older Persons specific housing noted at ACM in November 2020. Part 8 will be published in May 2021. |
| Total | 10 |  |

| Part V Delivery Programme for 2021 |  |  |  |
| --- | --- | --- | --- |
| Scheme Name | Firhouse/ Bohernabreena | Rathfarnham/ Templeogue | Status of Part V Agreement |
| Dodderbrook, Ballycullen | 9 |  | Part V units delivered Q1 2021. |
| Willowview, Ballyboden Road, Rathfarnham. |  | 1 | Part V agreed and units are due for delivery in Q2 2021. There is a total of 12 units within this scheme being acquired by Clúid Housing for Older Persons Housing. |
| Grand Total | 9 | 1 |  |

| Part V Agreements in Place |  |  |  |
| --- | --- | --- | --- |
| Scheme Name | Firhouse/ Bohernabreena | Rathfarnham/ Templeogue | Status of Part V Agreement |
| Scholarstown Woods, Rathfarnham | 14 | 0 | Part V agreement in place and 14 units due for delivery Q1 2022- delay due to Level 5 restrictions on construction. |
| Grand Total | 14 | 0 |  |