COMHAIRLE CONTAE ÁTHA CLIATH THEAS
SOUTH DUBLIN COUNTY COUNCIL

Tallaght Area Committee Meeting

24th May 2021

HEADED ITEM NO.2

Q2 2021 Housing Supply Programme Quarterly Report

|  | Housing Projected Delivery 2021 |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | LA Build | AHB Build | Part V | Total Build | LA Acquisitions | AHB Acquisitions |  | Total Acquisitions | Total Leasing |  | Voids |  | Total 2021 Projected Delivery |
| Pre-COVID Pipeline | 63 | 198 | 107 | 368 | 13 | 17 |  | 30 | 150 |  | 10 |  | 558 |
| Revised Pipeline 2021 | 2 | 146 | 97 | 245 | 13 | 17 |  | 30 | 150 |  | 0 |  | 425* |
|  | Department of Housing Build Target for 2021 |  |  | 408 |  |  | Department of Housing Leasing Target for 2021 |  |  | 190 |  | 598 |  |

* 2021 pipeline revised due to impact on programme of delivery during Level 5 restrictions.

| Housing Build Pipeline for 2021 Tallaght Area |  |  |  |  |
| --- | --- | --- | --- | --- |
| Local Electoral Area | LA Build | AHB Build | Part V | Total |
| Tallaght Central | 0 | 22 | 3 | 24 |
| Tallaght South | 0 | 0 | 32 | 32 |
| Total | 0 | 22 | 35 | 57 |

| Capital Housing Delivered 2021 to Date |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Local Electoral Area | Local Authority Build | AHB Build | Part V | Total Build | LA Acquisition | AHB Acquisition | Total Acquisitions | Total Leasing | Grand Total |
| Tallaght Central | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 4 | 5 |
| Tallaght South | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 11 | 12 |
| Grand Total | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 15 | 17 |

| Construction Programme 2020-2021 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Projects with Part 8 Planning Approval |  |  |  |  |  |
| Local Electoral Area | Project Name | Part 8 Approved Date | No. of Units | Current Status |
| Tallaght South | Catherine's Row, Tallaght | 10/09/2018 | 12 | Under construction. Projected delivery Q2 2022. |
| Tallaght Central | Fernwood & Maplewood | 08/10/2018 | 40 | Under construction. Projected delivery Q1 2022. |
| Tallaght Central | The Weir, Whitestown Way | 10/12/2018 | 81 | Contractor commenced on site May 2021. Projected delivery Q4 2022. |
| Tallaght Central | Old Bawn (Brady's Field) | 11/02/2020 | 12 | Detailed design underway to progress to tender Q3 2021. |
|  |  |  | 145 |  |

| Next tranche of Proposed Part 8’s |  |  |  |
| --- | --- | --- | --- |
| Scheme Location | Local Electoral Area | Proposed no. of Units | Status |
| St. Aongus’s Green | Tallaght Central | 12 | Proposed Older Persons specific housing noted at ACM in November 2020. Part 8 will be published in May 2021. |
| Total |  | 10 |  |

| Part V Delivery Programme for 2021 |  |  |  |
| --- | --- | --- | --- |
| Electoral Area | Scheme Name | Number | Status |
| Tallaght Central | Kingswood Castle, Tallaght | 2 | Part V agreed. Project under construction for delivery in Q2 2021. The total scheme of 24 units is being acquired for social housing provision by Respond! Housing. |
| Tallaght South | The Mews, Kingswood, Tallaght | 1 | Part V agreed. For delivery 2021. |
| Tallaght South | City West Quarter | 32 | Part V Agreed. Projected delivery 2021 |
|  |  | 35 |  |

| Part V Agreements in Place |  |  |  |
| --- | --- | --- | --- |
| Electoral Area | Scheme Name | Number | Status |
| Tallaght South | City West Village Apartments | 24 | Part V Agreed. Units will be delivered in 2022. |
| Tallaght South | Mountain Gate, Kiltipper. | 7 | Part V Agreed. Projected delivery Q1 2023. |
|  |  | 31 |  |