COMHAIRLE CONTAE ÁTHA CLIATH THEAS
SOUTH DUBLIN COUNTY COUNCIL

Lucan/Palmerstown/ North Clondalkin Area Committee Meeting

28th September 2021

HEADED ITEM NO.15

Q3 2021 Housing Supply Programme Quarterly Report

|  | Housing Projected Delivery 2021 |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | LA Build | AHB Build | Part V | Total Build | LA Acquisitions | AHB Acquisitions |  | Total Acquisitions | Total Leasing |  | Voids |  | Total 2021 Projected Delivery |
| Pre-COVID Pipeline | 63 | 198 | 107 | 368 | 13 | 17 |  | 30 | 150 |  | 10 |  | 558 |
| Revised Pipeline 2021 | 2 | 146 | 97 | 245 | 13 | 17 |  | 30 | 150 |  | 0 |  | 425* |
|  | Department of Housing Build Target for 2021 |  |  | 408 |  |  | Department of Housing Leasing Target for 2021 |  |  | 190 |  | 598 |  |

* 2021 pipeline revised due to impact on programme of delivery during Level 5 restrictions.

| Housing Build Pipeline for 2021 Lucan/Palmerstown/North Clondalkin |  |  |  |  |
| --- | --- | --- | --- | --- |
| Local Electoral Area | LA Build | AHB Build | Part V | Total |
| Lucan | 0 | 90 | 48 | 138 |
| Palmerstown -Fonthill | 2 | 0 | 0 | 2 |
| Total | 2 | 90 | 48 | 140 |

| Capital Housing Delivered 2021 to Date |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Local Electoral Area | Local Authority Build | AHB Build | Part V | Total Build | LA Acquisition | AHB Acquisition | Total Acquisitions | Total Leasing | Grand Total |
| Lucan | 0 | 32 | 0 | 32 | 0 | 0 | 0 | 11 | 43 |
| Palmerstown- Fonthill | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 |
| Grand Total | 0 | 32 | 0 | 32 | 0 | 0 | 0 | 19 | 51 |

| Construction Programme 2020-2021 |  |  |  |  |
| --- | --- | --- | --- | --- |
| Projects with Part 8 Planning Approval |  |  |  |  |
| Local Electoral Area | Project Name | Part 8 Approved Date | No. of Units Approved @ Part 8 | Current Status |
| Palmerstown -Fonthill | Balgaddy | 08/04/2019 | 69 | Tender design underway to progress to tender Q4 2021. |
| Palmerstown -Fonthill | Greenfort Gardens | 08/04/2019 | 2 | Under construction. Projected delivery Q4 2021. |
| Palmerstown -Fonthill | St. Mark’s Avenue | 08/07/2019 | 41 | Contractor appointed May 2021. Due to commence on site end of September 2021. |
| Palmerstown -Fonthill | Lucan Road, Palmerstown (Túath Housing) | 14/09/2020 | 4 | Stage 1 pre-qualification tender complete and assessment under way. Túath Housing to complete Stage 2 tender in Q4 2021 & progress to site start Q1 2022 (subject to DHLGH funding approval). |
| Palmerstown -Fonthill | St. Ronan’s Crescent | 13/09/2021 | 9 | Part 8 planning approved September 2021 to provide age friendly housing at St. Ronan’s Crescent, Clondalkin. |
|  |  |  | 125 |  |

| Part V Delivery Programme for 2021 |  |  |  |
| --- | --- | --- | --- |
| Electoral Area | Scheme Name | Number of Part V Units | Details |
| Lucan | Lock Road/Newcastle Road, Finnstown | 9 | Part V agreement in place. Total Scheme of 94 units. Respond Housing Association to acquire all of the units for delivery September/October 2021. |
| Lucan | Hallwell, Adamstown | 39 | Part V agreement in place. Housing delivery for Q4 2021. |
|  |  | 48 |  |

| Part V Agreements in Place |  |  |  |
| --- | --- | --- | --- |
| Electoral Area | Scheme Name | Number | Status |
| Lucan | Hallwell, Adamstown | 1 | Part V Agreed. Unit will be delivered in 2022. |
| Lucan | Somerton Phase 2 | 24 | Part V Agreed. Delivery expected 2022 |
| Lucan | St. Helens, Adamstown | 16 | Part V Agreed. Delivery expected 2023 |
| Palmerstown Fonthill | Cloverhill Road | 4 | Part V Agreement in Place. |
|  |  | 45 |  |